{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"macros":1,"external_links":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":8,"n_cols":32,"rows_kept":8,"flags":["formulas_cached_only"]}
["委托单位","单位名称","装置代号","区域代号","委托编号","委托日期","检件名称","检测批号","检测时机","检件编号（管线号）","焊口编号","焊工号","检件规格","检件材质","比例（%）","焊接方法","工作量米","工作量道","级别","检测日期","检测温度","检测人","缺陷性质\n（若无为空）","缺陷定量\n（若无为空）","结果（合格/不合格）","结果单编号","结果单日期","报告编号","报告日期","工作量","工程进度款","检测方法（PT/RT/MT/UT/设备PT/设备RT/设备MT/设备TU/TOFD）"]
["山东齐鲁石化工程有限公司","中石化第十建设有限公司","装置名称","工区名称","SEI-1010-127901-PE-A01-PT-0001","2021-03-24","压力管道","/","打磨除锈后","105-VBW-55003","D1G","A0362","φ26.7*5.56","A106-Gr.B",{"v":1,"d":"100%"},"GTAW+SMAW",1,"口","Ⅰ","2021-03-24",23,"王亚军",null,null,"合格",null,null,"PT-GLRP-JIC-105-VBW-55003-001","2019-11-14"]
["山东齐鲁石化工程有限公司","中石化第十建设有限公司","管道安装工程","裂解炉区","SEI-1010-127901-PE-A01-PT-0001","2021-03-24","压力管道","/","打磨除锈后","105-VBW-55003","D2G","A0362","φ26.7*5.56","A106-Gr.B",{"v":1,"d":"100%"},"GTAW",1,"口","Ⅰ","2021-03-24",23,"王亚军",null,null,"合格",null,null,"PT-GLRP-JIC-105-VBW-55003-001","2019-11-14"]
["山东齐鲁石化工程有限公司","中石化第十建设有限公司","管道安装工程","裂解炉区","SEI-1010-127901-PE-A01-PT-0001","2021-03-24","压力管道","/","打磨除锈后","105-VBW-55003","S8","A0362","φ33.4*6.35","A106-Gr.B",{"v":1,"d":"100%"},"GTAW",1,"口","Ⅰ","2021-03-24",23,"王亚军",null,null,"合格",null,null,"PT-GLRP-JIC-105-VBW-55003-001","2019-11-14"]
["山东齐鲁石化工程有限公司","中石化第十建设有限公司","管道安装工程","裂解炉区","SEI-1010-127901-PE-A01-PT-0002","2021-03-24","压力管道","/","打磨除锈后","105-ZX-F005PT-05000A","S1","A0362","φ21.3*3.73","20#",{"v":0.2,"d":"20%"},"GTAW",1,"口","Ⅰ","2021-03-24",23,"王亚军",null,null,"合格",null,null,"PT-GLRP-JIC-105-ZX-F005PT-05000A-001","2019-11-14"]
["山东齐鲁石化工程有限公司","中石化第十建设有限公司","管道安装工程","裂解炉区","SEI-1010-127901-PE-A01-PT-0003","2021-03-24","压力管道","/","打磨除锈后","105-ZX-F005PT-05000B","S1","A0362","φ21.3*3.73","20#",{"v":0.2,"d":"20%"},"GTAW",1,"口","Ⅰ","2021-03-24",23,"王亚军",null,null,"合格",null,null,"PT-GLRP-JIC-105-ZX-F005PT-05000B-001","2019-11-14"]
["山东齐鲁石化工程有限公司","中石化第十建设有限公司","管道安装工程","裂解炉区","SEI-1010-127901-PE-A01-PT-0004","2021-03-24","压力管道","/","打磨除锈后","105-ZX-F005PT-05000C","S1","A0362","φ21.3*3.73","20#",{"v":0.2,"d":"20%"},"GTAW",1,"口","Ⅰ","2021-03-24",23,"王亚军",null,null,"合格",null,null,"PT-GLRP-JIC-105-ZX-F005PT-05000C-001","2019-11-14"]
["山东齐鲁石化工程有限公司","中石化第十建设有限公司","管道安装工程","裂解炉区","SEI-1010-127901-PE-A01-PT-0005","2021-03-24","压力管道","/","打磨除锈后","105-ZX-F005PT-05001","S1","A0362","φ21.3*3.73","20#",{"v":0.2,"d":"20%"},"GTAW",1,"口","Ⅰ","2021-03-24",23,"王亚军",null,null,"合格",null,null,"PT-GLRP-JIC-105-ZX-F005PT-05001-001","2019-11-14"]