## Sheet1
Month | JOB_NO | PROJECT_JOB_TYPE | BUDGET_ORG | Budget_CHK | ACTUAL | Commit_PO | Commit_SSR | Cost_To_CMPT

## Sheet4 (hidden)
Cost Overview for Projects
B.U. | Job | Project Title | Job Status | Lead By | P.M. | C.M. | Approval Date | Hiden Information | [17 empty] | Approved Budget 1 | Estimated Final Cost 5=2+3+4 | Devi.(%) (5-1)/1 | Actual 2 | Committed 3 |  | Cost to complete 4 | Devi.(%) _POPR | Devi.(%) _SSR | Internal Engineering Cost |  | Internal Const.Supervsn Cost |  | Wrong Booking Indicator
[8 empty] | M.C.Date | TCCC Date | Business Closure Date | Priority | WBS Account | Netowrk | Actual Cost Migrated? | Job No. | Original Budget | Budget Change | Final cost | Actual cost | Commitment | Rem.M.H (Eng) | Rem.M.H (Con.Sup) | Budget(used to calculate C2C) | Cost to complete | Saved Cost |  |  |  |  | PR/PO | SSR |  |  |  | Rem M.H. /RMB | Compl (%) | Rem M.H. /RMB | Compl (%) | Material | SSR
CBP/C | 15292 | Modification of the Furnace Burners | On Going | CTE/P | Ding Juntao | 0 | 2015-12-31 | 0 | 0 | 0 | N | ZNIC.011312 | NZNIC015292K |  | 15292 | 0 | 0 | 0 | 0 | 195339.88 | 90000 | 0 | 0 | -285339.88 | 0 | 0 | -90000 | #DIV/0! | 0 | 195339.88 | 0 | -285339.88 | #DIV/0! | #DIV/0! | 90000 | 0% | 0 | #DIV/0! | 0 | 0
CEP/L | 15278 | Upgrade the HIPS Palletizer | On Going | CTE/P | Zhou Yanduo | Wu Zefei | 2015-12-30 | 0 | 0 | 0 | N | ZNIC.011307 | NZNIC015278K |  | 15278 | 1826000 | 0 | 0 | 0 | 0 | 117000 | 97000 | 1826000 | 1612000 | 0 | 1826000 | 1612000 | -11.72% | 0 | 0 | 0 | 1612000 | #DIV/0! | #DIV/0! | 117000 | 0% | 97000 | 0% | 0 | 0
CTE | 15277 | Add New Road Lamps at 5# Gate and ChengPin Road | On Going | CTE/A | Bian Jiacai | Sun Zhongpin | 2015-12-22 | 0 | 0 | 0 | N | ZNIF.623100.15.01 | NZNIC015277K |  | 15277 | 538000 | 0 | 16500 | 14300 | 1110376.9 | 0 | 0 | 538000 | -586676.9 | 0 | 538000 | 538000 | 0% | 14300 | 1110376.9 | 0 | -586676.9 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CBP/U | 15267 | Add a Pressure Control valve on CR Line | On Going | CTE/P | Yu Xiya | Jiang Haijing | 2015-12-18 | 0 | 0 | 0 | N | ZNIF.623350.15.01 | NZNIC015267K |  | 15267 | 676000 | 0 | 0 | 0 | 1454957.27 | 90000 | 110000 | 676000 | -978957.27 | 0 | 676000 | 476000 | -29.59% | 0 | 1454957.27 | 0 | -978957.27 | #DIV/0! | #DIV/0! | 90000 | 0% | 110000 | 0% | 0 | 0
CBP/U | 15263 | Adding Monitoring System for YBS Utility | Completed | CTE/A | Hu Xiao | Sun Zhongpin | 2015-11-20 | 2015-12-31 | 0 | 0 | H | ZNIF.620051.15.01 | NZNIC015263K |  | 15263 | 478000 | 0 | 770390 | 0 | 746000 | 0 | 0 | 478000 | -479936.9 | 81646.9 | 478000 | 396353.1 | -17.08% | 0 | 746000 | 130290 | -479936.9 | -40.94% | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
COA/A | 15256 | Add One Common Spare Motor for GAA Molten Salt Pumps | On Going | CTA/L | Zhu Qiang | N/A | 2015-10-20 | 0 | 0 | 0 | N | ZNIC.010728 | NZNIC015256K |  | 15256 | 2750000 | 0 | 2750000 | 0 | 0 | 6000 | 0 | 2750000 | 2744000 | 0 | 2750000 | 2744000 | -0.2182% | 0 | 0 | 0 | 2744000 | #DIV/0! | #DIV/0! | 6000 | 0% | 0 | #DIV/0! | 0 | 0
COA/A | 15247 | B450/B550 MCC Modification | On Going | CTA/L | Yi Yongjun | Sun Zhongpin | 2015-10-08 | 0 | 0 | 0 | H | ZNIC.010582 | NZNIC015247K |  | 15247 | 3500000 | 0 | 4610377 | 0 | 120980 | 109450 | 177250 | 3500000 | 2565096.9 | 527223.1 | 3500000 | 2686076.9 | -23.25% | 0 | 120980 | 0 | 2565096.9 | -32.19% | #DIV/0! | 109450 | 17.08% | 177250 | 1.528% | 0 | 0
COA/E | 15246 | C7100,C77100,C77400 Raplace the Boken Trays | On Going | CTM/A | Ling Wenqing | Shi Jinsong | 2015-09-17 | 0 | 0 | 0 | N | ZNIC.010345 | NZNIC015246K |  | 15246 | 2687000 | 0 | 4141957 | 4675 | 0 | 0 | 0 | 2687000 | 2384625.01 | 297699.99 | 2687000 | 2389300.01 | -11.08% | 4675 | 0 | 0 | 2384625.01 | -14.88% | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
COO/A | 15245 | Install Filters on the Bottom Discharge Lines of C2300 and C2500 | On Going | CTE/P | Zhang Bianlin | Jiang Haijin | 2015-12-01 | 0 | 0 | 0 | N | ZNIC.011107 | NZNIC015245K |  | 15245 | 1252000 | 0 | 1998000 | 26282.42 | 15811.97 | 165600 | 130000 | 1252000 | 831728.56 | 82577.05 | 1252000 | 873822.95 | -30.21% | 26282.42 | 15811.97 | 0 | 831728.56 | -28.67% | #DIV/0! | 165600 | 2.588% | 130000 | 0% | 0 | 0
CEP/S | 15242 | Relocation the Cable of PS Plant | On Going | CTE/A | Bian Jiacai | Sun Zhongpin | 2015-11-26 | 0 | 0 | 0 | N | ZNIC.011082 | NZNIC015242K |  | 15242 | 3196000 | 0 | 3196000 | 0 | 1560000 | 326670 | 198000 | 3196000 | 1111330 | 0 | 3196000 | 2671330 | -16.42% | 0 | 1560000 | 0 | 1111330 | #DIV/0! | #DIV/0! | 326670 | 2.777% | 198000 | 0% | 0 | 0
CBP/B | 15198 | Install two CCTVs in BD Plant | On Going | CTE/A | Hu Xiao | Chen Gang | 2015-10-28 | 0 | 0 | 0 | N | ZNIF.104500.15.03 | NZNIC015198K |  | 15198 | 217000 | 0 | 337980 | 82419.39 | 0 | 0 | 0 | 217000 | 132210.63 | 2369.98 | 217000 | 214630.02 | -1.092% | 82419.39 | 0 | 0 | 132210.63 | -1.936% | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
COO/C | 15197 | Revamping of C1 Flare KO Drums | On Going | CTE/P | Li Shouqing | Jiang Haijin | 2015-12-29 | 0 | 0 | 0 | N | ZNIC.011291 | NZNIC015197K |  | 15197 | 1340000 | 0 | 0 | 0 | 4201.71 | 231550 | 268125 | 1340000 | 836123.29 | 0 | 1340000 | 840325 | -37.29% | 0 | 4201.71 | 0 | 836123.29 | #DIV/0! | #DIV/0! | 231550 | 0% | 268125 | 0% | 0 | 0
CBL/P | 15180 | Air Conditioning Replacement for Jetty1/2/3 Operation Room | Completed | CTE/C | Wang Wei | Wang Wei | 2015-09-24 | 2015-11-26 | 0 | 0 | N | ZNIF.604220.15.01 | NZNIC015180K |  | 15180 | 94000 | 0 | 94000 | 127976.1 | 55137.76 | -4675 | 0 | 94000 | -89398.32 | 284.46 | 94000 | 93715.54 | -0.3026% | 127976.1 | 55137.76 | 0 | -89398.32 | #DIV/0! | -4.31% | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CTM | 15176 | Add Card Reader at D700 Central Workshop | On Going | CTE/A | Xu Zheng | 0 | 2015-08-31 | 0 | 0 | 0 | N | ZNIF.642320.15.03 | NZNIC015176K |  | 15176 | 0 | 0 | 42094 | 46928.77 | 0 | 14090 | 39000 | 0 | -99651.94 | -366.83 | 0 | -52723.17 | #DIV/0! | 46928.77 | 0 | 0 | -99651.94 | 1.112% | #DIV/0! | 14090 | 49.68% | 39000 | 0% | 0 | 0
CEP/S | 15168 | PS Chilling Unit Replacement | On Going | CTE/P | Gu Jingfeng | Wu Zefei | 2015-11-20 | 0 | 0 | 0 | N | ZNIC.011038 | NZNIC015168K |  | 15168 | 2910000 | 0 | 4470000 | 21726 | 11218.88 | 270050 | 245575 | 2910000 | 2361430.12 | 0 | 2910000 | 2394375 | -17.72% | 21726 | 11218.88 | 0 | 2361430.12 | #DIV/0! | #DIV/0! | 270050 | 6.298% | 245575 | 0% | 0 | 0
CBP/C | 15167 | Add Adjusters for One of the Furnaces Bottom Air Registers | On Going | CTE/P | Zhou Yanduo | Ling Taizhong | 2015-12-30 | 0 | 0 | 0 | N | ZNIC.011308 | NZNIC015167K |  | 15167 | 1490000 | 0 | 0 | 58781.93 | 5420 | 162525 | 145200 | 1490000 | 1118073.07 | 0 | 1490000 | 1182275 | -20.65% | 58781.93 | 5420 | 0 | 1118073.07 | #DIV/0! | #DIV/0! | 162525 | 0% | 145200 | 0% | 0 | 0
CBP/M | 15149 | Steel Structure Extension of Gas Cylinder Room of CTS/L | On Going | CTE/C | Wang Shicheng | Zhang Zhihe | 2015-09-30 | 0 | 0 | 0 | N | ZNIF.660300.15.01 | NZNIC015149K |  | 15149 | 264000 | 0 | 377771 | 11000 | 140000 | -69360 | -11000 | 264000 | -6932.83 | 1104.83 | 264000 | 262895.17 | -0.4185% | 11000 | 140000 | 118828 | -6932.83 | -4.967% | -29.59% | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 1
CBP/C | 15143 | Add Combustible Gas Detector in BCC Cylinder Room | On Going | CTE/A | Gong Feibao | Li Hong | 2015-10-30 | 0 | 0 | 0 | N | ZNIF.104100.15.06 | NZNIC015143K |  | 15143 | 70000 | 0 | 74202 | 186315.85 | 53878.98 | 7400 | 19000 | 70000 | -197178.83 | 584 | 70000 | 43016 | -38.55% | 186315.85 | 53878.98 | 0 | -197178.83 | -10.62% | #DIV/0! | 7400 | 47.14% | 19000 | 0% | 0 | 0
CBP/B | 15124 | Add Pump and Flow Control Valve on the Line for Sending Dimer to C-250 | On Going | CTE/P | Chen Chen | Ling Taizhong | 2015-07-27 | 0 | 0 | 0 | T | ZNIF.104500.15.01 | NZNIC015124K |  | 15124 | 730000 | 0 | 785138 | 36705 | 25936.29 | 96600 | 142450 | 730000 | 385728.61 | 42580.1 | 730000 | 448369.9 | -38.58% | 36705 | 25936.29 | 0 | 385728.61 | -24.21% | #DIV/0! | 96600 | 42.16% | 142450 | 7.5% | 0 | 0
CTM | 15122 | D700 Garbage Disposal Field Modification | On Going | CTE/C | Xia Qun | Xu Zhaofeng | 2015-07-16 | 0 | 0 | 0 | N | ZNIF.642320.15.02 | NZNIC015122K |  | 15122 | 369430 | 0 | 607585 | 25300 | 277846.76 | 37355 | 42100 | 369430 | -254390.99 | 164.23 | 369430 | 289810.77 | -21.55% | 25300 | 277846.76 | 241055 | -254390.99 | #DIV/0! | -8.019% | 37355 | 52.11% | 42100 | 19.04% | 0 | 1
CBP/C | 15117 | Add the Differential Pressure Signal of the Instrument Air Filter in DCS System | On Going | CTE/P | Zhang Fanwen | Li Hong | 2015-09-10 | 0 | 0 | 0 | N | ZNIF.104100.15.04 | NZNIC015117K |  | 15117 | 98000 | 0 | 109219 | 27300 | 269230.77 | -20140 | -1100 | 98000 | -213311.89 | 14781.12 | 98000 | 83218.88 | -15.08% | 27300 | 269230.77 | 0 | -213311.89 | -56.85% | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CEP/E | 15116 | Set a Waste Storage Area beside Tank Farm | On Going | CTE/C | Yan Jun | Xu Zhaofeng | 2015-08-20 | 0 | 0 | 0 | H | ZNIF.105600.15.01 | NZNIC015116K |  | 15116 | 382000 | 0 | 475340 | 54160 | 2751751.23 | 63030 | 98900 | 382000 | -2670277.27 | -3483.96 | 382000 | 223553.96 | -41.48% | 54160 | 2751751.23 | 87920 | -2670277.27 | 6.873% | #DIV/0! | 63030 | 30.74% | 98900 | 1.1% | 0 | 0
CBL/P | 15112 | Add Emergency Storage Area for Jettys in CLTF Reserved Land | On Going | CTE/P | Yu Yi | Guo Yibing | 2015-10-28 | 0 | 0 | 0 | N | ZNIF.604110.15.01 | NZNIC015112K |  | 15112 | 970000 | 0 | 1584746 | 239017.94 | 1924799.22 | 10805 | 47000 | 970000 | -1735496.16 | 9128 | 970000 | 903067 | -6.9% | 239017.94 | 1924799.22 | 474746 | -1735496.16 | -6.52% | #DIV/0! | 10805 | 56.78% | 47000 | 0% | 0 | 0
CTM | 15102 | Cleaning Room Renovation Project of Central Workshop | On Going | CTM/W | Zhai Chunrong | Lei Fucun | 2015-07-16 | 0 | 0 | 0 | N | ZNIF.642320.15.01 | NZNIC015102K |  | 15102 | 958000 | 0 | 1566340 | 852242.9 | 41000 | -11457.15 | 44000 | 958000 | -608712.17 | 55008.77 | 958000 | 858991.23 | -10.33% | 852242.9 | 41000 | 574460.5 | -608712.17 | -37.36% | -14.53% | 0 | 106.7% | 44000 | 0% | 0 | 1
CBP/M | 15097 | Improve Operation Method for Compound TBC | On Going | CTE/P | Wang Can | Ling Taizhong | 2015-12-23 | 0 | 0 | 0 | N | ZNIF.104400.15.01 | NZNIC015097K |  | 15097 | 598000 | 0 | 0 | 30380 | 587777.78 | 183000 | 142000 | 598000 | -345157.78 | 0 | 598000 | 273000 | -54.35% | 30380 | 587777.78 | 0 | -345157.78 | #DIV/0! | #DIV/0! | 183000 | 0% | 142000 | 0% | 0 | 0
CBP/C | 15091 | Add a New Solid Waste Storage Area | Canceled | CTE/C | Wang Shicheng | Zhang Zhihe | 2015-12-07 | 0 | 0 | 0 | N | ZNIF.104100.15.08 | NZNIC015091K |  | 15091 | 257000 | 0 | 0 | 183454.06 | 0 | 47000 | 56000 | 257000 | -29454.06 | 0 | 257000 | 154000 | -40.08% | 183454.06 | 0 | 0 | -29454.06 | #DIV/0! | #DIV/0! | 47000 | 0% | 56000 | 0% | 0 | 0
CBP/C | 15089 | Modify Lubrication oil Room and Spare Parts Stroge Room at West of Control Building | On Going | CTE/C | Wang Shicheng | Zhang Zhihe | 2015-12-07 | 0 | 0 | 0 | N | ZNIF.104100.15.07 | NZNIC015089K |  | 15089 | 752000 | 0 | 0 | 5306.45 | 23852.16 | 122000 | 94000 | 752000 | 506841.39 | 0 | 752000 | 536000 | -28.72% | 5306.45 | 23852.16 | 0 | 506841.39 | #DIV/0! | #DIV/0! | 122000 | 0% | 94000 | 0% | 0 | 0
CTM | 15079 | Fire Alarm System Modification for #5 Warehouse in East Laydown | On Going | CTE/A | Bian Jiacai | Sun Zhongpin | 2015-07-24 | 0 | 0 | 0 | N | ZNIF.641330.15.01 | NZNIC015079K |  | 15079 | 220000 | 0 | 262386 | 14640 | 810000 | -37045 | -2475 | 220000 | -682344.53 | 8654.53 | 220000 | 211345.47 | -3.934% | 14640 | 810000 | 69050 | -682344.53 | -22.19% | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CEP/P | 15071 | Build a Spare Part&Tool Warehouse | On Going | CTE/C | Gao Feng | Xia Weiguang | 2015-10-21 | 0 | 0 | 0 | H | ZNIC.010748 | NZNIC015071K |  | 15071 | 1222000 | 0 | 1499847 | 102162.89 | 787059.83 | 119350 | 129250 | 1222000 | -479485.72 | 200 | 1222000 | 973200 | -20.36% | 102162.89 | 787059.83 | 563463 | -479485.72 | -20% | #DIV/0! | 119350 | 36.55% | 129250 | 0% | 0 | 0
CBL/P | 15066 | Add On-line Water Analyzer on the NAP Unloading Piping of Jetty 4# | On Going | CTE/A | Xu Ge | Wang Xinwu | 2015-08-31 | 0 | 0 | 0 | N | ZNIF.651130.15.01 | NZNIC015066K |  | 15066 | 547000 | 0 | 816231 | 44429.04 | 140597.78 | 39800 | 34500 | 547000 | 296712.98 | -15039.8 | 547000 | 487739.8 | -10.83% | 44429.04 | 140597.78 | 6000 | 296712.98 | 4.966% | #DIV/0! | 39800 | 32.54% | 34500 | 32.35% | 0 | 0
CTS | 15061 | BCC Lab Modification | On Going | CTE/C | Yu Yi | Jiang Yunning | 2015-06-11 | 0 | 0 | 0 | N | ZNIC.009551 | NZNIC015061K |  | 15061 | 3490000 | 290000 | 6411751 | 928395.84 | 11111.11 | 75640 | 69300 | 3490000 | 2515801.69 | -292248.64 | 3780000 | 3637308.64 | -3.775% | 928395.84 | 11111.11 | 182000 | 2515801.69 | 10.03% | #DIV/0! | 75640 | 32.25% | 69300 | 26.74% | 0 | 1
C | 15051 | Set Up Intranet Portal System | On Going | CGA/I | Tao Yang | Tao Yang | 2015-03-18 | 0 | 0 | 0 | N | ZNIT.001180 | NZNIC015051K |  | 15051 | 2735000 | 0 | 4659799 | 0 | 4542735.05 | 0 | 0 | 2735000 | -1807735.05 | 0 | 2735000 | 2735000 | 0% | 0 | 4542735.05 | 0 | -1807735.05 | 0% | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CBP/P | 15047 | Change New CEMS | On Going | CTA/S | Tang Yiqun | Tang Yiqun | 2015-03-10 | 0 | 0 | 0 | N | ZNIC.008734 | NZNIC015047K |  | 15047 | 1203000 | 0 | 1344000 | 464825.16 | 0 | 5500 | 0 | 1203000 | 426442.63 | 206232.21 | 1203000 | 991267.79 | -17.6% | 464825.16 | 0 | 100000 | 426442.63 | -16.65% | -32.17% | 5500 | 0% | 0 | #DIV/0! | 0 | 0
CBP/C | 15042 | Add On-line Analyzer on the Outlet of the Z-908 | On Going | CTE/A | Gong Feibao | Li Hong | 2015-10-21 | 0 | 0 | 0 | H | ZNIC.010800 | NZNIC015042K |  | 15042 | 1145000 | 0 | 1732778 | 6520 | 242000 | 148435 | 105300 | 1145000 | 522104 | 120641 | 1145000 | 770624 | -32.7% | 6520 | 242000 | 0 | 522104 | -19.92% | #DIV/0! | 148435 | 27.19% | 105300 | 14.04% | 0 | 0
CBP/C | 15036 | Expand the Capacity of the Suspect Condensate Vent Condenser 390-E-920 | Completed | CTE/P | Ding Juntao | Tong Shaojian | 2015-05-11 | 2015-10-16 | 0 | 0 | H | ZNIF.104100.15.02 | NZNIC015036K |  | 15036 | 398000 | 0 | 398000 | 38205 | 227706.96 | 57450 | 28000 | 398000 | 12691.77 | 33946.27 | 398000 | 278603.73 | -30% | 38205 | 227706.96 | 0 | 12691.77 | -22.32% | -7.112% | 57450 | 57.76% | 28000 | 0% | 0 | 0
CBP/C | 15034 | Add Pressure&Temperature Signal DCS System for Three Drums at AEU Section | On Going | CTE/A | Gong Feibao | Li Hong | 2015-09-18 | 0 | 0 | 0 | N | ZNIF.104100.15.05 | NZNIC015034K |  | 15034 | 170000 | 0 | 193852 | 161613.1 | 82138.68 | 0 | -550 | 170000 | -80263.18 | 6511.4 | 170000 | 163488.6 | -3.83% | 161613.1 | 82138.68 | 0 | -80263.18 | -21.45% | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CEP/P | 15028 | Upgrade 4 sets PO Cupboard Freezer | On Going | CTE/P | Ding Juntao | Wang Yuncai | 2015-10-19 | 0 | 0 | 0 | T | ZNIC.010799 | NZNIC015028K |  | 15028 | 1319000 | 0 | 2129000 | 1000127.52 | 5128.21 | 122310 | 50050 | 1319000 | 119898.43 | 21485.84 | 1319000 | 1125154.16 | -14.7% | 1000127.52 | 5128.21 | 0 | 119898.43 | -2.653% | #DIV/0! | 122310 | 14.47% | 50050 | 8.081% | 0 | 0
CEP/S | 15026 | PS Positive Draft of Control Building Modification | On Going | CTE/C | Gao Feng | Wang Wei | 2015-07-09 | 0 | 0 | 0 | H | ZNIC.009794 | NZNIC015026K |  | 15026 | 1256000 | 0 | 2062440 | 53990 | 1072456.67 | 73910.85 | 53350 | 1256000 | -65629.78 | -12216.58 | 1256000 | 1140955.73 | -9.16% | 53990 | 1072456.67 | 80138.84 | -65629.78 | 1.333% | -5.66% | 73910.85 | 52.68% | 53350 | 19.17% | 0 | 1
COA/S | 15024 | SAP Steam System Energy Saving Modification | On Going | CTE/P | Xu Jin | Wang Yuncai | 2015-09-18 | 0 | 0 | 0 | N | ZNIC.010440 | NZNIC015024K |  | 15024 | 1419000 | 0 | 1559598 | 1716239.32 | 0 | 132100 | 196900 | 1419000 | -656256.24 | 27516.92 | 1419000 | 1062483.08 | -25.12% | 1716239.32 | 0 | 2500 | -656256.24 | -15.46% | #DIV/0! | 132100 | 12.98% | 196900 | 5.789% | 0 | 0
CEP/E | 15022 | Revamp HVAC System in EOEG Control Building | Completed | CTE/C | Gao Feng | Wang Wei | 2015-05-07 | 2015-12-04 | 0 | 0 | H | ZNIC.009264 | NZNIC015022K |  | 15022 | 1391000 | 0 | 1473957 | 2061289.79 | 0 | 56686.99 | 4950 | 1391000 | -577421.19 | -164661.59 | 1391000 | 1494024.6 | 7.407% | 2061289.79 | 0 | 10156 | -577421.19 | 19.39% | 10.52% | 56686.99 | 60.96% | 4950 | 91.96% | 0 | 4
CTS | 15016 | Environmental Monitoring Car | On Going | CTS/E | Fan Chenxi | Fan Chenxi | 2015-01-13 | 0 | 0 | 0 | N | ZNIC.008204 | NZNIC015016K |  | 15016 | 4000000 | 0 | 4542735 | 3215625.56 | 22568213.5 | 0 | 0 | 4000000 | -20968839.05 | -815000.01 | 4000000 | 4815000.01 | 20.38% | 3215625.56 | 22568213.5 | 0 | -20968839.05 | 18.11% | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CEP/L | 15014 | PS A915 Emergency Lighting and Fire Alarm System Modification | Completed | CTE/A | Xu Zheng | Zhang Pu | 2015-03-04 | 2015-09-22 | 0 | 0 | N | ZNIF.175410.15.01 | NZNIC015014K |  | 15014 | 434000 | 0 | 474825 | 738775.88 | 178940 | 12220 | 30050 | 434000 | 0 | -31728.64 | 434000 | 927715.88 | 113.8% | 738775.88 | 178940 | 10000 | 0 | 28.52% | -2.225% | 12220 | 84.33% | 30050 | 61.96% | 0 | 0
CTM | 15011 | Modification for Main Door of Spare Parts Warehouse | On Going | CTE/C | Yu Yi | Xu Zhaofeng | 2015-07-31 | 0 | 0 | 0 | N | ZNIF.641330.15.02 | NZNIC015011K |  | 15011 | 384000 | 0 | 626000 | 0 | 0 | 46480 | 43000 | 384000 | 306520 | -12000 | 384000 | 306520 | -20.18% | 0 | 0 | 0 | 306520 | 5.217% | #DIV/0! | 46480 | 12.3% | 43000 | 0% | 0 | 0
COA/E | 15010 | Replace the Material of P7120A/B by PFA | On Going | CTE/P | Xu Jin | Wu Zefei | 2015-08-10 | 0 | 0 | 0 | T | ZNIF.106200.15.01 | NZNIC015010K |  | 15010 | 495000 | 0 | 722707 | 0 | 0 | 51995 | 54450 | 495000 | 374972.14 | 13582.86 | 495000 | 374972.14 | -24.25% | 0 | 0 | 0 | 374972.14 | -4.851% | #DIV/0! | 51995 | 47.48% | 54450 | 1% | 0 | 0
CEP/E | 15009 | Modify Suction Side of P4330 | On Going | CTE/P | Gu Jingfeng | Wu Zefei | 2015-05-15 | 0 | 0 | 0 | T | ZNIF.105700.15.01 | NZNIC015009K |  | 15009 | 590000 | 0 | 672139 | 0 | 0 | 47245 | 75600 | 590000 | 410021.97 | 57133.03 | 590000 | 410021.97 | -30.5% | 0 | 0 | 0 | 410021.97 | -27.9% | #DIV/0! | 47245 | 70.47% | 75600 | 5.5% | 0 | 0
COA/A | 15004 | Revamp HVAC System in B550 Control Building | Completed | CTE/C | Gao Feng | Wang Wei | 2015-05-07 | 2015-09-06 | 0 | 0 | H | ZNIC.009265 | NZNIC015004K |  | 15004 | 1564000 | 0 | 1577128 | 437641.21 | 0 | 70660 | 33550 | 1564000 | 0 | 223669.2 | 1564000 | 445641.21 | -71.51% | 437641.21 | 0 | 8000 | 0 | -21.91% | -4.829% | 70660 | 56.6% | 33550 | 52.34% | 0 | 1
CBP/C | 14313 | Replace Existing Electrical Heater H-520 | On Going | CTE/A | Hu Xiao | Chen Gang | 2015-05-15 | 0 | 0 | 0 | N | ZNIC.009347 | NZNIC014313K |  | 14313 | 1885000 | 0 | 2957457 | 2330341.89 | 0 | 59860 | 63800 | 1885000 | -620049.08 | 51047.19 | 1885000 | 1710292.81 | -9.268% | 2330341.89 | 0 | 0 | -620049.08 | -4.771% | #DIV/0! | 59860 | 49.38% | 63800 | 0% | 0 | 0
CBP/M | 14312 | Replace Exchanger E2320 of EB/SM | Completed | CTM/M | Chu Chao | Chu Chao | 2014-12-24 | 2015-05-30 | 0 | 0 | T_2015 | ZNIC.008125 | NZNIC014312K |  | 14312 | 2160000 | 0 | 2160000 | 50805.16 | 0 | 13750 | 0 | 2160000 | 0 | 0 | 2160000 | 50805.16 | -97.65% | 50805.16 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 13750 | 0% | 0 | #DIV/0! | 0 | 0
CEP/E | 14311 | Change New C2450/CX2450/E1250A/E1250B/E1252 | Completed | CTM/E | Wang Zhigao | Wang Zhigao | 2014-12-24 | 2015-05-04 | 0 | 0 | T_2015 | ZNIC.008124 | NZNIC014311K |  | 14311 | 1675000 | 487000 | 2061290 | 316000 | 0 | 8000 | 8000 | 1675000 | 0 | 0 | 2162000 | 316000 | -85.38% | 316000 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 8000 | 0% | 8000 | 0% | 0 | 0
COA/S | 14309 | Add Extrusion Step for New Product AGM7 | On Going | CTE/P | Zhu Jianxin | Cao Yongbin | 2015-04-02 | 0 | 0 | 0 | H | ZNIC.008120 | NZNIC014309K |  | 14309 | 27782000 | 0 | 51729014 | 1034115.29 | 9200 | 144197.92 | 1280575 | 27782000 | 21740300.81 | 1880610.98 | 27782000 | 24476616.1 | -11.9% | 1034115.29 | 9200 | 1693000 | 21740300.81 | -7.533% | -17.61% | 144197.92 | 86.9% | 1280575 | 8.937% | 0 | 3
CBP/M | 14308 | Modification of EB/SM Cooling Water Pumps | On Going | CTE/P | Wang Lifen | Ling Taizhong | 2015-04-13 | 0 | 0 | 0 | N | ZNIC.009023 | NZNIC014308K |  | 14308 | 1357000 | 0 | 1673033 | 264528.16 | 835675.21 | -1025 | 57725 | 1357000 | -118350.31 | 79388.94 | 1357000 | 1219886.06 | -10.1% | 264528.16 | 835675.21 | 238033 | -118350.31 | -7.535% | #DIV/0! | 0 | 100.8% | 57725 | 57.24% | 0 | 2
CBP/M | 14307 | Replacement of F2404 | Completed | CTM/M | Chu Chao | Chu Chao | 2014-12-19 | 2015-05-30 | 0 | 0 | T_2015 | ZNIF.104400.14.04 | NZNIC014307K |  | 14307 | 192000 | 0 | 192000 | 23850.88 | 0 | 8000 | 0 | 192000 | 0 | 0 | 192000 | 23850.88 | -87.58% | 23850.88 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 8000 | 0% | 0 | #DIV/0! | 0 | 0
CBP/M | 14306 | Replacement of F2406 | Completed | CTM/M | Chu Chao | Chu Chao | 2014-12-19 | 2015-05-01 | 0 | 0 | T_2015 | ZNIF.104400.14.03 | NZNIC014306K |  | 14306 | 210000 | 0 | 210000 | 1400892.44 | 215773.95 | 8000 | 0 | 210000 | 0 | 0 | 210000 | 1616666.39 | 669.8% | 1400892.44 | 215773.95 | 0 | 0 | #DIV/0! | #DIV/0! | 8000 | 0% | 0 | #DIV/0! | 0 | 0
CBP/M | 14305 | Replacement of E1203 | Completed | CTM/M | Chu Chao | Chu Chao | 2014-12-18 | 2015-05-31 | 0 | 0 | T_2015 | ZNIF.104400.14.02 | NZNIC014305K |  | 14305 | 224000 | 0 | 224000 | 13055 | 31203.68 | 8000 | 0 | 224000 | 0 | 0 | 224000 | 44258.68 | -80.24% | 13055 | 31203.68 | 0 | 0 | #DIV/0! | #DIV/0! | 8000 | 0% | 0 | #DIV/0! | 0 | 0
COA/A | 14296 | Install Filters at Outlet of P9326/P9526 | Completed | CTE/P | Xu Jin | Wu Zefei | 2015-04-02 | 2015-12-04 | 0 | 0 | N | ZNIF.106600.15.01 | NZNIC014296K |  | 14296 | 830000 | 0 | 955432 | 2906231.59 | 0 | 25465 | -20175 | 830000 | -2454155.23 | 255348.64 | 830000 | 549186.36 | -33.83% | 2906231.59 | 0 | 97110 | -2454155.23 | -45.68% | -15.6% | 25465 | 83.25% | 0 | 130.1% | 0 | 0
CBP/M | 14288 | T2401 Replace Structure Packing of EB/SM | Completed | CTM/M | Chu Chao | Chu Chao | 2014-12-01 | 2015-05-31 | 0 | 0 | T_2015 | ZNIC.007947 | NZNIC014288K |  | 14288 | 2645000 | 0 | 2645000 | 839245.53 | 649.57 | 13750 | 27500 | 2645000 | 0 | 177495.99 | 2645000 | 839895.1 | -68.25% | 839245.53 | 649.57 | 0 | 0 | -6.112% | #DIV/0! | 13750 | 0% | 27500 | 0% | 0 | 0
CEP/P | 14287 | Add a Differential Pressure Transmitter in Control Room | Completed | CTE/A | Xu Ge | Li Xueyong | 2015-01-07 | 2015-06-19 | 0 | 0 | N | ZNIF.678152.15.01 | NZNIC014287K |  | 14287 | 104000 | 0 | 105300 | 0 | 80000 | 2471.78 | 4300 | 104000 | 0 | 2327.87 | 104000 | 80000 | -23.08% | 0 | 80000 | 0 | 0 | -14.29% | -24.26% | 2471.78 | 92.28% | 4300 | 81.3% | 0 | 1
CBP/M | 14286 | Change Gas Chromatograph A24201 to New Type | On Going | CTA/S | Li Huaxin | Li Huaxin | 2014-11-27 | 0 | 0 | 0 | N | ZNIF.104400.14.01 | NZNIC014286K |  | 14286 | 480000 | 0 | 480000 | 0 | 0 | 2000 | 4000 | 480000 | 373720 | 100280 | 480000 | 373720 | -22.14% | 0 | 0 | 0 | 373720 | -21.34% | #DIV/0! | 2000 | 0% | 4000 | 0% | 0 | 0
CTS/U | 14275 | Add Flowmeter on Main Pipeline for HPNG | Completed | CTE/A | Wang Zhen | Wang Xinwu | 2014-12-24 | 2015-12-14 | 0 | 0 | T_2015 | ZNIC.008123 | NZNIC014275K |  | 14275 | 1151000 | 0 | 1141315 | 835841.68 | 23515.86 | -41380 | -137100.49 | 1151000 | 178983.67 | 32658.79 | 1151000 | 1118341.21 | -2.837% | 835841.68 | 23515.86 | 80000 | 178983.67 | -4.335% | -0.6041% | 0 | 146.5% | 0 | 247.4% | 0 | 3
CBP/C | 14262 | Revamp HVAC System in BCC Control Building | Completed | CTE/C | Gao Feng | Wang Wei | 2015-05-07 | 2015-09-29 | 0 | 0 | H | ZNIC.009263 | NZNIC014262K |  | 14262 | 1216000 | 0 | 2093170 | 349453.42 | 0 | -91445 | 35750 | 1216000 | 0 | -39482.04 | 1216000 | 388648.42 | -68.04% | 349453.42 | 0 | 39195 | 0 | 3.654% | -6.237% | 0 | 413.7% | 35750 | 29.35% | 0 | 0
CGA | 14255 | Add a Pair of Card Reader on the West Side Door of Visitor Center for Personnel Access Control | Completed | CTA/S | Dai Xiaolong | Qiu Wei | 2014-10-29 | 2015-04-30 | 0 | 0 | N | ZNIF.632000.14.01 | NZNIC014255K |  | 14255 | 35000 | 0 | 35000 | 16500 | 0 | -7900 | 4899.25 | 35000 | 0 | 4790.92 | 35000 | 16500 | -52.86% | 16500 | 0 | 0 | 0 | 0.5001% | -40.56% | 0 | 495% | 4899.25 | 18.35% | 0 | 1
COO/C | 14252 | Supply DMA from C1 Plant to BSNJ | Completed | CTE/P | Sun Duoxun/Liu Xiaoli | Xu Yefeng | 2014-12-22 | 2015-08-30 | 0 | 0 | T_2015 | ZNIC.008115 | NZNIC014252K |  | 14252 | 1767000 | 0 | 2019104 | 309794.94 | 1500 | -16820 | -174931.56 | 1767000 | 0 | 328005.39 | 1767000 | 321294.94 | -81.82% | 309794.94 | 1500 | 10000 | 0 | -23.62% | -22.42% | 0 | 108.3% | 0 | 186.6% | 0 | 1
CBL/O | 14251 | Build a Operation Rest Room for ACN Loading Station | On Going | CTE/C | Yu Yi | Xu Zhaofeng | 2015-08-06 | 0 | 0 | 0 | N | ZNIF.412790.15.01 | NZNIC014251K |  | 14251 | 338000 | 0 | 395234 | 865494.28 | 0 | 47195 | 44000 | 338000 | -639874.3 | -4844.98 | 338000 | 251649.98 | -25.55% | 865494.28 | 0 | 26030 | -639874.3 | 18.25% | #DIV/0! | 47195 | 25.09% | 44000 | 0% | 0 | 0
CBP/C | 14243 | Add a C5 Raffinate Pipe from YUANGANG Company to C5 Hydrogenation Reactor | Completed | CTE/P | Cao Lin | Ling Taizhong | 2015-03-26 | 2015-09-06 | 0 | 0 | N | ZNIC.008902 | NZNIC014243K |  | 14243 | 3720000 | 0 | 3777568 | 1065641.62 | 17.09 | 7345 | -56535.9 | 3720000 | 0 | 1988.58 | 3720000 | 1123226.71 | -69.81% | 1065641.62 | 17.09 | 57568 | 0 | 1.562% | -14.35% | 7345 | 97.44% | 0 | 116.7% | 0 | 0
COA/L | 14240 | Recover the BA Railway Loading Station | Completed | CTE/P | Zhu Jianxin | Wu Zefei | 2014-12-22 | 2015-11-06 | 0 | 0 | H | ZNIC.008121 | NZNIC014240K |  | 14240 | 1907000 | 0 | 2176992 | 782229.91 | 8800 | 50540 | 45655.5 | 1907000 | 822860.85 | -8428.26 | 1907000 | 1819232.76 | -4.602% | 782229.91 | 8800 | 205342 | 822860.85 | 5.375% | -25.58% | 50540 | 84.11% | 45655.5 | 77.17% | 0 | 0
CEP/E | 14237 | LP Steam Rational Distribution and Utilization | On Going | CTE/P | Gu Jingfeng | Wu Zefei | 2015-11-20 | 0 | 0 | 0 | N | ZNIC.011039 | NZNIC014237K |  | 14237 | 1763000 | 0 | 1843000 | 157996.89 | 794908.22 | 258200 | 303050 | 1763000 | 248844.89 | 0 | 1763000 | 1201750 | -31.83% | 157996.89 | 794908.22 | 0 | 248844.89 | #DIV/0! | #DIV/0! | 258200 | 0.8449% | 303050 | 2.131% | 0 | 0
CEP/S | 14235 | Add Safety Facilities for PS Burner Unit | On Going | CTE/A | Xiao Lixuan | Li Xueyong | 2015-11-18 | 0 | 0 | 0 | N | ZNIF.105400.15.02 | NZNIC014235K |  | 14235 | 439000 | 0 | 439000 | 102570.04 | 301.3 | 87000 | 49100 | 439000 | 200028.66 | 0 | 439000 | 302900 | -31% | 102570.04 | 301.3 | 0 | 200028.66 | #DIV/0! | #DIV/0! | 87000 | 0% | 49100 | 16.78% | 0 | 0
CAP/E | 14234 | Add Anti-backflow facilities at LP Steam Header of MA/BA Plant | Completed | CTE/P | Zhu Jianxin | Wu Zefei | 2014-12-10 | 2015-04-30 | 0 | 0 | T_2015 | ZNIF.106300.14.01 | NZNIC014234K |  | 14234 | 893000 | 0 | 918516 | 253601.42 | 24000 | -31445 | -12263 | 893000 | 0 | 298340.62 | 893000 | 277601.42 | -68.91% | 253601.42 | 24000 | 0 | 0 | -36.64% | -18.89% | 0 | 120% | 0 | 110.9% | 0 | 0
COA/E | 14232 | Change the Breath Valve and Add a PSV for T9668 | Completed | CTE/P | Xu Jin | Wang Yuncai | 2014-11-20 | 2015-08-19 | 0 | 0 | N | ZNIF.106700.14.01 | NZNIC014232K |  | 14232 | 320000 | 0 | 349453 | 153369.21 | 0 | -63340 | -38225 | 320000 | 0 | -16307.6 | 320000 | 153369.21 | -52.07% | 153369.21 | 0 | 0 | 0 | 10.93% | -10.8% | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CAP/L | 14230 | Add a Shed for A455 Truck Parking Lot | On Going | CTE/C | Yu Yi | Lu Jie | 2015-09-09 | 0 | 0 | 0 | N | ZNIC.010285 | NZNIC014230K |  | 14230 | 1410000 | 0 | 1524250 | 0 | 152807.8 | 64900 | 71500 | 1410000 | 776006.19 | 226440.01 | 1410000 | 1047159.99 | -25.73% | 0 | 152807.8 | 118346 | 776006.19 | -47.18% | #DIV/0! | 64900 | 24.12% | 71500 | 27.78% | 0 | 2
CEP/L | 14227 | Rebuild the Existing Holding Device in PS Packing | Completed | CTE/P | Ding Juntao | Wang Yuncai | 2014-12-04 | 2015-06-29 | 0 | 0 | N | ZNIF.175410.14.01 | NZNIC014227K |  | 14227 | 350000 | 0 | 354290 | 4854302.86 | 699145.51 | -4602.98 | 8150 | 350000 | 0 | -20166.78 | 350000 | 5555048.37 | 1487% | 4854302.86 | 699145.51 | 1600 | 0 | 11.96% | -23.55% | 0 | 106.1% | 8150 | 81.89% | 0 | 2
CBL/O | 14226 | Add a Unloading System for PALD in B305 Loading Station | Completed | CTE/P | Yu Xiya | Jiang Haijin | 2014-12-03 | 2015-07-22 | 0 | 0 | T_2015 | ZNIC.007948 | NZNIC014226K |  | 14226 | 1270000 | 0 | 1280313 | 159712.92 | 0 | 52634 | -36350.12 | 1270000 | 0 | 135139 | 1270000 | 167625.92 | -86.8% | 159712.92 | 0 | 7913 | 0 | -17.7% | -25.23% | 52634 | 76.8% | 0 | 121.5% | 0 | 1
CBP/S | 14222 | Add H2 Pipeline to BSNJ from Syngas Plant | Completed | CTE/P | Cao Lin | Ling Taizhong | 2015-01-07 | 2015-09-30 | 0 | 0 | N | ZNIC.008171 | NZNIC014222K |  | 14222 | 1130000 | 559000 | 2285508 | 0 | 2293536.92 | -95320 | -76293.77 | 1689000 | 0 | 69393.75 | 1689000 | 2318536.92 | 37.27% | 0 | 2293536.92 | 25000 | 0 | -1.054% | -6.411% | 0 | 155.2% | 0 | 125.3% | 0 | 1
CBP/S | 14218 | Modify Antisurge Control System of K1401 | Completed | CTA/M | Cheng Guiyou | Gan Shuangfeng | 2014-08-15 | 2015-04-22 | 2015-05-04 | 0 | T_2015 | ZNIC.014218 | NZNIC014218K |  | 14218 | 1000000 | 0 | 1008800 | 348420.96 | 0 | 3300 | 0 | 1000000 | 0 | 44791.01 | 1000000 | 348420.96 | -65.16% | 348420.96 | 0 | 0 | 0 | -4.666% | #DIV/0! | 3300 | 0% | 0 | #DIV/0! | 0 | 0
COA/A | 14207 | Let-down MP Steam to LP Steam in GAA Plant | On Going | CTE/P | Zhu Jianxin | Wu Zefei | 2015-09-18 | 0 | 0 | 0 | T_2015 | ZNIC.010379 | NZNIC014207K |  | 14207 | 2362000 | 0 | 3206055 | 1591482.91 | 1500031.67 | -119335 | -44890 | 2362000 | -1605997.59 | 449579.81 | 2362000 | 1912420.19 | -19.03% | 1591482.91 | 1500031.67 | 426903.2 | -1605997.59 | -28.13% | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CBP/S | 14200 | Add Control Valve at 1st Stage Inlet Nitrogen Line of K1701 | Completed | CTE/P | Wang Can | Ling Taizhong | 2015-02-13 | 2014-10-20 | 0 | 0 | N | ZNIF.104300.15.01 | NZNIC014200K |  | 14200 | 155000 | 0 | 174249 | 0 | 0 | -1445 | 11850 | 155000 | 0 | 15654.94 | 155000 | 0 | -100% | 0 | 0 | 0 | 0 | -31.25% | -32.28% | 0 | 102.8% | 11850 | 71.1% | 0 | 0
CBL/O | 14198 | Replace Manual Loading Arm Z2810&Z4802 with Pneumatic One | On Going | CTE/P | Yu Xiya | Xu Yefeng | 2015-03-11 | 0 | 0 | 0 | T | ZNIF.412740.15.01 | NZNIC014198K |  | 14198 | 440000 | 0 | 466800 | 299849.03 | 15940.52 | 30305 | 32450 | 440000 | 46902.73 | 11752.72 | 440000 | 365492.28 | -16.93% | 299849.03 | 15940.52 | 2800 | 46902.73 | -4.882% | #DIV/0! | 30305 | 61.15% | 32450 | 26.25% | 0 | 0
CBL/O | 14197 | Replace Manual Loading Arm Z2203 with Pneumatic One | On Going | CTE/P | Yu Xiya | Xu Yefeng | 2015-03-11 | 0 | 0 | 0 | T | ZNIF.651010.15.01 | NZNIC014197K |  | 14197 | 273000 | 0 | 294920 | 7147716.94 | 0 | 22215 | 31250 | 273000 | -6959651.32 | 10269.38 | 273000 | 209265.62 | -23.35% | 7147716.94 | 0 | 21200 | -6959651.32 | -8.39% | 1.882% | 22215 | 68.26% | 31250 | 30.56% | 0 | 0
COO/O | 14194 | Add a Pump and Two On/off Valves for Val Loading | On Going | CTE/P | Liu Xiaoli | Jiang Haijin | 2015-11-06 | 0 | 0 | 0 | N | ZNIC.010907 | NZNIC014194K |  | 14194 | 1260000 | 0 | 1412808 | 2649878.44 | 3100773.21 | 302500 | 238150 | 1260000 | -5051849.19 | 20547.54 | 1260000 | 698802.46 | -44.54% | 2649878.44 | 3100773.21 | 0 | -5051849.19 | -12.68% | #DIV/0! | 302500 | 0% | 238150 | 9.224% | 0 | 0
CBP/C | 14187 | Add Pipeline to Send Light Fuel Oil to STT1310 | On Going | CTE/P | Qiu Zhufeng | Ling Taizhong | 2014-08-21 | 0 | 0 | 0 | T_2015 | ZNIC.014187 | NZNIC014187K |  | 14187 | 4207000 | 2188000 | 5575289 | 263559.93 | 103531 | 20846.61 | -59019.28 | #N/A | #N/A | #N/A | 6395000 | #N/A | #N/A | 263559.93 | 103531 | 39112 | #N/A | #N/A | -16.35% | 20846.61 | 90.02% | 0 | 115% | 0 | 2
CEP/S | 14182 | Rebuilt a Waste Liquid Storage | Completed | CTE/C | Gao Feng | Xia Weiguang | 2015-05-07 | 2015-12-15 | 0 | 0 | H | ZNIF.105400.15.01 | NZNIC014182K |  | 14182 | 748000 | 0 | 1175500 | 165755.11 | 16000 | -78032.96 | -8650 | 748000 | 289046.36 | 50298.53 | 748000 | 697701.47 | -6.724% | 165755.11 | 16000 | 226900 | 289046.36 | #DIV/0! | -21.08% | 0 | 159.1% | 0 | 118% | 0 | 3
CTM | 14173 | Technical Material Bar-code Management System | On Going | CFA/I | Tao Yang | Wang Jun | 2014-06-13 | 0 | 0 | 0 | N | ZNIC.014173 | NZNIC014173K |  | 14173 | 2580000 | 0 | 4873537 | 15484487.68 | 0 | 0 | 0 | 2580000 | -12904487.68 | 0 | 2580000 | 2580000 | 0% | 15484487.68 | 0 | 0 | -12904487.68 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CEP/E | 14168 | Change an Online TOC Analyzer | On Going | CTA/S | Yong Jie | Yong Jie | 2014-08-26 | 0 | 0 | 0 | N | ZNIC.014168 | NZNIC014168K |  | 14168 | 480000 | 0 | 480000 | 352861.92 | 2000 | -550 | 8800 | 480000 | 114338.08 | 2000 | 480000 | 469200 | -2.25% | 352861.92 | 2000 | 0 | 114338.08 | -0.5% | #DIV/0! | 0 | 107.1% | 8800 | 0% | 0 | 0
CBP/C | 14165 | Add Pipe from BYC EBO Ship Loading Pipe to YPC G102 Tank | Completed | CTE/P | Qiu Zhufeng | Ling Taizhong | 2014-07-22 | 2015-05-27 | 0 | 0 | H | ZNIC.014165 | NZNIC014165K |  | 14165 | 1143000 | 1448000 | 4095032 | 147730.98 | 0 | 7680 | -217067.97 | 2591000 | 0 | 1069078.94 | 2591000 | 151730.98 | -94.14% | 147730.98 | 0 | 4000 | 0 | -42.15% | -21.79% | 7680 | 82.66% | 0 | 257.6% | 0 | 5
CBL/O | 14163 | Replacement of 3 Low Efficiency Motors in A300 & RTTF | Canceled | CTA/L | Chen Kun | Chen Kun | 2014-06-13 | 0 | 0 | 0 | N | ZNIC.014163 | NZNIC014163K |  | 14163 | 87789 | 0 | 87789 | 180926.11 | 799388.77 | 4400 | 35000 | 87789 | -931925.88 | 0 | 87789 | 48389 | -44.88% | 180926.11 | 799388.77 | 0 | -931925.88 | #DIV/0! | #DIV/0! | 4400 | 0% | 35000 | 0% | 0 | 0
CBP/C | 14151 | Add New Pan Oil Pipe from Pan oil Pump to Ethylene Bottom Oil Pipe | Completed | CTE/P | Sun Aihong | Ling Taizhong | 2015-01-13 | 2015-12-14 | 0 | 0 | T_2015 | ZNIF.104100.15.01 | NZNIC014151K |  | 14151 | 410000 | 0 | 483095 | 1372804.69 | 82972.84 | -1425 | -36825 | 410000 | -1099331.31 | 51553.78 | 410000 | 358446.22 | -12.57% | 1372804.69 | 82972.84 | 2000 | -1099331.31 | -11.89% | -41.12% | 0 | 101.8% | 0 | 149.8% | 0 | 0
All | 14149 | BYC Electrical Monitoring & Control System (EMCS) Migration | Completed | CTA/VO | Gu Hemei | Sun Zhongpin | 2014-06-05 | 2015-04-20 | 2015-10-29 | 0 | T_2015 | ZNIC.014149 | NZNIC014149K |  | 14149 | 9740000 | 0 | 9742700 | 5797061.95 | 0 | -376977.24 | -47306 | 9740000 | 0 | 1289086.73 | 9740000 | 5797061.95 | -40.48% | 5797061.95 | 0 | 0 | 0 | -14.73% | -16.39% | 0 | 268% | 0 | 187.8% | 0 | 3
CEP/S | 14144 | Add PIB Tank and Feed System in HIPS Plant | On Going | CTE/P | Gu Jingfeng | Wu Zefei | 2014-12-08 | 0 | 0 | 0 | H | ZNIC.008007 | NZNIC014144K |  | 14144 | 6240000 | 0 | 10167086 | 1031907.57 | 9991.45 | -96586.63 | -140434.6 | 6240000 | 4124796.04 | 165282.94 | 6240000 | 6074717.06 | -2.649% | 1031907.57 | 9991.45 | 908022 | 4124796.04 | -2.838% | -22.69% | 0 | 118.6% | 0 | 137.9% | 1 | 8
CBL/P | 14141 | Add a Manual Sampler on the NAP Feed Piping from YPC | On Going | CTE/P | Li Shouqing | Jiang Haijin | 2015-03-20 | 0 | 0 | 0 | N | ZNIF.604170.15.01 | NZNIC014141K |  | 14141 | 497000 | 0 | 600931 | 1005817.98 | 2751276.84 | 9805 | 24825 | 497000 | -3225083.81 | -121441.01 | 497000 | 583811.01 | 17.47% | 1005817.98 | 2751276.84 | 51800 | -3225083.81 | 68.97% | #DIV/0! | 9805 | 90.66% | 24825 | 63.49% | 0 | 0
CBP/A | 14126 | Add ESD Interlock Signal and Block Valve for 410-R101A/B | Completed | CTE/A | Gong Feibao | Li Hong | 2014-08-06 | 2015-04-29 | 0 | 0 | T_2015 | ZNIC.014126 | NZNIC014126K |  | 14126 | 191000 | 0 | 207000 | 278055.72 | 158094.74 | -23330 | -4403 | 191000 | 0 | 7768.2 | 191000 | 436150.46 | 128.4% | 278055.72 | 158094.74 | 0 | 0 | -4.72% | -44.34% | 0 | 183.2% | 0 | 114.2% | 0 | 0
CBP/C | 14121 | H109 Convection Section Modification | Completed | CTE/P | Zhou Yanduo | Ling Taizhong | 2014-07-30 | 2015-05-27 | 2015-07-08 | 0 | T_2015 | ZNIC.014121 | NZNIC014121K |  | 14121 | 16490000 | 0 | 16492000 | 633055.06 | 0 | 18180 | -193590.96 | 16490000 | 0 | 13222412.33 | 16490000 | 635055.06 | -96.15% | 633055.06 | 0 | 2000 | 0 | -83.16% | 1.553% | 18180 | 90.04% | 0 | 162.3% | 0 | 0
CBP/M | 14115 | Replacement of 16 Low Efficiency Motors in EB/SM Plant | Completed | CTA/M | Lv Yong | Lv Yong | 2014-06-18 | 2015-07-14 | 0 | 0 | N | ZNIC.014115 | NZNIC014115K |  | 14115 | 873000 | 0 | 875000 | 5107010.57 | 601121.7 | 0 | 138240 | 873000 | 0 | 146828.34 | 873000 | 5708132.27 | 553.9% | 5107010.57 | 601121.7 | 0 | 0 | -30.86% | 2.773% | 0 | #DIV/0! | 138240 | 4% | 0 | 0
CHA | 14112 | EPS Replacement for Z100 1st and 2nd Floor | Completed | CTE/A | Bian Jiacai | Chen Gang | 2014-06-06 | 2015-03-31 | 0 | 0 | N | ZNIC.014112 | NZNIC014112K |  | 14112 | 284000 | 0 | 309000 | 346892.57 | 95000 | 5075 | -10725 | 284000 | 0 | 74872 | 284000 | 466892.57 | 64.4% | 346892.57 | 95000 | 25000 | 0 | -44.04% | #DIV/0! | 5075 | 83.07% | 0 | 134.8% | 0 | 0
CEP/S | 14107 | PS/EPS Plant Emergency Lighting Modification | On Going | CTE/A | Xu Zheng | Zhang Pu | 2015-07-24 | 0 | 0 | 0 | H | ZNIC.009924 | NZNIC014107K |  | 14107 | 1329000 | 0 | 2128389 | 412980.91 | 46000 | -2522.64 | 55700 | 1329000 | 222304.32 | 83393.27 | 1329000 | 1189906.73 | -10.47% | 412980.91 | 46000 | 508621.5 | 222304.32 | -11.71% | -5.66% | 0 | 104.1% | 55700 | 5.593% | 0 | 2
COO/A | 14104 | Add a Pipeline of ACN Waste Liquid to U5 Incinerator | On Going | CTE/P | Li Shouqing | Jiang Haijin | 2015-01-21 | 0 | 0 | 0 | N | ZNIC.008275 | NZNIC014104K |  | 14104 | 2063000 | 0 | 2151486 | 1233823.67 | 266524.42 | -16000 | -207203.72 | #N/A | #N/A | #N/A | 2063000 | #N/A | #N/A | 1233823.67 | 266524.42 | 594078 | #N/A | #N/A | -19.37% | 0 | 108.8% | 0 | 260.6% | 0 | 1
CTS/U | 14101 | Replacement of ID Fans_Phase II CLWI Modification | Completed | CTE/P | Zhou Yanduo | Jiang Haijin | 2014-04-28 | 2015-05-05 | 0 | 0 | T_2015 | ZNIC.014101 | NZNIC014101K |  | 14101 | 6213000 | 0 | 6354998 | 910066.25 | 64000 | -69218.58 | -403842.1 | 6213000 | 0 | -1007216.21 | 6213000 | 1019566.25 | -83.59% | 910066.25 | 64000 | 45500 | 0 | 35.54% | -3.613% | 0 | 113.5% | 0 | 250.2% | 0 | 9
CBP/C | 14097 | Add Fire Water Sprinkler Facilities for Pumps | Completed | CTE/P | Zhang Fanwen | Ling Taizhong | 2014-07-22 | 2015-10-08 | 0 | 0 | H | ZNIC.014097 | NZNIC014097K |  | 14097 | 1229000 | 0 | 1543231 | 2702154.85 | 0 | -11319.2 | -33375.3 | 1229000 | 0 | 20176.14 | 1229000 | 2798546.85 | 127.7% | 2702154.85 | 0 | 96392 | 0 | -4.307% | 2.407% | 0 | 106.2% | 0 | 116.7% | 0 | 1
CBP/C | 14091 | APC Implementation and Optimization of Ethylene Unit | On Going | CTA/S | Dai Xiaolong | Dai Xiaolong | 2014-03-19 | 0 | 0 | 0 | N | ZNIC.014091 | NZNIC014091K |  | 14091 | 11000000 | 0 | 13751277 | 111094.64 | 0 | -1082605.88 | 165800 | 11000000 | 10298311.89 | 424793.47 | 11000000 | 10409406.53 | -5.369% | 111094.64 | 0 | 0 | 10298311.89 | -10.46% | #DIV/0! | 0 | 460.9% | 165800 | 44.73% | 3 | 0
COO/A | 14088 | Increase the Yield of Product AEEA | Completed | CTE/P | Li Shouqing | Jiang Haijin | 2014-12-22 | 2015-10-09 | 0 | 0 | T_2015 | ZNIF.107830.14.01 | NZNIC014088K |  | 14088 | 494000 | 0 | 665445 | 342262.57 | 0 | -4610 | 1925 | 494000 | 0 | 10816.1 | 494000 | 343612.57 | -30.44% | 342262.57 | 0 | 1350 | 0 | 1.075% | -18.33% | 0 | 103.7% | 1925 | 97.81% | 0 | 1
CCP/O | 14087 | Add On/off Valves for HV24201/HV44201 | Completed | CTE/A | Wang Zhen | Wang Xinwu | 2014-06-03 | 2015-05-08 | 0 | 0 | T_2015 | ZNIC.014087 | NZNIC014087K |  | 14087 | 490000 | 140000 | 634555 | 372868.19 | 0 | -7700 | -48813.06 | 490000 | 0 | -194772.13 | 630000 | 374368.19 | -40.58% | 372868.19 | 0 | 1500 | 0 | 181.9% | -42.43% | 0 | 105.6% | 0 | 196.5% | 0 | 2
CEP/P | 14086 | Replacement of AMOT by Sentry System | Completed | CTE/A | Wang Zhen | Li Xueyong | 2014-05-19 | 2015-05-07 | 0 | 0 | T_2015 | ZNIC.014086 | NZNIC014086K |  | 14086 | 5612000 | 0 | 6213122 | 538736.16 | 4000 | 79750 | 40422 | 5612000 | 0 | 210924.66 | 5612000 | 542736.16 | -90.33% | 538736.16 | 4000 | 0 | 0 | -2.966% | -26.34% | 79750 | 68.82% | 40422 | 71.24% | 0 | 0
CBP/C | 14072 | Add 7 Samplers for Quench Section of Cracker | Completed | CTE/P | Qiu Zhufeng | Ling Taizhong | 2014-07-22 | 2015-05-09 | 0 | 0 | T_2015 | ZNIC.014072 | NZNIC014072K |  | 14072 | 593000 | 0 | 693000 | 139342.06 | 101839.4 | 7760 | 16329.11 | 593000 | 0 | -42106.55 | 593000 | 241181.46 | -59.33% | 139342.06 | 101839.4 | 0 | 0 | 16.67% | -10.27% | 7760 | 91.7% | 16329.11 | 87.73% | 0 | 0
CBP/M | 14068 | Replace Samplers for EB/SM | Completed | CTE/P | Sun Aihong | Wu Zefei | 2014-08-11 | 2015-04-30 | 0 | 0 | T_2015 | ZNIC.014068 | NZNIC014068K |  | 14068 | 485000 | 0 | 532500 | 8396184.58 | 18000 | 14200 | 23064.83 | 485000 | 0 | 182574.7 | 485000 | 8414184.58 | 1635% | 8396184.58 | 18000 | 0 | 0 | -49.56% | 12.34% | 14200 | 80.14% | 23064.83 | 70.15% | 0 | 0
CBP/M | 14067 | Replace Some Pumps for EB/SM | On Going | CTE/P | Wang Lifen | Ling Taizhong | 2014-08-15 | 0 | 0 | 0 | N | ZNIC.014067 | NZNIC014067K |  | 14067 | 1900000 | 0 | 2603495 | 574600.02 | 0 | -72464.76 | -120389.16 | 1900000 | 303189.16 | 439999.82 | 1900000 | 1460000.18 | -23.16% | 574600.02 | 0 | 582211 | 303189.16 | -33.37% | -29.92% | 0 | 135.4% | 0 | 146.7% | 9 | 8
CBP/M | 14066 | Revamp Outlet Motor Valves of Cooling Water Pumps | Completed | CTE/A | Gong Feibao | Li Hong | 2014-07-23 | 2015-04-23 | 0 | 0 | T_2015 | ZNIC.014066 | NZNIC014066K |  | 14066 | 1380000 | 0 | 1446000 | 405015.72 | 18205.13 | -21295 | -9865.43 | 1380000 | 0 | 1291047.2 | 1380000 | 423220.85 | -69.33% | 405015.72 | 18205.13 | 0 | 0 | -63.15% | -14.34% | 0 | 112.5% | 0 | 105.4% | 0 | 0
CBP/B | 14058 | Move the BD&IB Plant DCS Control Station from BCC to EBSM | Completed | CTE/A | Gong Feibao | Li Hong | 2014-08-19 | 2015-04-21 | 0 | 0 | T_2015 | ZNIC.014058 | NZNIC014058K |  | 14058 | 3400000 | 0 | 3410505 | 2165099.84 | 0 | -151971.82 | -98115.5 | 3400000 | 0 | 781486.66 | 3400000 | 2168404.84 | -36.22% | 2165099.84 | 0 | 3305 | 0 | -27.15% | -30.45% | 0 | 153.4% | 0 | 123.6% | 0 | 7
CEP/E | 14051 | Natural Gas Flowmeter Modification | Completed | CTE/P | Gu Jingfeng | Wu Zefei | 2014-03-17 | 2014-09-04 | 0 | 0 | T | ZNIC.014051 | NZNIC014051K |  | 14051 | 157000 | 0 | 158500 | 934930.21 | 8000 | 4950 | 19189.92 | 157000 | 0 | 321.44 | 157000 | 944430.21 | 501.5% | 934930.21 | 8000 | 1500 | 0 | 11.81% | -64.12% | 4950 | 92.62% | 19189.92 | 57.71% | 0 | 1
CBP/C | 14045 | Add Gas Detector around Liquid Hydrocarbon Pumps | Completed | CTE/A | Wang Zhen | Li Hong | 2014-07-16 | 2015-07-09 | 0 | 0 | N | ZNIC.014045 | NZNIC014045K |  | 14045 | 491000 | 0 | 503000 | 2022304.96 | 4498 | -8800 | -6600 | 491000 | 0 | 18860.84 | 491000 | 2038802.96 | 315.2% | 2022304.96 | 4498 | 12000 | 0 | 3.563% | -32.47% | 0 | 109.1% | 0 | 109.2% | 0 | 0
CBP/M | 14035 | Revamp H1203 Natural Gas Pipeline | Completed | CTE/P | Sun Aihong | Wu Zefei | 2014-06-06 | 2015-04-30 | 0 | 0 | T_2015 | ZNIC.014035 | NZNIC014035K |  | 14035 | 418000 | 0 | 419200 | 235404.64 | 0 | -5310 | 31263.4 | 418000 | 0 | 32076.6 | 418000 | 235404.64 | -43.68% | 235404.64 | 0 | 0 | 0 | -9.67% | -28% | 0 | 104.1% | 31263.4 | 69.76% | 0 | 0
CBP/M | 14034 | Add an Inhibitor Surge Drum for Each of T2401/2403 | Completed | CTE/P | Sun Aihong | Wu Zefei | 2014-07-21 | 2015-09-08 | 0 | 0 | T_2015 | ZNIC.014034 | NZNIC014034K |  | 14034 | 477000 | 0 | 542736 | 2301084.59 | 30000 | -24420 | -56351.67 | 477000 | 0 | 70420.5 | 477000 | 2331084.59 | 388.7% | 2301084.59 | 30000 | 0 | 0 | -14.46% | -38.48% | 0 | 120.7% | 0 | 140.1% | 0 | 2
CBP/M | 14033 | Add O2 Detector at Discharge of C2401 | Completed | CTE/A | Gong Feibao | Li Hong | 2014-07-10 | 2015-11-04 | 0 | 0 | T_2015 | ZNIC.014033 | NZNIC014033K |  | 14033 | 246000 | 0 | 352085 | 0 | 0 | -9222.07 | -30253 | 246000 | 258411.42 | -12411.42 | 246000 | 258411.42 | 5.045% | 0 | 0 | 0 | 258411.42 | 12.23% | -7.608% | 0 | 115.8% | 0 | 184.6% | 7 | 0
CBP/M | 14031 | 380VAC LV MCC System Modification of EB/SM | Completed | CTE/A | Zhao Wei | Sun Zhongpin | 2014-06-05 | 2015-05-08 | 2015-10-26 | 0 | T_2015 | ZNIC.014031 | NZNIC014031K |  | 14031 | 12200000 | 0 | 12485476 | 1276119.98 | 0 | 113179.14 | -210620.5 | #N/A | 0 | #N/A | 12200000 | 1543595.78 | -87.35% | 1276119.98 | 0 | 267475.8 | 0 | #N/A | -31.3% | 113179.14 | 91.6% | 0 | 159.2% | 0 | 12
CBP/C | 14023 | Expand the Capacity of 330-V-344 | Completed | CTE/P | Qiu Zhufeng | Ling Taizhong | 2014-06-04 | 2015-05-09 | 0 | 0 | T_2015 | ZNIC.014023 | NZNIC014023K |  | 14023 | 497000 | 100000 | 574600 | 1838951.56 | 0 | 12126.1 | -6871.17 | 597000 | 0 | 147937.95 | 597000 | 1838951.56 | 208% | 1838951.56 | 0 | 0 | 0 | -36.36% | -22.1% | 12126.1 | 91.8% | 0 | 105.2% | 0 | 4
COA/S | 14015 | E1210 Condensate Recycle | On Going | CTE/P | Zhu Jianxin | Wu Zefei | 2015-01-15 | 0 | 0 | 0 | N | ZNIF.106500.15.01 | NZNIC014015K |  | 14015 | 830000 | 290000 | 854477 | 307412.69 | 0 | 154110 | 122850 | 1120000 | 517373.92 | 11981.39 | 1120000 | 831058.61 | -25.8% | 307412.69 | 0 | 6272 | 517373.92 | -4.233% | -17.45% | 154110 | 51.38% | 122850 | 19.18% | 0 | 1
CTS/U | 14002 | Replace Material of the Pipeline between Compressor and Dryer | Completed | CTE/P | Li Shouqing | Zhang Fanwen | 2014-04-23 | 2015-04-24 | 0 | 0 | T_2015 | ZNIC.014002 | NZNIC014002K |  | 14002 | 2360000 | 0 | 2377500 | 1317699.78 | 160101 | -18560 | -77089.53 | 2360000 | 0 | -448100.21 | 2360000 | 1495300.78 | -36.64% | 1317699.78 | 160101 | 17500 | 0 | 54.73% | 4.618% | 0 | 114.2% | 0 | 144.2% | 0 | 0
CTS/U | 14001 | Add Heat Exchanger of CPS Pipeline to BCC | Completed | CTE/P | Li Shouqing | Zhang Fanwen | 2014-06-03 | 2015-04-30 | 0 | 0 | T_2015 | ZNIC.014001 | NZNIC014001K |  | 14001 | 1194000 | 0 | 1344261 | 3335935.81 | 431.09 | -21256.48 | 2578.3 | 1194000 | 0 | 124067.15 | 1194000 | 3338627.9 | 179.6% | 3335935.81 | 431.09 | 2261 | 0 | 1.364% | -29.74% | 0 | 112.5% | 2578.3 | 98.47% | 0 | 2
CBP/A | 13277 | D230 MCC Modification | Completed | CTE/A | Hu Xiao | Chen Gang | 2014-05-05 | 2015-05-08 | 0 | 0 | T_2015 | ZNIC.013277 | NZNIC013277K |  | 13277 | 3950000 | 0 | 3964380 | 594140.5 | 62.8 | -72400.52 | 91817.32 | #N/A | 0 | #N/A | 3950000 | 596585.3 | -84.9% | 594140.5 | 62.8 | 2382 | 0 | #N/A | 3.676% | 0 | 140.4% | 91817.32 | 65.37% | 0 | 4
CBP/M | 13270 | Gas Detector Modification for EB/SM Tank Farm | Completed | CTE/A | Wang Zhen | Li Hong | 2014-03-11 | 2015-09-03 | 0 | 0 | N | ZNIC.013270 | NZNIC013270K |  | 13270 | 432000 | 0 | 432000 | 436207.83 | 0 | -580 | -2475 | 432000 | 0 | 87683.36 | 432000 | 436207.83 | 0.974% | 436207.83 | 0 | 0 | 0 | -43.38% | -23.45% | 0 | 100.8% | 0 | 105.4% | 0 | 0
CHA | 13265 | Modify IET Office to Archive Centre Storeroom | Completed | CTE/C | Yu Yi | Jiang Yunning | 2014-10-14 | 2015-02-28 | 2015-09-04 | 0 | N | ZNIC.007512 | NZNIC013265K |  | 13265 | 1221000 | 1600000 | 2851000 | 342989.4 | 10345.47 | 4252.39 | -380587.92 | 2821000 | 0 | 208666.37 | 2821000 | 353334.87 | -87.47% | 342989.4 | 10345.47 | 0 | 0 | -34.54% | -12.12% | 4252.39 | 95.38% | 0 | 417.4% | 0 | 3
COA/E | 13263 | Add Solenoid Valve for P5845 and P6660/P6665 Diaphragm Pump Air Supply | Completed | CTA/A | Guo Jinhua | Guo Jinhua | 2014-01-22 | 2015-08-30 | 0 | 0 | N | ZNIC.013263 | NZNIC013263K |  | 13263 | 70000 | 0 | 70000 | 494014.8 | 0 | 0 | 1500 | 70000 | 0 | 0 | 70000 | 494014.8 | 605.7% | 494014.8 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 1500 | 0% | 0 | 0
CBP/C | 13260 | Upgrade PLC of Turbonmachinery Control System | Completed | CTA/B | Zhao Yongming | Zhao Yongming | 2013-12-11 | 2015-05-31 | 2015-05-28 | 0 | T_2015 | ZNIC.013260 | NZNIC013260K |  | 13260 | 2000000 | 0 | 2000000 | 566235.58 | 0 | 75600 | 0 | 2000000 | 0 | 490020.62 | 2000000 | 566235.58 | -71.69% | 566235.58 | 0 | 0 | 0 | -24.77% | #DIV/0! | 75600 | 5.5% | 0 | #DIV/0! | 0 | 0
CBP/C | 13259 | Upgrade Speed Control System of Compressors | Completed | CTA/B | Zhao Yongming | Zhao Yongming | 2013-12-11 | 2015-05-31 | 2015-05-28 | 0 | T_2015 | ZNIC.013259 | NZNIC013259K |  | 13259 | 2000000 | 0 | 2000000 | 3953938.62 | 80000 | 80000 | 0 | 2000000 | 0 | -201573.34 | 2000000 | 4033938.62 | 101.7% | 3953938.62 | 80000 | 0 | 0 | 10.34% | #DIV/0! | 80000 | 0% | 0 | #DIV/0! | 0 | 0
CBP/M | 13257 | Add a Waste Water Pump in EB/SM | Completed | CTE/P | Sun Aihong | Ling Taizhong | 2014-03-11 | 2015-12-11 | 0 | 0 | N | ZNIC.013257 | NZNIC013257K |  | 13257 | 365000 | 0 | 445854 | 15618577.86 | 100959.69 | 11640 | -11766.22 | 365000 | -15399602.03 | 26424.48 | 365000 | 326935.52 | -10.43% | 15618577.86 | 100959.69 | 7000 | -15399602.03 | -7.491% | -13.52% | 11640 | 88.56% | 0 | 115.1% | 0 | 1
CBP/C | 13247 | Modification of Filter System for P230 | Completed | CTE/P | Wang Can | Ling Taizhong | 2014-07-10 | 2015-05-09 | 0 | 0 | T_2015 | ZNIC.013247 | NZNIC013247K |  | 13247 | 1055000 | 495000 | 1485801 | 0 | 123215.39 | -65730.09 | -9245.61 | 1055000 | 0 | -586764.33 | 1550000 | 123215.39 | -92.05% | 0 | 123215.39 | 0 | 0 | 88.15% | -13.41% | 0 | 132.7% | 0 | 105.8% | 1 | 3
CBP/B | 13244 | Add Spare Exchangers and Filters in BEU | Completed | CTE/P | Gu Jingfeng | Ling Taizhong | 2014-03-11 | 2015-08-07 | 0 | 0 | T_2015 | ZNIC.013244 | NZNIC013244K |  | 13244 | 5250000 | 0 | 5251931 | 2179329.18 | 0 | -325563.53 | -170071.53 | 5250000 | 0 | 1619190.82 | 5250000 | 2180829.18 | -58.46% | 2179329.18 | 0 | 1500 | 0 | -44.8% | -18.29% | 0 | 181.3% | 0 | 156.2% | 0 | 7
CEP/S | 13243 | Revamp Rain Drainage System of PS Tank Farm | Completed | CTE/C | Gao Feng | Zhang Zhihe | 2014-07-21 | 2015-08-20 | 0 | 0 | H | ZNIC.013243 | NZNIC013243K |  | 13243 | 561000 | 0 | 598204 | 2308010.69 | 5000 | 32768.2 | -19676.26 | 561000 | 0 | 49509.96 | 561000 | 2317010.69 | 313% | 2308010.69 | 5000 | 4000 | 0 | -3.773% | -18.62% | 32768.2 | 81.61% | 0 | 119.5% | 0 | 3
CAP/E | 13240 | Add Jacket Heat Exchanger on V6700 | Completed | CTE/P | Xie Qiang | Wu Zefei | 2014-01-17 | 2014-09-04 | 0 | 0 | N | ZNIC.013240 | NZNIC013240K |  | 13240 | 410000 | 0 | 437708 | 853489.94 | 81632.29 | -5905 | -20524.44 | #N/A | 0 | #N/A | 410000 | 936622.23 | 128.4% | 853489.94 | 81632.29 | 1500 | 0 | #N/A | -27.27% | 0 | 105.5% | 0 | 124.2% | 0 | 1
CBL/O | 13236 | Rebuild RTTF Operation Room 1&2 | Completed | CTE/C | Yu Yi | Guo Bing | 2014-09-11 | 2015-10-31 | 0 | 0 | N | ZNIC.013236 | NZNIC013236K |  | 13236 | 942000 | 0 | 1383028 | 4188948.63 | 0 | -6810 | 33188.45 | 942000 | -3686177.81 | -24642.27 | 942000 | 933453.82 | -0.9072% | 4188948.63 | 0 | 430683 | -3686177.81 | 50.92% | -38.72% | 0 | 104.8% | 33188.45 | 74.65% | 0 | 3
CBP/A | 13234 | Replacement of 800-UPS-001 | Completed | CTE/A | Bian Jiacai | Chen Gang | 2014-01-27 | 2015-04-16 | 0 | 0 | T_2015 | ZNIC.013234 | NZNIC013234K |  | 13234 | 774000 | 0 | 774000 | 2898798.17 | 20095 | 1251.89 | -4677 | 774000 | 0 | 129054.19 | 774000 | 2918893.17 | 277.1% | 2898798.17 | 20095 | 0 | 0 | -21.64% | 4.821% | 1251.89 | 97.48% | 0 | 120.7% | 0 | 3
CBP/C | 13233 | Replacement of 300-UPS-001 | Completed | CTE/A | Bian Jiacai | Chen Gang | 2014-01-27 | 2015-04-23 | 0 | 0 | T_2015 | ZNIC.013233 | NZNIC013233K |  | 13233 | 881000 | 0 | 881000 | 2785887.7 | 80000 | 11560 | -2795.88 | 881000 | 0 | 127408.53 | 881000 | 2865887.7 | 225.3% | 2785887.7 | 80000 | 0 | 0 | -18.57% | 17.74% | 11560 | 76.78% | 0 | 112.4% | 0 | 2
CBP/C | 13229 | Replace Economizer with High Efficient Type for SUB | Completed | CTE/P | Qiu Zhufeng | Ling Taizhong | 2014-04-14 | 2015-05-06 | 0 | 0 | T_2015 | ZNIC.013229 | NZNIC013229K |  | 13229 | 3054000 | 1553000 | 4073939 | 1404921.44 | 0 | -21153.97 | -14625 | 3054000 | 0 | -196768.88 | 4607000 | 1444921.44 | -68.64% | 1404921.44 | 0 | 40000 | 0 | 4.776% | 4.668% | 0 | 112.4% | 0 | 110.1% | 1 | 0
CCP/A | 13224 | Add 2000m3 DEOA Tank in RTTF | Completed | CTE/P | Jiang Hao/Liu Xiaoli | Xu Yefeng/Zong Baorong | 2014-02-27 | 2015-05-05 | 0 | 0 | T_2015 | ZNIC.013224 | NZNIC013224K |  | 13224 | 15880000 | 0 | 16101960 | 163582.22 | 44000 | 332800 | 202300 | 15880000 | 0 | -54575.1 | 15880000 | 207582.22 | -98.69% | 163582.22 | 44000 | 0 | 0 | 56.4% | -27.37% | 332800 | 0% | 202300 | 18.95% | 0 | 0
CTS/U | 13209 | Adding a New Ultrasonic Flowmeter on DM Water in CLWI | Hold | CTA/U | Yu Yong | Yu Yong | 2013-10-10 | 0 | 0 | 0 | N | ZNIC.013209 | NZNIC013209K |  | 13209 | 90000 | 0 | 213215 | 5873055.08 | 1583692.53 | 0 | 5000 | 90000 | -7371747.61 | 0 | 90000 | 85000 | -5.556% | 5873055.08 | 1583692.53 | 0 | -7371747.61 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 5000 | 0% | 0 | 0
COO/C | 13198 | NPG_TMA Supply from C1 Plant | Completed | CTE/P | Sun Duoxun | Jiang Haijin | 2013-09-11 | 2015-06-05 | 0 | 0 | T_2015 | ZNIC.131198 | NZNIC013198K |  | 13198 | 1676000 | 0 | 2185329 | 914799.43 | 0 | -352510.27 | -287309.01 | 1676000 | 0 | 129032.34 | 1676000 | 920799.43 | -45.06% | 914799.43 | 0 | 6000 | 0 | -31.39% | 0.4295% | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 4
COO/O | 13197 | NPG_IBA Supply from OXO Plant | Completed | CTE/P | Sun Duoxun | Jiang Haijin | 2013-09-11 | 2015-06-03 | 0 | 0 | T_2015 | ZNIC.131197 | NZNIC013197K |  | 13197 | 1720000 | 0 | 2319011 | 952566.79 | 0 | -345333.97 | -276334.4 | 1720000 | 0 | 328807.09 | 1720000 | 958566.79 | -44.27% | 952566.79 | 0 | 6000 | 0 | -39.1% | -17.22% | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 3
CBP/M | 13195 | Replace an Air Dryer | On Going | CTE/P | Ding Juntao | Ling Taizhong | 2014-12-24 | 0 | 0 | 0 | N | ZNIC.008126 | NZNIC013195K |  | 13195 | 1344000 | 0 | 1596491 | 1128415.8 | 3111.11 | -49443.02 | -27500 | 1344000 | -215420.64 | 171914.73 | 1344000 | 1172085.27 | -12.79% | 1128415.8 | 3111.11 | 255979 | -215420.64 | -19.3% | -46.85% | 0 | 136.4% | 0 | 119.6% | 0 | 6
CBP/C | 13190 | Add Explosion-proof Monitoring Camera in BCC&SCTF | Completed | CTE/A | Bian Jiacai | Chen Gang | 2014-02-10 | 2015-06-30 | 0 | 0 | N | ZNIC.013190 | NZNIC013190K |  | 13190 | 5665000 | 0 | 5675760 | 12384256.04 | 6752.13 | 2820 | -18150 | 5665000 | 0 | 1068608.18 | 5665000 | 12391008.17 | 118.7% | 12384256.04 | 6752.13 | 0 | 0 | -23.7% | -5.856% | 2820 | 98.62% | 0 | 106.7% | 0 | 0
CBP/M | 13189 | Air-conditioning System Modification in CCR of 7100 | Completed | CTE/C | Gao Feng | Wang Wei | 2014-01-28 | 2015-06-30 | 0 | 0 | N | ZNIC.013189 | NZNIC013189K |  | 13189 | 4234000 | 0 | 4398544 | 1479893 | 0 | -54198.12 | 9568.87 | #N/A | 0 | #N/A | 4234000 | 1493478 | -64.73% | 1479893 | 0 | 13585 | 0 | #N/A | -19.36% | 0 | 123.2% | 9568.87 | 94.14% | 0 | 2
CBP/M | 13184 | Modify Waste Water System for EB/SM Tank Farm | Completed | CTE/P | Sun Aihong | Ling Taizhong | 2014-04-24 | 2015-11-06 | 0 | 0 | T_2015 | ZNIC.013184 | NZNIC013184K |  | 13184 | 4080000 | 0 | 4814735 | 200821.98 | 0 | -20197.27 | -169055.05 | 4080000 | 2328004.77 | 1233088.25 | 4080000 | 2846911.75 | -30.22% | 200821.98 | 0 | 318085 | 2328004.77 | -35.79% | -21.21% | 0 | 107.5% | 0 | 147.7% | 0 | 5
CEP/S | 13165 | Control System of Pelletizing Upgrading in HIPS | Completed | CTE/A | Gong Feibao | Zeng Qing | 2013-11-13 | 2015-05-28 | 0 | 0 | T_2015 | ZNIC.013165 | NZNIC013165K |  | 13165 | 1139000 | 91000 | 1404921 | 1792039.75 | 8000 | 58600 | 77500 | 1139000 | 0 | -640000 | 1230000 | 1800039.75 | 46.34% | 1792039.75 | 8000 | 0 | 0 | 66.67% | #DIV/0! | 58600 | 38.96% | 77500 | 0% | 0 | 0
CBP/C | 13156 | Add a Control Valve on K650 Outlet Line to Flare | Completed | CTE/P | Qiu Zhufeng | Li Hong | 2013-12-17 | 2015-04-28 | 0 | 0 | T_2015 | ZNIC.013156 | NZNIC013156K |  | 13156 | 340000 | 0 | 390000 | 2569715.72 | 6557.26 | 22600 | -9034.34 | 340000 | 0 | 37188.48 | 340000 | 2576272.98 | 657.7% | 2569715.72 | 6557.26 | 0 | 0 | -22.75% | -42.71% | 22600 | 67.13% | 0 | 121.2% | 0 | 0
CAP/A | 13133 | Add New Restab Unit System | Completed | CTE/P | Zhu Jianxin | Wu Zefei | 2014-01-24 | 2014-12-16 | 0 | 0 | H | ZNIC.013133 | NZNIC013133K |  | 13133 | 8751000 | 0 | 10339693 | 987739.89 | 0 | -619842.02 | -265472.81 | 8751000 | 0 | 1411008.29 | 8751000 | 992739.89 | -88.66% | 987739.89 | 0 | 5000 | 0 | -26.34% | -33.37% | 0 | 201.4% | 0 | 136.9% | 9 | 7
CBP/M | 13120 | EB/SM Plant Paging System Modification | Completed | CTA/S | Dai Xiaolong | Qiu Wei | 2013-07-10 | 2015-06-30 | 0 | 0 | N | ZNIC.013120 | NZNIC013120K |  | 13120 | 950000 | 0 | 963899 | 488548.7 | 35000 | -4714 | 4950.58 | 950000 | 0 | -159529.9 | 950000 | 537447.7 | -43.43% | 488548.7 | 35000 | 13899 | 0 | 24.09% | -6.733% | 0 | 147.1% | 4950.58 | 83.5% | 0 | 1
CEP/S | 13115 | PS&EPS Plant Paging System Modification | Completed | CTA/S | Dai Xiaolong | Qiu Wei | 2013-07-10 | 2015-06-30 | 0 | 0 | H | ZNIC.013115 | NZNIC013115K |  | 13115 | 1050000 | 0 | 1050000 | 10398219.24 | 55160 | -18875 | 30000 | 1050000 | 0 | -143097.13 | 1050000 | 10453379.24 | 895.6% | 10398219.24 | 55160 | 0 | 0 | 20.01% | -14.74% | 0 | 288.8% | 30000 | 0% | 0 | 0
CEP/S | 13114 | Add Back Flow Protection in Utility Supply Pipes | Completed | CTE/P | Gu Jingfeng | Zhang Fanwen | 2013-08-29 | 2015-05-05 | 0 | 0 | T_2015 | ZNIC.013114 | NZNIC013114K |  | 13114 | 1996000 | 0 | 1999111 | 17404454.84 | 88866.57 | -45660.51 | -17168.87 | 1996000 | 0 | 618079.77 | 1996000 | 17493321.41 | 776.4% | 17404454.84 | 88866.57 | 0 | 0 | -72.48% | -20.94% | 0 | 127.6% | 0 | 109.6% | 0 | 2
CTS/U | 13112 | CLWI Modification | Completed | CTE/P | Zhou Yanduo | Zhang Fanwen | 2013-11-04 | 2015-01-13 | 2015-07-10 | 0 | H | ZNIC.013112 | NZNIC013112K |  | 13112 | 16000000 | 0 | 16045806 | 9200387.35 | 871.8 | -7723526.81 | -493586.35 | 16000000 | 0 | 1068187.92 | 16000000 | 9240312.65 | -42.25% | 9200387.35 | 871.8 | 39053.5 | 0 | -5.846% | -22.81% | 0 | 3189% | 0 | 335% | 6 | 15
CCP/A | 13106 | Add a EDA Recycle Pump to Produce More PIP/DETA | Completed | CTE/P | Li Shouqing | Wang Wei | 2013-08-07 | 2014-08-31 | 0 | 0 | T | ZNIC.013106 | NZNIC013106K |  | 13106 | 1715000 | 0 | 1715000 | 35347526.69 | 0 | 17614.53 | -115361.37 | 1715000 | 0 | 247600.61 | 1715000 | 35347526.69 | 1961% | 35347526.69 | 0 | 0 | 0 | -18.84% | -26.87% | 17614.53 | 93.17% | 0 | 183.9% | 0 | 2
CBP/C | 13105 | Add a Gasoline Reflux Pump for Quench Oil Fractionator | Canceled | CTE/P | Sun Aihong | Ling Taizhong | 2014-02-08 | 0 | 0 | 0 | T_2015 | ZNIC.013105 | NZNIC013105K |  | 13105 | 1947000 | 0 | 1947000 | 1225101.06 | 0 | 143495 | 239487.52 | 1947000 | 267487.07 | 71429.35 | 1947000 | 1492588.13 | -23.34% | 1225101.06 | 0 | 0 | 267487.07 | -3.622% | -77.76% | 143495 | 46.32% | 239487.52 | 18.07% | 0 | 0
CTA | 13096 | C402 HVAC Replacement and Roof Repair | Completed | CTE/C | Yu Yi | Wang Wei | 2013-11-25 | 2015-02-05 | 0 | 0 | N | ZNIC.013096 | NZNIC013096K |  | 13096 | 2660000 | 0 | 2668000 | 198961.96 | 0 | -49810 | -426602.39 | 2660000 | 0 | 678663.9 | 2660000 | 198961.96 | -92.52% | 198961.96 | 0 | 0 | 0 | -42.96% | -15.33% | 0 | 125.9% | 0 | 336.5% | 0 | 2
CBP/C | 13081 | Replace the Electric Heat Tracing on Furnaces | On Going | CTE/A | Wang Zhen | Li Hong | 2013-09-04 | 0 | 0 | 0 | T_2015 | ZNIC.013081 | NZNIC013081K |  | 13081 | 3238000 | 0 | 3564454 | 3390558.14 | 0 | -19825 | -314050 | 3238000 | -856972.03 | 409516.89 | 3238000 | 2828483.11 | -12.65% | 3390558.14 | 0 | 294897 | -856972.03 | -24.3% | -13.29% | 0 | 104.6% | 0 | 159.5% | 0 | 0
CEP/L | 13064 | Fire Alarm System Modification in PS/EPS Logistics | Completed | CTE/A | Hu Xiao | Zhang Pu | 2013-09-02 | 2014-05-27 | 0 | 0 | H | ZNIC.013064 | NZNIC013064K |  | 13064 | 977000 | 0 | 987740 | 7811054.88 | 202040.21 | -27880.01 | 16225 | 977000 | 0 | 36997.21 | 977000 | 8013095.09 | 720.2% | 7811054.88 | 202040.21 | 0 | 0 | -5.324% | -4.121% | 0 | 123.3% | 16225 | 91.18% | 0 | 2
CBP/C | 13060 | Add Two Inhibiter Injection Pumps | Completed | CTE/P | Sun Aihong | Ling Taizhong | 2014-03-26 | 2015-05-09 | 0 | 0 | T_2015 | ZNIC.013060 | NZNIC013060K |  | 13060 | 650000 | 0 | 685000 | 1995929.24 | 0 | -1995 | 36765.83 | 650000 | 0 | -44714.47 | 650000 | 1995929.24 | 207.1% | 1995929.24 | 0 | 0 | 0 | 16.45% | -26.68% | 0 | 101.5% | 36765.83 | 71.06% | 0 | 1
CAP/L | 13058 | IS/IT Project for NASA | Completed | CFA | Liu Min | Tao Yang | 2013-05-13 | 2014-07-01 | 2014-12-22 | 0 | N | ZNIC.013058 | NZNIC013058K |  | 13058 | 10180000 | 2092000 | 10453379 | 827631.42 | 0 | -1839306.56 | 0 | 10180000 | 0 | 0 | 12272000 | 827631.42 | -93.26% | 827631.42 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CCP/A | 13054 | Add 2000m3 EDA Tank in RTTF | Completed | CTE/P | Jiang Hao/Liu Xiaoli | Xu Yefeng/Zong Baorong | 2014-02-27 | 2015-05-05 | 0 | 0 | T_2015 | ZNIC.013054 | NZNIC013054K |  | 13054 | 15880000 | 0 | 17551322 | 991416.14 | 0 | -517624.15 | -720912.5 | 15880000 | 0 | 24293.1 | 15880000 | 1040416.14 | -93.45% | 991416.14 | 0 | 49000 | 0 | 37.81% | -30.24% | 0 | 266.8% | 0 | 409.7% | 0 | 1
CBP/P | 13016 | MarkV Upgrade of Gas Turbines Control System, Power Plant | On Going | CTA/U | Lei Yufa | He Zhengyu | 2013-02-01 | 0 | 0 | 0 | N | ZNIC.013016 | NZNIC013016K |  | 13016 | 18000000 | 0 | 18075872 | 23104108.17 | 120000 | 460845 | -267896.5 | 18000000 | -11812114.81 | 6127161.64 | 18000000 | 11411993.36 | -36.6% | 23104108.17 | 120000 | 0 | -11812114.81 | -38.98% | 4.953% | 460845 | 29.1% | 0 | 189.3% | 0 | 0
CBP/C | 12137 | Replace Radiant Section Tubes for 7 Liquid Furnaces | Completed | CTE/P | Zhou Yanduo | Tong Shaojian | 2013-04-17 | 2015-12-02 | 0 | 0 | T | ZNIC.012137 | NZNIC012137K |  | 12137 | 58500000 | 0 | 63756970 | 359673.87 | 794339.62 | 21414.34 | 1324100.36 | 58500000 | 53732809.9 | 2051891.91 | 58500000 | 55102593.39 | -5.808% | 359673.87 | 794339.62 | 215770 | 53732809.9 | 1.451% | -16.68% | 21414.34 | 93.43% | 1324100.36 | 44.53% | 0 | 27
CBP/B | 12119 | Add a Filter to Remove Metal Ions from IBOL | Completed | CTE/P | Sun Aihong | Ling Taizhong | 2013-03-26 | 2014-05-22 | 2015-07-31 | 0 | N | ZNIC.012119 | NZNIC012119K |  | 12119 | 1570000 | 0 | 1571500 | 0 | 0 | -172047.53 | -78710.57 | #N/A | 0 | #N/A | 1570000 | 1500 | -99.9% | 0 | 0 | 1500 | 0 | #N/A | -23.81% | 0 | 177.8% | 0 | 154.3% | 0 | 7
CBP/B | 12071 | Add Raffinate I Washer Column System in BD Plant | Completed | CTE/P | Cao Lin | Wang Yuncai | 2013-09-09 | 2014-10-27 | 0 | 0 | T_2015 | ZNIC.012071 | NZNIC012071K |  | 12071 | 8622000 | 0 | 8824040 | 0 | 0 | -1043844.15 | -535306.12 | 8622000 | 0 | -75000.21 | 8622000 | 0 | -100% | 0 | 0 | 0 | 0 | 9.063% | -10.71% | 0 | 251.6% | 0 | 159.9% | 2 | 10
CTS/P | 12044 | Cooling Water Expansion from PP to Syngas | Completed | CTE/P | Sun Duoxun | Wu Zefei | 2014-05-05 | 2015-04-27 | 0 | 0 | T_2015 | ZNIC.012044 | NZNIC012044K |  | 12044 | 3830000 | 0 | 3834800 | 0 | 0 | -61072.5 | -40305.81 | 3830000 | 0 | 1054974.68 | 3830000 | 0 | -100% | 0 | 0 | 0 | 0 | -40.93% | -19.64% | 0 | 128.8% | 0 | 128.9% | 0 | 1
CBP/M | 11229 | Revamp Dosing System of Cooling System of EB/SM | Completed | CTE/P | Zhu Jianxin | Ling Taizhong | 2014-03-11 | 2015-05-09 | 0 | 0 | H | ZNIC.011229 | NZNIC011229K |  | 11229 | 1099000 | 0 | 1101000 | 0 | 0 | -191656.98 | -142193.85 | 1099000 | 0 | 224642.99 | 1099000 | 2000 | -99.82% | 0 | 0 | 2000 | 0 | -1.282% | -38.3% | 0 | 185.2% | 0 | 180.8% | 2 | 6
Note on A1: Bianlin Zhang: Pls Refer to header's postil if you feel puzzled with the meaning of number.
Note on AB2: bianlin zhang: for the closed ones,this is final cost,or is Estimated final cost
Note on AG2: bianlin zhang: Including unissued PR,unissued SSR and unsettled internal manhour
Note on AH2: bianlin zhang: =(PO-PR)/PR
Note on AI2: bianlin zhang: =(SES actual-SES budget)/SES budget
Note on AE3: bianlin zhang: Unsettled PR/PO cost
Note on AF3: bianlin zhang: Unsettled SSR cost

## Sheet6 (hidden)
Cost Overview for Projects
B.U. | Job | Project Title | Job Status | Lead By | P.M. | C.M. | Approval Date | Hiden Information | [17 empty] | Approved Budget 1 | Estimated Final Cost 5=2+3+4 | Devi.(%) (5-1)/1 | Actual 2 | Committed 3 |  | Cost to complete 4 | Devi.(%) _POPR | Devi.(%) _SSR | Internal Engineering Cost |  | Internal Const.Supervsn Cost |  | Wrong Booking Indicator
[8 empty] | M.C.Date | TCCC Date | Business Closure Date | Priority | WBS Account | Netowrk | Actual Cost Migrated? | Job No. | Original Budget | Budget Change | Final cost | Actual cost | Commitment | Rem.M.H (Eng) | Rem.M.H (Con.Sup) | Budget(used to calculate C2C) | Cost to complete | Saved Cost |  |  |  |  | PR/PO | SSR |  |  |  | Rem M.H. /RMB | Compl (%) | Rem M.H. /RMB | Compl (%) | Material | SSR
CBP/C | 15292 | Modification of the Furnace Burners | On Going | CTE/P | Ding Juntao | 0 | 42369 | 0 | 0 | 0 | N | ZNIC.011312 | NZNIC015292K |  | 15292 | 0 | 0 | 0 | 0 | 2560000 | 90000 | 0 | 0 | -2650000 | 0 | 0 | -90000 | #DIV/0! | 0 | 2560000 | 0 | -2650000 | #DIV/0! | #DIV/0! | 90000 | 0 | 0 | #DIV/0! | 0 | 0
CEP/L | 15278 | Upgrade the HIPS Palletizer | On Going | CTE/P | Zhou Yanduo | Wu Zefei | 42368 | 0 | 0 | 0 | N | ZNIC.011307 | NZNIC015278K |  | 15278 | 1826000 | 0 | 0 | 0 | 1300000 | 117000 | 97000 | 1826000 | 312000 | 0 | 1826000 | 1612000 | -0.1172 | 0 | 1300000 | 0 | 312000 | #DIV/0! | #DIV/0! | 117000 | 0 | 97000 | 0 | 0 | 0
CTE | 15277 | Add New Road Lamps at 5# Gate and ChengPin Road | On Going | CTE/A | Bian Jiacai | Sun Zhongpin | 42360 | 0 | 0 | 0 | N | ZNIF.623100.15.01 | NZNIC015277K |  | 15277 | 538000 | 0 | 16500 | 0 | 0 | 0 | 0 | 538000 | 538000 | 0 | 538000 | 538000 | 0 | 0 | 0 | 0 | 538000 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CBP/U | 15267 | Add a Pressure Control valve on CR Line | On Going | CTE/P | Yu Xiya | Jiang Haijing | 42356 | 0 | 0 | 0 | N | ZNIF.623350.15.01 | NZNIC015267K |  | 15267 | 676000 | 0 | 0 | 0 | 0 | 90000 | 110000 | 676000 | 476000 | 0 | 676000 | 476000 | -0.29586 | 0 | 0 | 0 | 476000 | #DIV/0! | #DIV/0! | 90000 | 0 | 110000 | 0 | 0 | 0
CBP/U | 15263 | Adding Monitoring System for YBS Utility | Completed | CTE/A | Hu Xiao | Sun Zhongpin | 42328 | 42369 | 0 | 0 | H | ZNIF.620051.15.01 | NZNIC015263K |  | 15263 | 478000 | 0 | 770390 | 14152.7 | 86534.19 | 0 | 0 | 478000 | 165376.21 | 81646.9 | 478000 | 396353.1 | -0.17081 | 14152.7 | 86534.19 | 130290 | 165376.21 | -0.40936 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
COA/A | 15256 | Add One Common Spare Motor for GAA Molten Salt Pumps | On Going | CTA/L | Zhu Qiang | N/A | 42297 | 0 | 0 | 0 | N | ZNIC.010728 | NZNIC015256K |  | 15256 | 2750000 | 0 | 2750000 | 0 | 0 | 6000 | 0 | 2750000 | 2744000 | 0 | 2750000 | 2744000 | -0.0021818 | 0 | 0 | 0 | 2744000 | #DIV/0! | #DIV/0! | 6000 | 0 | 0 | #DIV/0! | 0 | 0
COA/A | 15247 | B450/B550 MCC Modification | On Going | CTA/L | Yi Yongjun | Sun Zhongpin | 42285 | 0 | 0 | 0 | H | ZNIC.010582 | NZNIC015247K |  | 15247 | 3500000 | 0 | 4610377 | 25300 | 1110376.9 | 109450 | 177250 | 3500000 | 1550400 | 527223.1 | 3500000 | 2686076.9 | -0.23255 | 25300 | 1110376.9 | 0 | 1550400 | -0.32195 | #DIV/0! | 109450 | 0.17083 | 177250 | 0.015278 | 0 | 0
COA/E | 15246 | C7100,C77100,C77400 Raplace the Boken Trays | On Going | CTM/A | Ling Wenqing | Shi Jinsong | 42264 | 0 | 0 | 0 | N | ZNIC.010345 | NZNIC015246K |  | 15246 | 2687000 | 0 | 4141957 | 0 | 1454957.27 | 0 | 0 | 2687000 | 934342.74 | 297699.99 | 2687000 | 2389300.01 | -0.11079 | 0 | 1454957.27 | 0 | 934342.74 | -0.14885 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
COO/A | 15245 | Install Filters on the Bottom Discharge Lines of C2300 and C2500 | On Going | CTE/P | Zhang Bianlin | Jiang Haijin | 42339 | 0 | 0 | 0 | N | ZNIC.011107 | NZNIC015245K |  | 15245 | 1252000 | 0 | 1998000 | 4400 | 669959.87 | 165600 | 130000 | 1252000 | 199463.08 | 82577.05 | 1252000 | 873822.95 | -0.30206 | 4400 | 669959.87 | 0 | 199463.08 | -0.28665 | #DIV/0! | 165600 | 0.025882 | 130000 | 0 | 0 | 0
CEP/S | 15242 | Relocation the Cable of PS Plant | On Going | CTE/A | Bian Jiacai | Sun Zhongpin | 42334 | 0 | 0 | 0 | N | ZNIC.011082 | NZNIC015242K |  | 15242 | 3196000 | 0 | 3196000 | 9330 | 800000 | 326670 | 198000 | 3196000 | 1862000 | 0 | 3196000 | 2671330 | -0.16416 | 9330 | 800000 | 0 | 1862000 | #DIV/0! | #DIV/0! | 326670 | 0.027768 | 198000 | 0 | 0 | 0
CBP/B | 15198 | Install two CCTVs in BD Plant | On Going | CTE/A | Hu Xiao | Chen Gang | 42305 | 0 | 0 | 0 | N | ZNIF.104500.15.03 | NZNIC015198K |  | 15198 | 217000 | 0 | 337980 | 762.24 | 105748.42 | 0 | 0 | 217000 | 108119.36 | 2369.98 | 217000 | 214630.02 | -0.010922 | 762.24 | 105748.42 | 0 | 108119.36 | -0.019363 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
COO/C | 15197 | Revamping of C1 Flare KO Drums | On Going | CTE/P | Li Shouqing | Jiang Haijin | 42367 | 0 | 0 | 0 | N | ZNIC.011291 | NZNIC015197K |  | 15197 | 1340000 | 0 | 0 | 0 | 115000 | 231550 | 268125 | 1340000 | 725325 | 0 | 1340000 | 840325 | -0.37289 | 0 | 115000 | 0 | 725325 | #DIV/0! | #DIV/0! | 231550 | 0 | 268125 | 0 | 0 | 0
CBL/P | 15180 | Air Conditioning Replacement for Jetty1/2/3 Operation Room | Completed | CTE/C | Wang Wei | Wang Wei | 42271 | 42334 | 0 | 0 | N | ZNIF.604220.15.01 | NZNIC015180K |  | 15180 | 94000 | 0 | 94000 | 10990.54 | 0 | -4675 | 0 | 94000 | 82725 | 284.46 | 94000 | 93715.54 | -0.0030262 | 10990.54 | 0 | 0 | 82725 | #DIV/0! | -0.0431 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CTM | 15176 | Add Card Reader at D700 Central Workshop | On Going | CTE/A | Xu Zheng | 0 | 42247 | 0 | 0 | 0 | N | ZNIF.642320.15.03 | NZNIC015176K |  | 15176 | 0 | 0 | 42094 | 26642.42 | 15811.97 | 14090 | 39000 | 0 | -95177.56 | -366.83 | 0 | -52723.17 | #DIV/0! | 26642.42 | 15811.97 | 0 | -95177.56 | 0.011119 | #DIV/0! | 14090 | 0.49679 | 39000 | 0 | 0 | 0
CEP/S | 15168 | PS Chilling Unit Replacement | On Going | CTE/P | Gu Jingfeng | Wu Zefei | 42328 | 0 | 0 | 0 | N | ZNIC.011038 | NZNIC015168K |  | 15168 | 2910000 | 0 | 4470000 | 18150 | 1560000 | 270050 | 245575 | 2910000 | 816225 | 0 | 2910000 | 2394375 | -0.17719 | 18150 | 1560000 | 0 | 816225 | #DIV/0! | #DIV/0! | 270050 | 0.062977 | 245575 | 0 | 0 | 0
CBP/C | 15167 | Add Adjusters for One of the Furnaces Bottom Air Registers | On Going | CTE/P | Zhou Yanduo | Ling Taizhong | 42368 | 0 | 0 | 0 | N | ZNIC.011308 | NZNIC015167K |  | 15167 | 1490000 | 0 | 0 | 0 | 850000 | 162525 | 145200 | 1490000 | 332275 | 0 | 1490000 | 1182275 | -0.20653 | 0 | 850000 | 0 | 332275 | #DIV/0! | #DIV/0! | 162525 | 0 | 145200 | 0 | 0 | 0
CBP/M | 15149 | Steel Structure Extension of Gas Cylinder Room of CTS/L | On Going | CTE/C | Wang Shicheng | Zhang Zhihe | 42277 | 0 | 0 | 0 | N | ZNIF.660300.15.01 | NZNIC015149K |  | 15149 | 264000 | 0 | 377771 | 91219.39 | 0 | -69360 | -11000 | 264000 | 52847.78 | 1104.83 | 264000 | 262895.17 | -0.004185 | 91219.39 | 0 | 118828 | 52847.78 | -0.049673 | -0.29588 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 1
CBP/C | 15143 | Add Combustible Gas Detector in BCC Cylinder Room | On Going | CTE/A | Gong Feibao | Li Hong | 42307 | 0 | 0 | 0 | N | ZNIF.104100.15.06 | NZNIC015143K |  | 15143 | 70000 | 0 | 74202 | 6600 | 4201.71 | 7400 | 19000 | 70000 | 32214.29 | 584 | 70000 | 43016 | -0.38549 | 6600 | 4201.71 | 0 | 32214.29 | -0.10618 | #DIV/0! | 7400 | 0.47143 | 19000 | 0 | 0 | 0
CBP/B | 15124 | Add Pump and Flow Control Valve on the Line for Sending Dimer to C-250 | On Going | CTE/P | Chen Chen | Ling Taizhong | 42212 | 0 | 0 | 0 | T | ZNIF.104500.15.01 | NZNIC015124K |  | 15124 | 730000 | 0 | 785138 | 144705.94 | 113946.5 | 96600 | 142450 | 730000 | 189717.46 | 42580.1 | 730000 | 448369.9 | -0.38579 | 144705.94 | 113946.5 | 0 | 189717.46 | -0.24213 | #DIV/0! | 96600 | 0.42156 | 142450 | 0.075 | 0 | 0
CTM | 15122 | D700 Garbage Disposal Field Modification | On Going | CTE/C | Xia Qun | Xu Zhaofeng | 42201 | 0 | 0 | 0 | N | ZNIF.642320.15.02 | NZNIC015122K |  | 15122 | 369430 | 0 | 607585 | 52428.77 | 0 | 37355 | 42100 | 369430 | -3673 | 164.23 | 369430 | 289810.77 | -0.21552 | 52428.77 | 0 | 241055 | -3673 | #DIV/0! | -0.08019 | 37355 | 0.52109 | 42100 | 0.19038 | 0 | 1
CBP/C | 15117 | Add the Differential Pressure Signal of the Instrument Air Filter in DCS System | On Going | CTE/P | Zhang Fanwen | Li Hong | 42257 | 0 | 0 | 0 | N | ZNIF.104100.15.04 | NZNIC015117K |  | 15117 | 98000 | 0 | 109219 | 24266 | 11218.88 | -20140 | -1100 | 98000 | 47734 | 14781.12 | 98000 | 83218.88 | -0.15083 | 24266 | 11218.88 | 0 | 47734 | -0.5685 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CEP/E | 15116 | Set a Waste Storage Area beside Tank Farm | On Going | CTE/C | Yan Jun | Xu Zhaofeng | 42236 | 0 | 0 | 0 | H | ZNIF.105600.15.01 | NZNIC015116K |  | 15116 | 382000 | 0 | 475340 | 69271.93 | 9073.97 | 63030 | 98900 | 382000 | 57288.06 | -3483.96 | 382000 | 223553.96 | -0.41478 | 69271.93 | 9073.97 | 87920 | 57288.06 | 0.068732 | #DIV/0! | 63030 | 0.30736 | 98900 | 0.011 | 0 | 0
CBL/P | 15112 | Add Emergency Storage Area for Jettys in CLTF Reserved Land | On Going | CTE/P | Yu Yi | Guo Yibing | 42305 | 0 | 0 | 0 | N | ZNIF.604110.15.01 | NZNIC015112K |  | 15112 | 970000 | 0 | 1584746 | 14195 | 130872 | 10805 | 47000 | 970000 | 283254 | 9128 | 970000 | 903067 | -0.069003 | 14195 | 130872 | 474746 | 283254 | -0.0652 | #DIV/0! | 10805 | 0.5678 | 47000 | 0 | 0 | 0
CTM | 15102 | Cleaning Room Renovation Project of Central Workshop | On Going | CTM/W | Zhai Chunrong | Lei Fucun | 42201 | 0 | 0 | 0 | N | ZNIF.642320.15.01 | NZNIC015102K |  | 15102 | 958000 | 0 | 1566340 | 236387.42 | 41932.48 | -11457.15 | 44000 | 958000 | 6210.83 | 55008.77 | 958000 | 858991.23 | -0.10335 | 236387.42 | 41932.48 | 574460.5 | 6210.83 | -0.37362 | -0.1453 | 0 | 1.067 | 44000 | 0 | 0 | 1
CBP/M | 15097 | Improve Operation Method for Compound TBC | On Going | CTE/P | Wang Can | Ling Taizhong | 42361 | 0 | 0 | 0 | N | ZNIF.104400.15.01 | NZNIC015097K |  | 15097 | 598000 | 0 | 0 | 0 | 70000 | 183000 | 142000 | 598000 | 203000 | 0 | 598000 | 273000 | -0.54348 | 0 | 70000 | 0 | 203000 | #DIV/0! | #DIV/0! | 183000 | 0 | 142000 | 0 | 0 | 0
CBP/C | 15091 | Add a New Solid Waste Storage Area | Canceled | CTE/C | Wang Shicheng | Zhang Zhihe | 42345 | 0 | 0 | 0 | N | ZNIF.104100.15.08 | NZNIC015091K |  | 15091 | 257000 | 0 | 0 | 0 | 0 | 47000 | 56000 | 257000 | 154000 | 0 | 257000 | 154000 | -0.40078 | 0 | 0 | 0 | 154000 | #DIV/0! | #DIV/0! | 47000 | 0 | 56000 | 0 | 0 | 0
CBP/C | 15089 | Modify Lubrication oil Room and Spare Parts Stroge Room at West of Control Building | On Going | CTE/C | Wang Shicheng | Zhang Zhihe | 42345 | 0 | 0 | 0 | N | ZNIF.104100.15.07 | NZNIC015089K |  | 15089 | 752000 | 0 | 0 | 0 | 3000 | 122000 | 94000 | 752000 | 533000 | 0 | 752000 | 536000 | -0.28723 | 0 | 3000 | 0 | 533000 | #DIV/0! | #DIV/0! | 122000 | 0 | 94000 | 0 | 0 | 0
CTM | 15079 | Fire Alarm System Modification for #5 Warehouse in East Laydown | On Going | CTE/A | Bian Jiacai | Sun Zhongpin | 42209 | 0 | 0 | 0 | N | ZNIF.641330.15.01 | NZNIC015079K |  | 15079 | 220000 | 0 | 262386 | 56014.01 | 9442.28 | -37045 | -2475 | 220000 | 76839.18 | 8654.53 | 220000 | 211345.47 | -0.039339 | 56014.01 | 9442.28 | 69050 | 76839.18 | -0.22191 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CEP/P | 15071 | Build a Spare Part&Tool Warehouse | On Going | CTE/C | Gao Feng | Xia Weiguang | 42298 | 0 | 0 | 0 | H | ZNIC.010748 | NZNIC015071K |  | 15071 | 1222000 | 0 | 1499847 | 68750 | 7683.76 | 119350 | 129250 | 1222000 | 333303.24 | 200 | 1222000 | 973200 | -0.2036 | 68750 | 7683.76 | 563463 | 333303.24 | -0.2 | #DIV/0! | 119350 | 0.3655 | 129250 | 0 | 0 | 0
CBL/P | 15066 | Add On-line Water Analyzer on the NAP Unloading Piping of Jetty 4# | On Going | CTE/A | Xu Ge | Wang Xinwu | 42247 | 0 | 0 | 0 | N | ZNIF.651130.15.01 | NZNIC015066K |  | 15066 | 547000 | 0 | 816231 | 35790.48 | 271713.5 | 39800 | 34500 | 547000 | 174235.82 | -15039.8 | 547000 | 487739.8 | -0.10834 | 35790.48 | 271713.5 | 6000 | 174235.82 | 0.049658 | #DIV/0! | 39800 | 0.32542 | 34500 | 0.32353 | 0 | 0
CTS | 15061 | BCC Lab Modification | On Going | CTE/C | Yu Yi | Jiang Yunning | 42166 | 0 | 0 | 0 | N | ZNIC.009551 | NZNIC015061K |  | 15061 | 3490000 | 290000 | 6411751 | 66046.96 | 2751631.89 | 75640 | 69300 | 3490000 | 637629.79 | -292248.64 | 3780000 | 3637308.64 | -0.037749 | 66046.96 | 2751631.89 | 182000 | 637629.79 | 0.10031 | #DIV/0! | 75640 | 0.32253 | 69300 | 0.26744 | 0 | 1
C | 15051 | Set Up Intranet Portal System | On Going | CGA/I | Tao Yang | Tao Yang | 42081 | 0 | 0 | 0 | N | ZNIT.001180 | NZNIC015051K |  | 15051 | 2735000 | 0 | 4659799 | 239017.94 | 1919138.84 | 0 | 0 | 2735000 | 576843.22 | 0 | 2735000 | 2735000 | 0 | 239017.94 | 1919138.84 | 0 | 576843.22 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CBP/P | 15047 | Change New CEMS | On Going | CTA/S | Tang Yiqun | Tang Yiqun | 42073 | 0 | 0 | 0 | N | ZNIC.008734 | NZNIC015047K |  | 15047 | 1203000 | 0 | 1344000 | 852242.9 | 17295.75 | 5500 | 0 | 1203000 | 21729.14 | 206232.21 | 1203000 | 991267.79 | -0.176 | 852242.9 | 17295.75 | 100000 | 21729.14 | -0.16645 | -0.32174 | 5500 | 0 | 0 | #DIV/0! | 0 | 0
CBP/C | 15042 | Add On-line Analyzer on the Outlet of the Z-908 | On Going | CTE/A | Gong Feibao | Li Hong | 42298 | 0 | 0 | 0 | H | ZNIC.010800 | NZNIC015042K |  | 15042 | 1145000 | 0 | 1732778 | 72640 | 414580.35 | 148435 | 105300 | 1145000 | 283403.65 | 120641 | 1145000 | 770624 | -0.32697 | 72640 | 414580.35 | 0 | 283403.65 | -0.19918 | #DIV/0! | 148435 | 0.27193 | 105300 | 0.14041 | 0 | 0
CBP/C | 15036 | Expand the Capacity of the Suspect Condensate Vent Condenser 390-E-920 | Completed | CTE/P | Ding Juntao | Tong Shaojian | 42135 | 42293 | 0 | 0 | H | ZNIF.104100.15.02 | NZNIC015036K |  | 15036 | 398000 | 0 | 398000 | 184174.06 | 0 | 57450 | 28000 | 398000 | 94429.67 | 33946.27 | 398000 | 278603.73 | -0.29999 | 184174.06 | 0 | 0 | 94429.67 | -0.22323 | -0.071117 | 57450 | 0.57757 | 28000 | 0 | 0 | 0
CBP/C | 15034 | Add Pressure&Temperature Signal DCS System for Three Drums at AEU Section | On Going | CTE/A | Gong Feibao | Li Hong | 42265 | 0 | 0 | 0 | N | ZNIF.104100.15.05 | NZNIC015034K |  | 15034 | 170000 | 0 | 193852 | 5856.45 | 23578.39 | 0 | -550 | 170000 | 134053.76 | 6511.4 | 170000 | 163488.6 | -0.038302 | 5856.45 | 23578.39 | 0 | 134053.76 | -0.21448 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CEP/P | 15028 | Upgrade 4 sets PO Cupboard Freezer | On Going | CTE/P | Ding Juntao | Wang Yuncai | 42296 | 0 | 0 | 0 | T | ZNIC.010799 | NZNIC015028K |  | 15028 | 1319000 | 0 | 2129000 | 25090 | 673943.73 | 122310 | 50050 | 1319000 | 426120.43 | 21485.84 | 1319000 | 1125154.16 | -0.14696 | 25090 | 673943.73 | 0 | 426120.43 | -0.026526 | #DIV/0! | 122310 | 0.14469 | 50050 | 0.080808 | 0 | 0
CEP/S | 15026 | PS Positive Draft of Control Building Modification | On Going | CTE/C | Gao Feng | Wang Wei | 42194 | 0 | 0 | 0 | H | ZNIC.009794 | NZNIC015026K |  | 15026 | 1256000 | 0 | 2062440 | 121067.89 | 789459.83 | 73910.85 | 53350 | 1256000 | 150289.17 | -12216.58 | 1256000 | 1140955.73 | -0.091596 | 121067.89 | 789459.83 | 80138.84 | 150289.17 | 0.013328 | -0.056604 | 73910.85 | 0.52682 | 53350 | 0.19167 | 0 | 1
COA/S | 15024 | SAP Steam System Energy Saving Modification | On Going | CTE/P | Xu Jin | Wang Yuncai | 42265 | 0 | 0 | 0 | N | ZNIC.010440 | NZNIC015024K |  | 15024 | 1419000 | 0 | 1559598 | 54300.76 | 127648.57 | 132100 | 196900 | 1419000 | 878033.75 | 27516.92 | 1419000 | 1062483.08 | -0.25125 | 54300.76 | 127648.57 | 2500 | 878033.75 | -0.15464 | #DIV/0! | 132100 | 0.12978 | 196900 | 0.057895 | 0 | 0
CEP/E | 15022 | Revamp HVAC System in EOEG Control Building | Completed | CTE/C | Gao Feng | Wang Wei | 42131 | 42342 | 0 | 0 | H | ZNIC.009264 | NZNIC015022K |  | 15022 | 1391000 | 0 | 1473957 | 1035368.41 | 13711.11 | 56686.99 | 4950 | 1391000 | 434789.08 | -164661.59 | 1391000 | 1494024.6 | 0.074065 | 1035368.41 | 13711.11 | 10156 | 434789.08 | 0.19387 | 0.10522 | 56686.99 | 0.60959 | 4950 | 0.91964 | 0 | 4
CTS | 15016 | Environmental Monitoring Car | On Going | CTS/E | Fan Chenxi | Fan Chenxi | 42017 | 0 | 0 | 0 | N | ZNIC.008204 | NZNIC015016K |  | 15016 | 4000000 | 0 | 4542735 | 0 | 4542735.05 | 0 | 0 | 4000000 | 272264.96 | -815000.01 | 4000000 | 4815000.01 | 0.20375 | 0 | 4542735.05 | 0 | 272264.96 | 0.18111 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CEP/L | 15014 | PS A915 Emergency Lighting and Fire Alarm System Modification | Completed | CTE/A | Xu Zheng | Zhang Pu | 42067 | 42269 | 0 | 0 | N | ZNIF.175410.15.01 | NZNIC015014K |  | 15014 | 434000 | 0 | 474825 | 464825.16 | 0 | 12220 | 30050 | 434000 | 0 | -31728.64 | 434000 | 474825.16 | 0.094067 | 464825.16 | 0 | 10000 | 0 | 0.28516 | -0.02225 | 12220 | 0.84333 | 30050 | 0.61962 | 0 | 0
CTM | 15011 | Modification for Main Door of Spare Parts Warehouse | On Going | CTE/C | Yu Yi | Xu Zhaofeng | 42216 | 0 | 0 | 0 | N | ZNIF.641330.15.02 | NZNIC015011K |  | 15011 | 384000 | 0 | 626000 | 6520 | 242000 | 46480 | 43000 | 384000 | 58000 | -12000 | 384000 | 306520 | -0.20177 | 6520 | 242000 | 0 | 58000 | 0.052174 | #DIV/0! | 46480 | 0.12302 | 43000 | 0 | 0 | 0
COA/E | 15010 | Replace the Material of P7120A/B by PFA | On Going | CTE/P | Xu Jin | Wu Zefei | 42226 | 0 | 0 | 0 | T | ZNIF.106200.15.01 | NZNIC015010K |  | 15010 | 495000 | 0 | 722707 | 47555 | 227706.96 | 51995 | 54450 | 495000 | 99710.18 | 13582.86 | 495000 | 374972.14 | -0.24248 | 47555 | 227706.96 | 0 | 99710.18 | -0.04851 | #DIV/0! | 51995 | 0.4748 | 54450 | 0.01 | 0 | 0
CEP/E | 15009 | Modify Suction Side of P4330 | On Going | CTE/P | Gu Jingfeng | Wu Zefei | 42139 | 0 | 0 | 0 | T | ZNIF.105700.15.01 | NZNIC015009K |  | 15009 | 590000 | 0 | 672139 | 248275.91 | 19205.38 | 47245 | 75600 | 590000 | 142540.68 | 57133.03 | 590000 | 410021.97 | -0.30505 | 248275.91 | 19205.38 | 0 | 142540.68 | -0.27897 | #DIV/0! | 47245 | 0.70472 | 75600 | 0.055 | 0 | 0
COA/A | 15004 | Revamp HVAC System in B550 Control Building | Completed | CTE/C | Gao Feng | Wang Wei | 42131 | 42253 | 0 | 0 | H | ZNIC.009265 | NZNIC015004K |  | 15004 | 1564000 | 0 | 1577128 | 1011375.73 | 0 | 70660 | 33550 | 1564000 | 0 | 223669.2 | 1564000 | 1019375.73 | -0.34823 | 1011375.73 | 0 | 8000 | 0 | -0.21915 | -0.04829 | 70660 | 0.56597 | 33550 | 0.52344 | 0 | 1
CBP/C | 14313 | Replace Existing Electrical Heater H-520 | On Going | CTE/A | Hu Xiao | Chen Gang | 42139 | 0 | 0 | 0 | N | ZNIC.009347 | NZNIC014313K |  | 14313 | 1885000 | 0 | 2957457 | 58390 | 1072456.67 | 59860 | 63800 | 1885000 | 579446.14 | 51047.19 | 1885000 | 1710292.81 | -0.092683 | 58390 | 1072456.67 | 0 | 579446.14 | -0.047708 | #DIV/0! | 59860 | 0.49378 | 63800 | 0 | 0 | 0
CBP/M | 14312 | Replace Exchanger E2320 of EB/SM | Completed | CTM/M | Chu Chao | Chu Chao | 41997 | 42154 | 0 | 0 | T_2015 | ZNIC.008125 | NZNIC014312K |  | 14312 | 2160000 | 0 | 2160000 | 1716239.32 | 0 | 13750 | 0 | 2160000 | 0 | 0 | 2160000 | 1716239.32 | -0.20544 | 1716239.32 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 13750 | 0 | 0 | #DIV/0! | 0 | 0
CEP/E | 14311 | Change New C2450/CX2450/E1250A/E1250B/E1252 | Completed | CTM/E | Wang Zhigao | Wang Zhigao | 41997 | 42128 | 0 | 0 | T_2015 | ZNIC.008124 | NZNIC014311K |  | 14311 | 1675000 | 487000 | 2061290 | 2061289.79 | 0 | 8000 | 8000 | 1675000 | 0 | 0 | 2162000 | 2061289.79 | -0.046582 | 2061289.79 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 8000 | 0 | 8000 | 0 | 0 | 0
COA/S | 14309 | Add Extrusion Step for New Product AGM7 | On Going | CTE/P | Zhu Jianxin | Cao Yongbin | 42096 | 0 | 0 | 0 | H | ZNIC.008120 | NZNIC014309K |  | 14309 | 27782000 | 0 | 51729014 | 4764929.34 | 21832964.62 | 144197.92 | 1280575 | 27782000 | -3814277.86 | 1880610.98 | 27782000 | 24476616.1 | -0.11898 | 4764929.34 | 21832964.62 | 1693000 | -3814277.86 | -0.075334 | -0.17611 | 144197.92 | 0.869 | 1280575 | 0.089369 | 0 | 3
CBP/M | 14308 | Modification of EB/SM Cooling Water Pumps | On Going | CTE/P | Wang Lifen | Ling Taizhong | 42107 | 0 | 0 | 0 | N | ZNIC.009023 | NZNIC014308K |  | 14308 | 1357000 | 0 | 1673033 | 1044929.1 | 2600 | -1025 | 57725 | 1357000 | -65676.04 | 79388.94 | 1357000 | 1219886.06 | -0.10104 | 1044929.1 | 2600 | 238033 | -65676.04 | -0.075353 | #DIV/0! | 0 | 1.0076 | 57725 | 0.57241 | 0 | 2
CBP/M | 14307 | Replacement of F2404 | Completed | CTM/M | Chu Chao | Chu Chao | 41992 | 42154 | 0 | 0 | T_2015 | ZNIF.104400.14.04 | NZNIC014307K |  | 14307 | 192000 | 0 | 192000 | 0 | 0 | 8000 | 0 | 192000 | 0 | 0 | 192000 | 0 | -1 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 8000 | 0 | 0 | #DIV/0! | 0 | 0
CBP/M | 14306 | Replacement of F2406 | Completed | CTM/M | Chu Chao | Chu Chao | 41992 | 42125 | 0 | 0 | T_2015 | ZNIF.104400.14.03 | NZNIC014306K |  | 14306 | 210000 | 0 | 210000 | 0 | 0 | 8000 | 0 | 210000 | 0 | 0 | 210000 | 0 | -1 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 8000 | 0 | 0 | #DIV/0! | 0 | 0
CBP/M | 14305 | Replacement of E1203 | Completed | CTM/M | Chu Chao | Chu Chao | 41991 | 42155 | 0 | 0 | T_2015 | ZNIF.104400.14.02 | NZNIC014305K |  | 14305 | 224000 | 0 | 224000 | 0 | 0 | 8000 | 0 | 224000 | 0 | 0 | 224000 | 0 | -1 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 8000 | 0 | 0 | #DIV/0! | 0 | 0
COA/A | 14296 | Install Filters at Outlet of P9326/P9526 | Completed | CTE/P | Xu Jin | Wu Zefei | 42096 | 42342 | 0 | 0 | N | ZNIF.106600.15.01 | NZNIC014296K |  | 14296 | 830000 | 0 | 955432 | 499820.89 | 0 | 25465 | -20175 | 830000 | -47744.53 | 255348.64 | 830000 | 549186.36 | -0.33833 | 499820.89 | 0 | 97110 | -47744.53 | -0.45678 | -0.15597 | 25465 | 0.83247 | 0 | 1.3011 | 0 | 0
CBP/M | 14288 | T2401 Replace Structure Packing of EB/SM | Completed | CTM/M | Chu Chao | Chu Chao | 41974 | 42155 | 0 | 0 | T_2015 | ZNIC.007947 | NZNIC014288K |  | 14288 | 2645000 | 0 | 2645000 | 2330341.89 | 0 | 13750 | 27500 | 2645000 | 0 | 177495.99 | 2645000 | 2330341.89 | -0.11896 | 2330341.89 | 0 | 0 | 0 | -0.061121 | #DIV/0! | 13750 | 0 | 27500 | 0 | 0 | 0
CEP/P | 14287 | Add a Differential Pressure Transmitter in Control Room | Completed | CTE/A | Xu Ge | Li Xueyong | 42011 | 42174 | 0 | 0 | N | ZNIF.678152.15.01 | NZNIC014287K |  | 14287 | 104000 | 0 | 105300 | 58883.38 | 0 | 2471.78 | 4300 | 104000 | 0 | 2327.87 | 104000 | 58883.38 | -0.43381 | 58883.38 | 0 | 0 | 0 | -0.14295 | -0.24258 | 2471.78 | 0.92276 | 4300 | 0.81304 | 0 | 1
CBP/M | 14286 | Change Gas Chromatograph A24201 to New Type | On Going | CTA/S | Li Huaxin | Li Huaxin | 41970 | 0 | 0 | 0 | N | ZNIF.104400.14.01 | NZNIC014286K |  | 14286 | 480000 | 0 | 480000 | 316000 | 0 | 2000 | 4000 | 480000 | 57720 | 100280 | 480000 | 373720 | -0.22142 | 316000 | 0 | 0 | 57720 | -0.21336 | #DIV/0! | 2000 | 0 | 4000 | 0 | 0 | 0
CTS/U | 14275 | Add Flowmeter on Main Pipeline for HPNG | Completed | CTE/A | Wang Zhen | Wang Xinwu | 41997 | 42352 | 0 | 0 | T_2015 | ZNIC.008123 | NZNIC014275K |  | 14275 | 1151000 | 0 | 1141315 | 1115658.21 | 0 | -41380 | -137100.49 | 1151000 | -77317 | 32658.79 | 1151000 | 1118341.21 | -0.028374 | 1115658.21 | 0 | 80000 | -77317 | -0.04335 | -0.0060412 | 0 | 1.4649 | 0 | 2.4742 | 0 | 3
CBP/C | 14262 | Revamp HVAC System in BCC Control Building | Completed | CTE/C | Gao Feng | Wang Wei | 42131 | 42276 | 0 | 0 | H | ZNIC.009263 | NZNIC014262K |  | 14262 | 1216000 | 0 | 2093170 | 272607.06 | 835675.21 | -91445 | 35750 | 1216000 | 0 | -39482.04 | 1216000 | 1147477.27 | -0.056351 | 272607.06 | 835675.21 | 39195 | 0 | 0.036542 | -0.062373 | 0 | 4.137 | 35750 | 0.29348 | 0 | 0
CGA | 14255 | Add a Pair of Card Reader on the West Side Door of Visitor Center for Personnel Access Control | Completed | CTA/S | Dai Xiaolong | Qiu Wei | 41941 | 42124 | 0 | 0 | N | ZNIF.632000.14.01 | NZNIC014255K |  | 14255 | 35000 | 0 | 35000 | 23850.88 | 0 | -7900 | 4899.25 | 35000 | 0 | 4790.92 | 35000 | 23850.88 | -0.31855 | 23850.88 | 0 | 0 | 0 | 0.0050013 | -0.40562 | 0 | 4.95 | 4899.25 | 0.18346 | 0 | 1
COO/C | 14252 | Supply DMA from C1 Plant to BSNJ | Completed | CTE/P | Sun Duoxun/Liu Xiaoli | Xu Yefeng | 41995 | 42246 | 0 | 0 | T_2015 | ZNIC.008115 | NZNIC014252K |  | 14252 | 1767000 | 0 | 2019104 | 1429212.63 | 215773.95 | -16820 | -174931.56 | 1767000 | 0 | 328005.39 | 1767000 | 1654986.58 | -0.063392 | 1429212.63 | 215773.95 | 10000 | 0 | -0.23624 | -0.22417 | 0 | 1.0833 | 0 | 1.866 | 0 | 1
CBL/O | 14251 | Build a Operation Rest Room for ACN Loading Station | On Going | CTE/C | Yu Yi | Xu Zhaofeng | 42222 | 0 | 0 | 0 | N | ZNIF.412790.15.01 | NZNIC014251K |  | 14251 | 338000 | 0 | 395234 | 15805 | 31139.76 | 47195 | 44000 | 338000 | 178675.22 | -4844.98 | 338000 | 251649.98 | -0.25547 | 15805 | 31139.76 | 26030 | 178675.22 | 0.18251 | #DIV/0! | 47195 | 0.25087 | 44000 | 0 | 0 | 0
CBP/C | 14243 | Add a C5 Raffinate Pipe from YUANGANG Company to C5 Hydrogenation Reactor | Completed | CTE/P | Cao Lin | Ling Taizhong | 42089 | 42253 | 0 | 0 | N | ZNIC.008902 | NZNIC014243K |  | 14243 | 3720000 | 0 | 3777568 | 2919128.48 | 0 | 7345 | -56535.9 | 3720000 | 0 | 1988.58 | 3720000 | 2976696.48 | -0.19981 | 2919128.48 | 0 | 57568 | 0 | 0.015619 | -0.14349 | 7345 | 0.97441 | 0 | 1.1668 | 0 | 0
COA/L | 14240 | Recover the BA Railway Loading Station | Completed | CTE/P | Zhu Jianxin | Wu Zefei | 41995 | 42314 | 0 | 0 | H | ZNIC.008121 | NZNIC014240K |  | 14240 | 1907000 | 0 | 2176992 | 895845.41 | 3600 | 50540 | 45655.5 | 1907000 | 714445.35 | -8428.26 | 1907000 | 1819232.76 | -0.046024 | 895845.41 | 3600 | 205342 | 714445.35 | 0.05375 | -0.25577 | 50540 | 0.84107 | 45655.5 | 0.77172 | 0 | 0
CEP/E | 14237 | LP Steam Rational Distribution and Utilization | On Going | CTE/P | Gu Jingfeng | Wu Zefei | 42328 | 0 | 0 | 0 | N | ZNIC.011039 | NZNIC014237K |  | 14237 | 1763000 | 0 | 1843000 | 8800 | 401000 | 258200 | 303050 | 1763000 | 791950 | 0 | 1763000 | 1201750 | -0.31835 | 8800 | 401000 | 0 | 791950 | #DIV/0! | #DIV/0! | 258200 | 0.0084485 | 303050 | 0.021314 | 0 | 0
CEP/S | 14235 | Add Safety Facilities for PS Burner Unit | On Going | CTE/A | Xiao Lixuan | Li Xueyong | 42326 | 0 | 0 | 0 | N | ZNIF.105400.15.02 | NZNIC014235K |  | 14235 | 439000 | 0 | 439000 | 9900 | 180000 | 87000 | 49100 | 439000 | 113000 | 0 | 439000 | 302900 | -0.31002 | 9900 | 180000 | 0 | 113000 | #DIV/0! | #DIV/0! | 87000 | 0 | 49100 | 0.1678 | 0 | 0
CAP/E | 14234 | Add Anti-backflow facilities at LP Steam Header of MA/BA Plant | Completed | CTE/P | Zhu Jianxin | Wu Zefei | 41983 | 42124 | 0 | 0 | T_2015 | ZNIF.106300.14.01 | NZNIC014234K |  | 14234 | 893000 | 0 | 918516 | 857151.14 | 23515.86 | -31445 | -12263 | 893000 | 0 | 298340.62 | 893000 | 880667 | -0.013811 | 857151.14 | 23515.86 | 0 | 0 | -0.36642 | -0.18891 | 0 | 1.2003 | 0 | 1.1085 | 0 | 0
COA/E | 14232 | Change the Breath Valve and Add a PSV for T9668 | Completed | CTE/P | Xu Jin | Wang Yuncai | 41963 | 42235 | 0 | 0 | N | ZNIF.106700.14.01 | NZNIC014232K |  | 14232 | 320000 | 0 | 349453 | 349453.42 | 0 | -63340 | -38225 | 320000 | 0 | -16307.6 | 320000 | 349453.42 | 0.092042 | 349453.42 | 0 | 0 | 0 | 0.10928 | -0.108 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CAP/L | 14230 | Add a Shed for A455 Truck Parking Lot | On Going | CTE/C | Yu Yi | Lu Jie | 42256 | 0 | 0 | 0 | N | ZNIC.010285 | NZNIC014230K |  | 14230 | 1410000 | 0 | 1524250 | 48125 | 216717.94 | 64900 | 71500 | 1410000 | 663971.05 | 226440.01 | 1410000 | 1047159.99 | -0.25733 | 48125 | 216717.94 | 118346 | 663971.05 | -0.47175 | #DIV/0! | 64900 | 0.24116 | 71500 | 0.27778 | 0 | 2
CEP/L | 14227 | Rebuild the Existing Holding Device in PS Packing | Completed | CTE/P | Ding Juntao | Wang Yuncai | 41977 | 42184 | 0 | 0 | N | ZNIF.175410.14.01 | NZNIC014227K |  | 14227 | 350000 | 0 | 354290 | 316498.34 | 1500 | -4602.98 | 8150 | 350000 | 0 | -20166.78 | 350000 | 319598.34 | -0.086862 | 316498.34 | 1500 | 1600 | 0 | 0.11964 | -0.23552 | 0 | 1.0606 | 8150 | 0.81889 | 0 | 2
CBL/O | 14226 | Add a Unloading System for PALD in B305 Loading Station | Completed | CTE/P | Yu Xiya | Jiang Haijin | 41976 | 42207 | 0 | 0 | T_2015 | ZNIC.007948 | NZNIC014226K |  | 14226 | 1270000 | 0 | 1280313 | 885593.22 | 0 | 52634 | -36350.12 | 1270000 | 0 | 135139 | 1270000 | 893506.22 | -0.29645 | 885593.22 | 0 | 7913 | 0 | -0.177 | -0.25226 | 52634 | 0.768 | 0 | 1.2153 | 0 | 1
CBP/S | 14222 | Add H2 Pipeline to BSNJ from Syngas Plant | Completed | CTE/P | Cao Lin | Ling Taizhong | 42011 | 42277 | 0 | 0 | N | ZNIC.008171 | NZNIC014222K |  | 14222 | 1130000 | 559000 | 2285508 | 1715110.23 | 17.09 | -95320 | -76293.77 | 1689000 | 0 | 69393.75 | 1689000 | 1740127.32 | 0.030271 | 1715110.23 | 17.09 | 25000 | 0 | -0.010545 | -0.064106 | 0 | 1.5519 | 0 | 1.2529 | 0 | 1
CBP/S | 14218 | Modify Antisurge Control System of K1401 | Completed | CTA/M | Cheng Guiyou | Gan Shuangfeng | 41866 | 42116 | 42128 | 0 | T_2015 | ZNIC.014218 | NZNIC014218K |  | 14218 | 1000000 | 0 | 1008800 | 782229.91 | 8800 | 3300 | 0 | 1000000 | 0 | 44791.01 | 1000000 | 791029.91 | -0.20897 | 782229.91 | 8800 | 0 | 0 | -0.046657 | #DIV/0! | 3300 | 0 | 0 | #DIV/0! | 0 | 0
COA/A | 14207 | Let-down MP Steam to LP Steam in GAA Plant | On Going | CTE/P | Zhu Jianxin | Wu Zefei | 42265 | 0 | 0 | 0 | T_2015 | ZNIC.010379 | NZNIC014207K |  | 14207 | 2362000 | 0 | 3206055 | 607640.92 | 563929.76 | -119335 | -44890 | 2362000 | 313946.31 | 449579.81 | 2362000 | 1912420.19 | -0.19034 | 607640.92 | 563929.76 | 426903.2 | 313946.31 | -0.28134 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CBP/S | 14200 | Add Control Valve at 1st Stage Inlet Nitrogen Line of K1701 | Completed | CTE/P | Wang Can | Ling Taizhong | 42048 | 41932 | 0 | 0 | N | ZNIF.104300.15.01 | NZNIC014200K |  | 14200 | 155000 | 0 | 174249 | 117753.86 | 0 | -1445 | 11850 | 155000 | 0 | 15654.94 | 155000 | 117753.86 | -0.2403 | 117753.86 | 0 | 0 | 0 | -0.31254 | -0.32281 | 0 | 1.0283 | 11850 | 0.71098 | 0 | 0
CBL/O | 14198 | Replace Manual Loading Arm Z2810&Z4802 with Pneumatic One | On Going | CTE/P | Yu Xiya | Xu Yefeng | 42074 | 0 | 0 | 0 | T | ZNIF.412740.15.01 | NZNIC014198K |  | 14198 | 440000 | 0 | 466800 | 254976.42 | 24000 | 30305 | 32450 | 440000 | 83715.86 | 11752.72 | 440000 | 365492.28 | -0.16934 | 254976.42 | 24000 | 2800 | 83715.86 | -0.048815 | #DIV/0! | 30305 | 0.61147 | 32450 | 0.2625 | 0 | 0
CBL/O | 14197 | Replace Manual Loading Arm Z2203 with Pneumatic One | On Going | CTE/P | Yu Xiya | Xu Yefeng | 42074 | 0 | 0 | 0 | T | ZNIF.651010.15.01 | NZNIC014197K |  | 14197 | 273000 | 0 | 294920 | 158227.76 | 0 | 22215 | 31250 | 273000 | 29837.86 | 10269.38 | 273000 | 209265.62 | -0.23346 | 158227.76 | 0 | 21200 | 29837.86 | -0.083904 | 0.018819 | 22215 | 0.68264 | 31250 | 0.30556 | 0 | 0
COO/O | 14194 | Add a Pump and Two On/off Valves for Val Loading | On Going | CTE/P | Liu Xiaoli | Jiang Haijin | 42314 | 0 | 0 | 0 | N | ZNIC.010907 | NZNIC014194K |  | 14194 | 1260000 | 0 | 1412808 | 24200 | 126687.65 | 302500 | 238150 | 1260000 | 547914.81 | 20547.54 | 1260000 | 698802.46 | -0.44539 | 24200 | 126687.65 | 0 | 547914.81 | -0.12684 | #DIV/0! | 302500 | 0 | 238150 | 0.092243 | 0 | 0
CBP/C | 14187 | Add Pipeline to Send Light Fuel Oil to STT1310 | On Going | CTE/P | Qiu Zhufeng | Ling Taizhong | 41872 | 0 | 0 | 0 | T_2015 | ZNIC.014187 | NZNIC014187K |  | 14187 | 4207000 | 2188000 | 5575289 | 5037001.23 | 531725.06 | 20846.61 | -59019.28 | #N/A | #N/A | #N/A | 6395000 | #N/A | #N/A | 5037001.23 | 531725.06 | 39112 | #N/A | #N/A | -0.16345 | 20846.61 | 0.90016 | 0 | 1.1504 | 0 | 2
CEP/S | 14182 | Rebuilt a Waste Liquid Storage | Completed | CTE/C | Gao Feng | Xia Weiguang | 42131 | 42353 | 0 | 0 | H | ZNIF.105400.15.01 | NZNIC014182K |  | 14182 | 748000 | 0 | 1175500 | 308201.47 | 0 | -78032.96 | -8650 | 748000 | 162600 | 50298.53 | 748000 | 697701.47 | -0.067244 | 308201.47 | 0 | 226900 | 162600 | #DIV/0! | -0.21081 | 0 | 1.5912 | 0 | 1.1802 | 0 | 3
CTM | 14173 | Technical Material Bar-code Management System | On Going | CFA/I | Tao Yang | Wang Jun | 41803 | 0 | 0 | 0 | N | ZNIC.014173 | NZNIC014173K |  | 14173 | 2580000 | 0 | 4873537 | 0 | 2293536.92 | 0 | 0 | 2580000 | 286463.08 | 0 | 2580000 | 2580000 | 0 | 0 | 2293536.92 | 0 | 286463.08 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CEP/E | 14168 | Change an Online TOC Analyzer | On Going | CTA/S | Yong Jie | Yong Jie | 41877 | 0 | 0 | 0 | N | ZNIC.014168 | NZNIC014168K |  | 14168 | 480000 | 0 | 480000 | 348420.96 | 0 | -550 | 8800 | 480000 | 120779.04 | 2000 | 480000 | 469200 | -0.0225 | 348420.96 | 0 | 0 | 120779.04 | -0.005 | #DIV/0! | 0 | 1.0714 | 8800 | 0 | 0 | 0
CBP/C | 14165 | Add Pipe from BYC EBO Ship Loading Pipe to YPC G102 Tank | Completed | CTE/P | Qiu Zhufeng | Ling Taizhong | 41842 | 42151 | 0 | 0 | H | ZNIC.014165 | NZNIC014165K |  | 14165 | 1143000 | 1448000 | 4095032 | 1592582.91 | 1500031.67 | 7680 | -217067.97 | 2591000 | 0 | 1069078.94 | 2591000 | 3096614.58 | 0.19514 | 1592582.91 | 1500031.67 | 4000 | 0 | -0.42154 | -0.21792 | 7680 | 0.82664 | 0 | 2.5755 | 0 | 5
CBL/O | 14163 | Replacement of 3 Low Efficiency Motors in A300 & RTTF | Canceled | CTA/L | Chen Kun | Chen Kun | 41803 | 0 | 0 | 0 | N | ZNIC.014163 | NZNIC014163K |  | 14163 | 87789 | 0 | 87789 | 0 | 0 | 4400 | 35000 | 87789 | 48389 | 0 | 87789 | 48389 | -0.4488 | 0 | 0 | 0 | 48389 | #DIV/0! | #DIV/0! | 4400 | 0 | 35000 | 0 | 0 | 0
CBP/C | 14151 | Add New Pan Oil Pipe from Pan oil Pump to Ethylene Bottom Oil Pipe | Completed | CTE/P | Sun Aihong | Ling Taizhong | 42017 | 42352 | 0 | 0 | T_2015 | ZNIF.104100.15.01 | NZNIC014151K |  | 14151 | 410000 | 0 | 483095 | 374983.24 | 0 | -1425 | -36825 | 410000 | -18537.02 | 51553.78 | 410000 | 358446.22 | -0.12574 | 374983.24 | 0 | 2000 | -18537.02 | -0.11893 | -0.41125 | 0 | 1.0183 | 0 | 1.4976 | 0 | 0
All | 14149 | BYC Electrical Monitoring & Control System (EMCS) Migration | Completed | CTA/VO | Gu Hemei | Sun Zhongpin | 41795 | 42114 | 42306 | 0 | T_2015 | ZNIC.014149 | NZNIC014149K |  | 14149 | 9740000 | 0 | 9742700 | 7151007.15 | 0 | -376977.24 | -47306 | 9740000 | 0 | 1289086.73 | 9740000 | 7151007.15 | -0.26581 | 7151007.15 | 0 | 0 | 0 | -0.14725 | -0.16389 | 0 | 2.6799 | 0 | 1.8777 | 0 | 3
CEP/S | 14144 | Add PIB Tank and Feed System in HIPS Plant | On Going | CTE/P | Gu Jingfeng | Wu Zefei | 41981 | 0 | 0 | 0 | H | ZNIC.008007 | NZNIC014144K |  | 14144 | 6240000 | 0 | 10167086 | 2987057.18 | 2850148.21 | -96586.63 | -140434.6 | 6240000 | -670510.33 | 165282.94 | 6240000 | 6074717.06 | -0.026488 | 2987057.18 | 2850148.21 | 908022 | -670510.33 | -0.028385 | -0.22695 | 0 | 1.1857 | 0 | 1.3794 | 1 | 8
CBL/P | 14141 | Add a Manual Sampler on the NAP Feed Piping from YPC | On Going | CTE/P | Li Shouqing | Jiang Haijin | 42083 | 0 | 0 | 0 | N | ZNIF.604170.15.01 | NZNIC014141K |  | 14141 | 497000 | 0 | 600931 | 298326.77 | 95439.15 | 9805 | 24825 | 497000 | 138245.09 | -121441.01 | 497000 | 583811.01 | 0.17467 | 298326.77 | 95439.15 | 51800 | 138245.09 | 0.68971 | #DIV/0! | 9805 | 0.90662 | 24825 | 0.63493 | 0 | 0
CBP/A | 14126 | Add ESD Interlock Signal and Block Valve for 410-R101A/B | Completed | CTE/A | Gong Feibao | Li Hong | 41857 | 42123 | 0 | 0 | T_2015 | ZNIC.014126 | NZNIC014126K |  | 14126 | 191000 | 0 | 207000 | 194143.69 | 0 | -23330 | -4403 | 191000 | 0 | 7768.2 | 191000 | 194143.69 | 0.016459 | 194143.69 | 0 | 0 | 0 | -0.047198 | -0.44344 | 0 | 1.8317 | 0 | 1.1417 | 0 | 0
CBP/C | 14121 | H109 Convection Section Modification | Completed | CTE/P | Zhou Yanduo | Ling Taizhong | 41850 | 42151 | 42193 | 0 | T_2015 | ZNIC.014121 | NZNIC014121K |  | 14121 | 16490000 | 0 | 16492000 | 15521887.68 | 0 | 18180 | -193590.96 | 16490000 | 0 | 13222412.33 | 16490000 | 15523887.68 | -0.058588 | 15521887.68 | 0 | 2000 | 0 | -0.83155 | 0.01553 | 18180 | 0.90044 | 0 | 1.623 | 0 | 0
CBP/M | 14115 | Replacement of 16 Low Efficiency Motors in EB/SM Plant | Completed | CTA/M | Lv Yong | Lv Yong | 41808 | 42199 | 0 | 0 | N | ZNIC.014115 | NZNIC014115K |  | 14115 | 873000 | 0 | 875000 | 352861.92 | 2000 | 0 | 138240 | 873000 | 0 | 146828.34 | 873000 | 354861.92 | -0.59351 | 352861.92 | 2000 | 0 | 0 | -0.30859 | 0.027732 | 0 | #DIV/0! | 138240 | 0.04 | 0 | 0
CHA | 14112 | EPS Replacement for Z100 1st and 2nd Floor | Completed | CTE/A | Bian Jiacai | Chen Gang | 41796 | 42094 | 0 | 0 | N | ZNIC.014112 | NZNIC014112K |  | 14112 | 284000 | 0 | 309000 | 147730.98 | 0 | 5075 | -10725 | 284000 | 0 | 74872 | 284000 | 172730.98 | -0.39179 | 147730.98 | 0 | 25000 | 0 | -0.44042 | #DIV/0! | 5075 | 0.83069 | 0 | 1.3482 | 0 | 0
CEP/S | 14107 | PS/EPS Plant Emergency Lighting Modification | On Going | CTE/A | Xu Zheng | Zhang Pu | 42209 | 0 | 0 | 0 | H | ZNIC.009924 | NZNIC014107K |  | 14107 | 1329000 | 0 | 2128389 | 199141.15 | 631642.51 | -2522.64 | 55700 | 1329000 | -149498.43 | 83393.27 | 1329000 | 1189906.73 | -0.10466 | 199141.15 | 631642.51 | 508621.5 | -149498.43 | -0.11706 | -0.056604 | 0 | 1.0414 | 55700 | 0.055932 | 0 | 2
COO/A | 14104 | Add a Pipeline of ACN Waste Liquid to U5 Incinerator | On Going | CTE/P | Li Shouqing | Jiang Haijin | 42025 | 0 | 0 | 0 | N | ZNIC.008275 | NZNIC014104K |  | 14104 | 2063000 | 0 | 2151486 | 1462802.23 | 700.1 | -16000 | -207203.72 | #N/A | #N/A | #N/A | 2063000 | #N/A | #N/A | 1462802.23 | 700.1 | 594078 | #N/A | #N/A | -0.19373 | 0 | 1.0884 | 0 | 2.6062 | 0 | 1
CTS/U | 14101 | Replacement of ID Fans_Phase II CLWI Modification | Completed | CTE/P | Zhou Yanduo | Jiang Haijin | 41757 | 42129 | 0 | 0 | T_2015 | ZNIC.014101 | NZNIC014101K |  | 14101 | 6213000 | 0 | 6354998 | 5851828.53 | 0 | -69218.58 | -403842.1 | 6213000 | 0 | -1007216.21 | 6213000 | 5897328.53 | -0.050808 | 5851828.53 | 0 | 45500 | 0 | 0.35537 | -0.036127 | 0 | 1.1353 | 0 | 2.5016 | 0 | 9
CBP/C | 14097 | Add Fire Water Sprinkler Facilities for Pumps | Completed | CTE/P | Zhang Fanwen | Ling Taizhong | 41842 | 42285 | 0 | 0 | H | ZNIC.014097 | NZNIC014097K |  | 14097 | 1229000 | 0 | 1543231 | 1245208.14 | 3291.45 | -11319.2 | -33375.3 | 1229000 | 0 | 20176.14 | 1229000 | 1344891.59 | 0.094297 | 1245208.14 | 3291.45 | 96392 | 0 | -0.04307 | 0.024065 | 0 | 1.0616 | 0 | 1.1674 | 0 | 1
CBP/C | 14091 | APC Implementation and Optimization of Ethylene Unit | On Going | CTA/S | Dai Xiaolong | Dai Xiaolong | 41717 | 0 | 0 | 0 | N | ZNIC.014091 | NZNIC014091K |  | 14091 | 11000000 | 0 | 13751277 | 1673216.16 | 2159010.01 | -1082605.88 | 165800 | 11000000 | 6577180.36 | 424793.47 | 11000000 | 10409406.53 | -0.05369 | 1673216.16 | 2159010.01 | 0 | 6577180.36 | -0.10461 | #DIV/0! | 0 | 4.6087 | 165800 | 0.44733 | 3 | 0
COO/A | 14088 | Increase the Yield of Product AEEA | Completed | CTE/P | Li Shouqing | Jiang Haijin | 41995 | 42286 | 0 | 0 | T_2015 | ZNIF.107830.14.01 | NZNIC014088K |  | 14088 | 494000 | 0 | 665445 | 386739.66 | 58119.66 | -4610 | 1925 | 494000 | 0 | 10816.1 | 494000 | 446209.32 | -0.096742 | 386739.66 | 58119.66 | 1350 | 0 | 0.010747 | -0.18329 | 0 | 1.0375 | 1925 | 0.97813 | 0 | 1
CCP/O | 14087 | Add On/off Valves for HV24201/HV44201 | Completed | CTE/A | Wang Zhen | Wang Xinwu | 41793 | 42132 | 0 | 0 | T_2015 | ZNIC.014087 | NZNIC014087K |  | 14087 | 490000 | 140000 | 634555 | 633055.06 | 0 | -7700 | -48813.06 | 490000 | 0 | -194772.13 | 630000 | 634555.06 | 0.0072303 | 633055.06 | 0 | 1500 | 0 | 1.8187 | -0.42426 | 0 | 1.0558 | 0 | 1.9647 | 0 | 2
CEP/P | 14086 | Replacement of AMOT by Sentry System | Completed | CTE/A | Wang Zhen | Li Xueyong | 41778 | 42131 | 0 | 0 | T_2015 | ZNIC.014086 | NZNIC014086K |  | 14086 | 5612000 | 0 | 6213122 | 5708132.27 | 0 | 79750 | 40422 | 5612000 | 0 | 210924.66 | 5612000 | 5708132.27 | 0.01713 | 5708132.27 | 0 | 0 | 0 | -0.029661 | -0.2634 | 79750 | 0.68817 | 40422 | 0.71235 | 0 | 0
CBP/C | 14072 | Add 7 Samplers for Quench Section of Cracker | Completed | CTE/P | Qiu Zhufeng | Ling Taizhong | 41842 | 42133 | 0 | 0 | T_2015 | ZNIC.014072 | NZNIC014072K |  | 14072 | 593000 | 0 | 693000 | 595389.97 | 0 | 7760 | 16329.11 | 593000 | 0 | -42106.55 | 593000 | 595389.97 | 0.0040303 | 595389.97 | 0 | 0 | 0 | 0.16674 | -0.10272 | 7760 | 0.91701 | 16329.11 | 0.87732 | 0 | 0
CBP/M | 14068 | Replace Samplers for EB/SM | Completed | CTE/P | Sun Aihong | Wu Zefei | 41862 | 42124 | 0 | 0 | T_2015 | ZNIC.014068 | NZNIC014068K |  | 14068 | 485000 | 0 | 532500 | 554464.44 | 0 | 14200 | 23064.83 | 485000 | 0 | 182574.7 | 485000 | 554464.44 | 0.14323 | 554464.44 | 0 | 0 | 0 | -0.4956 | 0.12345 | 14200 | 0.8014 | 23064.83 | 0.70152 | 0 | 0
CBP/M | 14067 | Replace Some Pumps for EB/SM | On Going | CTE/P | Wang Lifen | Ling Taizhong | 41866 | 0 | 0 | 0 | N | ZNIC.014067 | NZNIC014067K |  | 14067 | 1900000 | 0 | 2603495 | 1404372.79 | 2897.44 | -72464.76 | -120389.16 | 1900000 | -529481.05 | 439999.82 | 1900000 | 1460000.18 | -0.23158 | 1404372.79 | 2897.44 | 582211 | -529481.05 | -0.33367 | -0.29917 | 0 | 1.3542 | 0 | 1.4667 | 9 | 8
CBP/M | 14066 | Revamp Outlet Motor Valves of Cooling Water Pumps | Completed | CTE/A | Gong Feibao | Li Hong | 41843 | 42117 | 0 | 0 | T_2015 | ZNIC.014066 | NZNIC014066K |  | 14066 | 1380000 | 0 | 1446000 | 1066525.31 | 0 | -21295 | -9865.43 | 1380000 | 0 | 1291047.2 | 1380000 | 1066525.31 | -0.22716 | 1066525.31 | 0 | 0 | 0 | -0.63149 | -0.14337 | 0 | 1.1253 | 0 | 1.054 | 0 | 0
CBP/B | 14058 | Move the BD&IB Plant DCS Control Station from BCC to EBSM | Completed | CTE/A | Gong Feibao | Li Hong | 41870 | 42115 | 0 | 0 | T_2015 | ZNIC.014058 | NZNIC014058K |  | 14058 | 3400000 | 0 | 3410505 | 2704774.17 | 0 | -151971.82 | -98115.5 | 3400000 | 0 | 781486.66 | 3400000 | 2708079.17 | -0.20351 | 2704774.17 | 0 | 3305 | 0 | -0.2715 | -0.30449 | 0 | 1.5345 | 0 | 1.2363 | 0 | 7
CEP/E | 14051 | Natural Gas Flowmeter Modification | Completed | CTE/P | Gu Jingfeng | Wu Zefei | 41715 | 41886 | 0 | 0 | T | ZNIC.014051 | NZNIC014051K |  | 14051 | 157000 | 0 | 158500 | 111094.64 | 0 | 4950 | 19189.92 | 157000 | 0 | 321.44 | 157000 | 112594.64 | -0.28284 | 111094.64 | 0 | 1500 | 0 | 0.11808 | -0.64123 | 4950 | 0.92623 | 19189.92 | 0.57708 | 0 | 1
CBP/C | 14045 | Add Gas Detector around Liquid Hydrocarbon Pumps | Completed | CTE/A | Wang Zhen | Li Hong | 41836 | 42194 | 0 | 0 | N | ZNIC.014045 | NZNIC014045K |  | 14045 | 491000 | 0 | 503000 | 342262.57 | 0 | -8800 | -6600 | 491000 | 0 | 18860.84 | 491000 | 354262.57 | -0.27849 | 342262.57 | 0 | 12000 | 0 | 0.035633 | -0.32468 | 0 | 1.0914 | 0 | 1.0923 | 0 | 0
CBP/M | 14035 | Revamp H1203 Natural Gas Pipeline | Completed | CTE/P | Sun Aihong | Wu Zefei | 41796 | 42124 | 0 | 0 | T_2015 | ZNIC.014035 | NZNIC014035K |  | 14035 | 418000 | 0 | 419200 | 372951.79 | 0 | -5310 | 31263.4 | 418000 | 0 | 32076.6 | 418000 | 372951.79 | -0.10777 | 372951.79 | 0 | 0 | 0 | -0.096701 | -0.28002 | 0 | 1.0413 | 31263.4 | 0.69765 | 0 | 0
CBP/M | 14034 | Add an Inhibitor Surge Drum for Each of T2401/2403 | Completed | CTE/P | Sun Aihong | Wu Zefei | 41841 | 42255 | 0 | 0 | T_2015 | ZNIC.014034 | NZNIC014034K |  | 14034 | 477000 | 0 | 542736 | 549736.16 | 0 | -24420 | -56351.67 | 477000 | 0 | 70420.5 | 477000 | 549736.16 | 0.15249 | 549736.16 | 0 | 0 | 0 | -0.1446 | -0.38481 | 0 | 1.2065 | 0 | 1.401 | 0 | 2
CBP/M | 14033 | Add O2 Detector at Discharge of C2401 | Completed | CTE/A | Gong Feibao | Li Hong | 41830 | 42312 | 0 | 0 | T_2015 | ZNIC.014033 | NZNIC014033K |  | 14033 | 246000 | 0 | 352085 | 245105.55 | 130 | -9222.07 | -30253 | 246000 | 13175.87 | -12411.42 | 246000 | 258411.42 | 0.050453 | 245105.55 | 130 | 0 | 13175.87 | 0.12231 | -0.076076 | 0 | 1.1582 | 0 | 1.8462 | 7 | 0
CBP/M | 14031 | 380VAC LV MCC System Modification of EB/SM | Completed | CTE/A | Zhao Wei | Sun Zhongpin | 41795 | 42132 | 42303 | 0 | T_2015 | ZNIC.014031 | NZNIC014031K |  | 14031 | 12200000 | 0 | 12485476 | 8396184.58 | 0 | 113179.14 | -210620.5 | #N/A | 0 | #N/A | 12200000 | 8663660.38 | -0.28986 | 8396184.58 | 0 | 267475.8 | 0 | #N/A | -0.313 | 113179.14 | 0.91597 | 0 | 1.5919 | 0 | 12
CBP/C | 14023 | Expand the Capacity of 330-V-344 | Completed | CTE/P | Qiu Zhufeng | Ling Taizhong | 41794 | 42133 | 0 | 0 | T_2015 | ZNIC.014023 | NZNIC014023K |  | 14023 | 497000 | 100000 | 574600 | 574600.02 | 0 | 12126.1 | -6871.17 | 597000 | 0 | 147937.95 | 597000 | 574600.02 | -0.037521 | 574600.02 | 0 | 0 | 0 | -0.36364 | -0.22102 | 12126.1 | 0.91797 | 0 | 1.0516 | 0 | 4
COA/S | 14015 | E1210 Condensate Recycle | On Going | CTE/P | Zhu Jianxin | Wu Zefei | 42019 | 0 | 0 | 0 | N | ZNIF.106500.15.01 | NZNIC014015K |  | 14015 | 830000 | 290000 | 854477 | 425970.85 | 48000 | 154110 | 122850 | 1120000 | 350815.76 | 11981.39 | 1120000 | 831058.61 | -0.25798 | 425970.85 | 48000 | 6272 | 350815.76 | -0.042333 | -0.17453 | 154110 | 0.51385 | 122850 | 0.19178 | 0 | 1
CTS/U | 14002 | Replace Material of the Pipeline between Compressor and Dryer | Completed | CTE/P | Li Shouqing | Zhang Fanwen | 41752 | 42118 | 0 | 0 | T_2015 | ZNIC.014002 | NZNIC014002K |  | 14002 | 2360000 | 0 | 2377500 | 2165099.84 | 0 | -18560 | -77089.53 | 2360000 | 0 | -448100.21 | 2360000 | 2182599.84 | -0.07517 | 2165099.84 | 0 | 17500 | 0 | 0.54726 | 0.046183 | 0 | 1.1418 | 0 | 1.4422 | 0 | 0
CTS/U | 14001 | Add Heat Exchanger of CPS Pipeline to BCC | Completed | CTE/P | Li Shouqing | Zhang Fanwen | 41793 | 42124 | 0 | 0 | T_2015 | ZNIC.014001 | NZNIC014001K |  | 14001 | 1194000 | 0 | 1344261 | 1032623.23 | 8000 | -21256.48 | 2578.3 | 1194000 | 0 | 124067.15 | 1194000 | 1042884.23 | -0.12656 | 1032623.23 | 8000 | 2261 | 0 | 0.013642 | -0.29739 | 0 | 1.1255 | 2578.3 | 0.98468 | 0 | 2
CBP/A | 13277 | D230 MCC Modification | Completed | CTE/A | Hu Xiao | Chen Gang | 41764 | 42132 | 0 | 0 | T_2015 | ZNIC.013277 | NZNIC013277K |  | 13277 | 3950000 | 0 | 3964380 | 2035043.68 | 4498 | -72400.52 | 91817.32 | #N/A | 0 | #N/A | 3950000 | 2041923.68 | -0.48306 | 2035043.68 | 4498 | 2382 | 0 | #N/A | 0.036757 | 0 | 1.4044 | 91817.32 | 0.65365 | 0 | 4
CBP/M | 13270 | Gas Detector Modification for EB/SM Tank Farm | Completed | CTE/A | Wang Zhen | Li Hong | 41709 | 42250 | 0 | 0 | N | ZNIC.013270 | NZNIC013270K |  | 13270 | 432000 | 0 | 432000 | 243654.64 | 0 | -580 | -2475 | 432000 | 0 | 87683.36 | 432000 | 243654.64 | -0.43598 | 243654.64 | 0 | 0 | 0 | -0.43378 | -0.23445 | 0 | 1.0082 | 0 | 1.0536 | 0 | 0
CHA | 13265 | Modify IET Office to Archive Centre Storeroom | Completed | CTE/C | Yu Yi | Jiang Yunning | 41926 | 42063 | 42251 | 0 | N | ZNIC.007512 | NZNIC013265K |  | 13265 | 1221000 | 1600000 | 2851000 | 2301084.59 | 30000 | 4252.39 | -380587.92 | 2821000 | 0 | 208666.37 | 2821000 | 2331084.59 | -0.17367 | 2301084.59 | 30000 | 0 | 0 | -0.34541 | -0.12118 | 4252.39 | 0.95378 | 0 | 4.1742 | 0 | 3
COA/E | 13263 | Add Solenoid Valve for P5845 and P6660/P6665 Diaphragm Pump Air Supply | Completed | CTA/A | Guo Jinhua | Guo Jinhua | 41661 | 42246 | 0 | 0 | N | ZNIC.013263 | NZNIC013263K |  | 13263 | 70000 | 0 | 70000 | 0 | 0 | 0 | 1500 | 70000 | 0 | 0 | 70000 | 0 | -1 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 1500 | 0 | 0 | 0
CBP/C | 13260 | Upgrade PLC of Turbonmachinery Control System | Completed | CTA/B | Zhao Yongming | Zhao Yongming | 41619 | 42155 | 42152 | 0 | T_2015 | ZNIC.013260 | NZNIC013260K |  | 13260 | 2000000 | 0 | 2000000 | 1276119.98 | 0 | 75600 | 0 | 2000000 | 0 | 490020.62 | 2000000 | 1276119.98 | -0.36194 | 1276119.98 | 0 | 0 | 0 | -0.24774 | #DIV/0! | 75600 | 0.055 | 0 | #DIV/0! | 0 | 0
CBP/C | 13259 | Upgrade Speed Control System of Compressors | Completed | CTA/B | Zhao Yongming | Zhao Yongming | 41619 | 42155 | 42152 | 0 | T_2015 | ZNIC.013259 | NZNIC013259K |  | 13259 | 2000000 | 0 | 2000000 | 1838951.56 | 0 | 80000 | 0 | 2000000 | 0 | -201573.34 | 2000000 | 1838951.56 | -0.080524 | 1838951.56 | 0 | 0 | 0 | 0.10337 | #DIV/0! | 80000 | 0 | 0 | #DIV/0! | 0 | 0
CBP/M | 13257 | Add a Waste Water Pump in EB/SM | Completed | CTE/P | Sun Aihong | Ling Taizhong | 41709 | 42349 | 0 | 0 | N | ZNIC.013257 | NZNIC013257K |  | 13257 | 365000 | 0 | 445854 | 376522.83 | 0 | 11640 | -11766.22 | 365000 | -56587.31 | 26424.48 | 365000 | 326935.52 | -0.10429 | 376522.83 | 0 | 7000 | -56587.31 | -0.074907 | -0.13516 | 11640 | 0.8856 | 0 | 1.1507 | 0 | 1
CBP/C | 13247 | Modification of Filter System for P230 | Completed | CTE/P | Wang Can | Ling Taizhong | 41830 | 42133 | 0 | 0 | T_2015 | ZNIC.013247 | NZNIC013247K |  | 13247 | 1055000 | 495000 | 1485801 | 1620413.84 | 101 | -65730.09 | -9245.61 | 1055000 | 0 | -586764.33 | 1550000 | 1620514.84 | 0.045493 | 1620413.84 | 101 | 0 | 0 | 0.88147 | -0.13413 | 0 | 1.3266 | 0 | 1.058 | 1 | 3
CBP/B | 13244 | Add Spare Exchangers and Filters in BEU | Completed | CTE/P | Gu Jingfeng | Ling Taizhong | 41709 | 42223 | 0 | 0 | T_2015 | ZNIC.013244 | NZNIC013244K |  | 13244 | 5250000 | 0 | 5251931 | 3330289.88 | 431.09 | -325563.53 | -170071.53 | 5250000 | 0 | 1619190.82 | 5250000 | 3332220.97 | -0.36529 | 3330289.88 | 431.09 | 1500 | 0 | -0.448 | -0.18288 | 0 | 1.8131 | 0 | 1.5622 | 0 | 7
CEP/S | 13243 | Revamp Rain Drainage System of PS Tank Farm | Completed | CTE/C | Gao Feng | Zhang Zhihe | 41841 | 42236 | 0 | 0 | H | ZNIC.013243 | NZNIC013243K |  | 13243 | 561000 | 0 | 598204 | 594203.35 | 0 | 32768.2 | -19676.26 | 561000 | 0 | 49509.96 | 561000 | 598203.35 | 0.066316 | 594203.35 | 0 | 4000 | 0 | -0.037726 | -0.18619 | 32768.2 | 0.81612 | 0 | 1.195 | 0 | 3
CAP/E | 13240 | Add Jacket Heat Exchanger on V6700 | Completed | CTE/P | Xie Qiang | Wu Zefei | 41656 | 41886 | 0 | 0 | N | ZNIC.013240 | NZNIC013240K |  | 13240 | 410000 | 0 | 437708 | 436207.83 | 0 | -5905 | -20524.44 | #N/A | 0 | #N/A | 410000 | 437707.83 | 0.06758 | 436207.83 | 0 | 1500 | 0 | #N/A | -0.27267 | 0 | 1.0548 | 0 | 1.2415 | 0 | 1
CBL/O | 13236 | Rebuild RTTF Operation Room 1&2 | Completed | CTE/C | Yu Yi | Guo Bing | 41893 | 42308 | 0 | 0 | N | ZNIC.013236 | NZNIC013236K |  | 13236 | 942000 | 0 | 1383028 | 384367.86 | 10029.9 | -6810 | 33188.45 | 942000 | 108373.06 | -24642.27 | 942000 | 933453.82 | -0.0090724 | 384367.86 | 10029.9 | 430683 | 108373.06 | 0.50922 | -0.3872 | 0 | 1.0484 | 33188.45 | 0.74646 | 0 | 3
CBP/A | 13234 | Replacement of 800-UPS-001 | Completed | CTE/A | Bian Jiacai | Chen Gang | 41666 | 42110 | 0 | 0 | T_2015 | ZNIC.013234 | NZNIC013234K |  | 13234 | 774000 | 0 | 774000 | 494014.8 | 0 | 1251.89 | -4677 | 774000 | 0 | 129054.19 | 774000 | 494014.8 | -0.36174 | 494014.8 | 0 | 0 | 0 | -0.2164 | 0.048207 | 1251.89 | 0.97485 | 0 | 1.2074 | 0 | 3
CBP/C | 13233 | Replacement of 300-UPS-001 | Completed | CTE/A | Bian Jiacai | Chen Gang | 41666 | 42117 | 0 | 0 | T_2015 | ZNIC.013233 | NZNIC013233K |  | 13233 | 881000 | 0 | 881000 | 566235.58 | 0 | 11560 | -2795.88 | 881000 | 0 | 127408.53 | 881000 | 566235.58 | -0.35728 | 566235.58 | 0 | 0 | 0 | -0.18571 | 0.17743 | 11560 | 0.76775 | 0 | 1.124 | 0 | 2
CBP/C | 13229 | Replace Economizer with High Efficient Type for SUB | Completed | CTE/P | Qiu Zhufeng | Ling Taizhong | 41743 | 42130 | 0 | 0 | T_2015 | ZNIC.013229 | NZNIC013229K |  | 13229 | 3054000 | 1553000 | 4073939 | 4279187.91 | 0 | -21153.97 | -14625 | 3054000 | 0 | -196768.88 | 4607000 | 4319187.91 | -0.062473 | 4279187.91 | 0 | 40000 | 0 | 0.047765 | 0.046675 | 0 | 1.1237 | 0 | 1.1007 | 1 | 0
CCP/A | 13224 | Add 2000m3 DEOA Tank in RTTF | Completed | CTE/P | Jiang Hao/Liu Xiaoli | Xu Yefeng/Zong Baorong | 41697 | 42129 | 0 | 0 | T_2015 | ZNIC.013224 | NZNIC013224K |  | 13224 | 15880000 | 0 | 16101960 | 17613149.76 | 36292.33 | 332800 | 202300 | 15880000 | 0 | -54575.1 | 15880000 | 17649442.09 | 0.11143 | 17613149.76 | 36292.33 | 0 | 0 | 0.56397 | -0.27373 | 332800 | 0 | 202300 | 0.1895 | 0 | 0
CTS/U | 13209 | Adding a New Ultrasonic Flowmeter on DM Water in CLWI | Hold | CTA/U | Yu Yong | Yu Yong | 41557 | 0 | 0 | 0 | N | ZNIC.013209 | NZNIC013209K |  | 13209 | 90000 | 0 | 213215 | 0 | 123215.39 | 0 | 5000 | 90000 | -38215.39 | 0 | 90000 | 85000 | -0.055556 | 0 | 123215.39 | 0 | -38215.39 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 5000 | 0 | 0 | 0
COO/C | 13198 | NPG_TMA Supply from C1 Plant | Completed | CTE/P | Sun Duoxun | Jiang Haijin | 41528 | 42160 | 0 | 0 | T_2015 | ZNIC.131198 | NZNIC013198K |  | 13198 | 1676000 | 0 | 2185329 | 2195537.55 | 0 | -352510.27 | -287309.01 | 1676000 | 0 | 129032.34 | 1676000 | 2201537.55 | 0.31357 | 2195537.55 | 0 | 6000 | 0 | -0.31388 | 0.0042945 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 4
COO/O | 13197 | NPG_IBA Supply from OXO Plant | Completed | CTE/P | Sun Duoxun | Jiang Haijin | 41528 | 42158 | 0 | 0 | T_2015 | ZNIC.131197 | NZNIC013197K |  | 13197 | 1720000 | 0 | 2319011 | 2315658.3 | 5000 | -345333.97 | -276334.4 | 1720000 | 0 | 328807.09 | 1720000 | 2326658.3 | 0.35271 | 2315658.3 | 5000 | 6000 | 0 | -0.39097 | -0.17224 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 3
CBP/M | 13195 | Replace an Air Dryer | On Going | CTE/P | Ding Juntao | Ling Taizhong | 41997 | 0 | 0 | 0 | N | ZNIC.008126 | NZNIC013195K |  | 13195 | 1344000 | 0 | 1596491 | 949744.01 | 462.5 | -49443.02 | -27500 | 1344000 | -34100.24 | 171914.73 | 1344000 | 1172085.27 | -0.12791 | 949744.01 | 462.5 | 255979 | -34100.24 | -0.19296 | -0.46852 | 0 | 1.364 | 0 | 1.1961 | 0 | 6
CBP/C | 13190 | Add Explosion-proof Monitoring Camera in BCC&SCTF | Completed | CTE/A | Bian Jiacai | Chen Gang | 41680 | 42185 | 0 | 0 | N | ZNIC.013190 | NZNIC013190K |  | 13190 | 5665000 | 0 | 5675760 | 4203228.63 | 0 | 2820 | -18150 | 5665000 | 0 | 1068608.18 | 5665000 | 4203228.63 | -0.25804 | 4203228.63 | 0 | 0 | 0 | -0.23695 | -0.05856 | 2820 | 0.98624 | 0 | 1.0667 | 0 | 0
CBP/M | 13189 | Air-conditioning System Modification in CCR of 7100 | Completed | CTE/C | Gao Feng | Wang Wei | 41667 | 42185 | 0 | 0 | N | ZNIC.013189 | NZNIC013189K |  | 13189 | 4234000 | 0 | 4398544 | 3008109.75 | 20095 | -54198.12 | 9568.87 | #N/A | 0 | #N/A | 4234000 | 3041789.75 | -0.28158 | 3008109.75 | 20095 | 13585 | 0 | #N/A | -0.19356 | 0 | 1.2324 | 9568.87 | 0.94142 | 0 | 2
CBP/M | 13184 | Modify Waste Water System for EB/SM Tank Farm | Completed | CTE/P | Sun Aihong | Ling Taizhong | 41753 | 42314 | 0 | 0 | T_2015 | ZNIC.013184 | NZNIC013184K |  | 13184 | 4080000 | 0 | 4814735 | 3070395.75 | 52079.48 | -20197.27 | -169055.05 | 4080000 | -593648.48 | 1233088.25 | 4080000 | 2846911.75 | -0.30223 | 3070395.75 | 52079.48 | 318085 | -593648.48 | -0.35793 | -0.21213 | 0 | 1.0746 | 0 | 1.4773 | 0 | 5
CEP/S | 13165 | Control System of Pelletizing Upgrading in HIPS | Completed | CTE/A | Gong Feibao | Zeng Qing | 41591 | 42152 | 0 | 0 | T_2015 | ZNIC.013165 | NZNIC013165K |  | 13165 | 1139000 | 91000 | 1404921 | 1404921.44 | 0 | 58600 | 77500 | 1139000 | 0 | -640000 | 1230000 | 1404921.44 | 0.14221 | 1404921.44 | 0 | 0 | 0 | 0.66667 | #DIV/0! | 58600 | 0.38958 | 77500 | 0 | 0 | 0
CBP/C | 13156 | Add a Control Valve on K650 Outlet Line to Flare | Completed | CTE/P | Qiu Zhufeng | Li Hong | 41625 | 42122 | 0 | 0 | T_2015 | ZNIC.013156 | NZNIC013156K |  | 13156 | 340000 | 0 | 390000 | 204932.78 | 0 | 22600 | -9034.34 | 340000 | 0 | 37188.48 | 340000 | 204932.78 | -0.39726 | 204932.78 | 0 | 0 | 0 | -0.2275 | -0.42707 | 22600 | 0.67127 | 0 | 1.2119 | 0 | 0
CAP/A | 13133 | Add New Restab Unit System | Completed | CTE/P | Zhu Jianxin | Wu Zefei | 41663 | 41989 | 0 | 0 | H | ZNIC.013133 | NZNIC013133K |  | 13133 | 8751000 | 0 | 10339693 | 5873055.08 | 1583692.53 | -619842.02 | -265472.81 | 8751000 | 0 | 1411008.29 | 8751000 | 7461747.61 | -0.14733 | 5873055.08 | 1583692.53 | 5000 | 0 | -0.2634 | -0.33373 | 0 | 2.0145 | 0 | 1.3692 | 9 | 7
CBP/M | 13120 | EB/SM Plant Paging System Modification | Completed | CTA/S | Dai Xiaolong | Qiu Wei | 41465 | 42185 | 0 | 0 | N | ZNIC.013120 | NZNIC013120K |  | 13120 | 950000 | 0 | 963899 | 914799.43 | 0 | -4714 | 4950.58 | 950000 | 0 | -159529.9 | 950000 | 928698.43 | -0.022423 | 914799.43 | 0 | 13899 | 0 | 0.24089 | -0.067334 | 0 | 1.4714 | 4950.58 | 0.83498 | 0 | 1
CEP/S | 13115 | PS&EPS Plant Paging System Modification | Completed | CTA/S | Dai Xiaolong | Qiu Wei | 41465 | 42185 | 0 | 0 | H | ZNIC.013115 | NZNIC013115K |  | 13115 | 1050000 | 0 | 1050000 | 952566.79 | 0 | -18875 | 30000 | 1050000 | 0 | -143097.13 | 1050000 | 952566.79 | -0.092794 | 952566.79 | 0 | 0 | 0 | 0.20007 | -0.14744 | 0 | 2.8875 | 30000 | 0 | 0 | 0
CEP/S | 13114 | Add Back Flow Protection in Utility Supply Pipes | Completed | CTE/P | Gu Jingfeng | Zhang Fanwen | 41515 | 42129 | 0 | 0 | T_2015 | ZNIC.013114 | NZNIC013114K |  | 13114 | 1996000 | 0 | 1999111 | 1128415.8 | 3111.11 | -45660.51 | -17168.87 | 1996000 | 0 | 618079.77 | 1996000 | 1131526.91 | -0.4331 | 1128415.8 | 3111.11 | 0 | 0 | -0.72477 | -0.20945 | 0 | 1.2758 | 0 | 1.096 | 0 | 2
CTS/U | 13112 | CLWI Modification | Completed | CTE/P | Zhou Yanduo | Zhang Fanwen | 41582 | 42017 | 42195 | 0 | H | ZNIC.013112 | NZNIC013112K |  | 13112 | 16000000 | 0 | 16045806 | 12367299.12 | 0 | -7723526.81 | -493586.35 | 16000000 | 0 | 1068187.92 | 16000000 | 12406352.62 | -0.2246 | 12367299.12 | 0 | 39053.5 | 0 | -0.058458 | -0.22808 | 0 | 31.8941 | 0 | 3.3504 | 6 | 15
CCP/A | 13106 | Add a EDA Recycle Pump to Produce More PIP/DETA | Completed | CTE/P | Li Shouqing | Wang Wei | 41493 | 41882 | 0 | 0 | T | ZNIC.013106 | NZNIC013106K |  | 13106 | 1715000 | 0 | 1715000 | 1479893 | 0 | 17614.53 | -115361.37 | 1715000 | 0 | 247600.61 | 1715000 | 1479893 | -0.13709 | 1479893 | 0 | 0 | 0 | -0.18836 | -0.26874 | 17614.53 | 0.93171 | 0 | 1.839 | 0 | 2
CBP/C | 13105 | Add a Gasoline Reflux Pump for Quench Oil Fractionator | Canceled | CTE/P | Sun Aihong | Ling Taizhong | 41678 | 0 | 0 | 0 | T_2015 | ZNIC.013105 | NZNIC013105K |  | 13105 | 1947000 | 0 | 1947000 | 203571.98 | 0 | 143495 | 239487.52 | 1947000 | 1289016.15 | 71429.35 | 1947000 | 1492588.13 | -0.23339 | 203571.98 | 0 | 0 | 1289016.15 | -0.036222 | -0.77757 | 143495 | 0.46317 | 239487.52 | 0.18075 | 0 | 0
CTA | 13096 | C402 HVAC Replacement and Roof Repair | Completed | CTE/C | Yu Yi | Wang Wei | 41603 | 42040 | 0 | 0 | N | ZNIC.013096 | NZNIC013096K |  | 13096 | 2660000 | 0 | 2668000 | 1792039.75 | 8000 | -49810 | -426602.39 | 2660000 | 0 | 678663.9 | 2660000 | 1800039.75 | -0.32329 | 1792039.75 | 8000 | 0 | 0 | -0.42957 | -0.15328 | 0 | 1.2595 | 0 | 3.3648 | 0 | 2
CBP/C | 13081 | Replace the Electric Heat Tracing on Furnaces | On Going | CTE/A | Wang Zhen | Li Hong | 41521 | 0 | 0 | 0 | T_2015 | ZNIC.013081 | NZNIC013081K |  | 13081 | 3238000 | 0 | 3564454 | 2598843.26 | 8477.26 | -19825 | -314050 | 3238000 | -73734.41 | 409516.89 | 3238000 | 2828483.11 | -0.12647 | 2598843.26 | 8477.26 | 294897 | -73734.41 | -0.243 | -0.13285 | 0 | 1.0456 | 0 | 1.5948 | 0 | 0
CEP/L | 13064 | Fire Alarm System Modification in PS/EPS Logistics | Completed | CTE/A | Hu Xiao | Zhang Pu | 41519 | 41786 | 0 | 0 | H | ZNIC.013064 | NZNIC013064K |  | 13064 | 977000 | 0 | 987740 | 987739.89 | 0 | -27880.01 | 16225 | 977000 | 0 | 36997.21 | 977000 | 987739.89 | 0.010993 | 987739.89 | 0 | 0 | 0 | -0.053243 | -0.041214 | 0 | 1.2325 | 16225 | 0.91181 | 0 | 2
CBP/C | 13060 | Add Two Inhibiter Injection Pumps | Completed | CTE/P | Sun Aihong | Ling Taizhong | 41724 | 42133 | 0 | 0 | T_2015 | ZNIC.013060 | NZNIC013060K |  | 13060 | 650000 | 0 | 685000 | 614689.9 | 0 | -1995 | 36765.83 | 650000 | 0 | -44714.47 | 650000 | 614689.9 | -0.054323 | 614689.9 | 0 | 0 | 0 | 0.16454 | -0.26684 | 0 | 1.0149 | 36765.83 | 0.71062 | 0 | 1
CAP/L | 13058 | IS/IT Project for NASA | Completed | CFA | Liu Min | Tao Yang | 41407 | 41821 | 41995 | 0 | N | ZNIC.013058 | NZNIC013058K |  | 13058 | 10180000 | 2092000 | 10453379 | 10398219.24 | 55160 | -1839306.56 | 0 | 10180000 | 0 | 0 | 12272000 | 10453379.24 | -0.14819 | 10398219.24 | 55160 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0
CCP/A | 13054 | Add 2000m3 EDA Tank in RTTF | Completed | CTE/P | Jiang Hao/Liu Xiaoli | Xu Yefeng/Zong Baorong | 41697 | 42129 | 0 | 0 | T_2015 | ZNIC.013054 | NZNIC013054K |  | 13054 | 15880000 | 0 | 17551322 | 19104689.11 | 88866.57 | -517624.15 | -720912.5 | 15880000 | 0 | 24293.1 | 15880000 | 19242555.68 | 0.21175 | 19104689.11 | 88866.57 | 49000 | 0 | 0.37808 | -0.30243 | 0 | 2.6676 | 0 | 4.0967 | 0 | 1
CBP/P | 13016 | MarkV Upgrade of Gas Turbines Control System, Power Plant | On Going | CTA/U | Lei Yufa | He Zhengyu | 41306 | 0 | 0 | 0 | N | ZNIC.013016 | NZNIC013016K |  | 13016 | 18000000 | 0 | 18075872 | 9270482.94 | 871.8 | 460845 | -267896.5 | 18000000 | 2140638.62 | 6127161.64 | 18000000 | 11411993.36 | -0.366 | 9270482.94 | 871.8 | 0 | 2140638.62 | -0.38982 | 0.049534 | 460845 | 0.29101 | 0 | 1.893 | 0 | 0
CBP/C | 12137 | Replace Radiant Section Tubes for 7 Liquid Furnaces | Completed | CTE/P | Zhou Yanduo | Tong Shaojian | 41381 | 42340 | 0 | 0 | T | ZNIC.012137 | NZNIC012137K |  | 12137 | 58500000 | 0 | 63756970 | 44906196.54 | 0 | 21414.34 | 1324100.36 | 58500000 | 9980626.85 | 2051891.91 | 58500000 | 55102593.39 | -0.058075 | 44906196.54 | 0 | 215770 | 9980626.85 | 0.014512 | -0.16679 | 21414.34 | 0.93429 | 1324100.36 | 0.44534 | 0 | 27
CBP/B | 12119 | Add a Filter to Remove Metal Ions from IBOL | Completed | CTE/P | Sun Aihong | Ling Taizhong | 41359 | 41781 | 42216 | 0 | N | ZNIC.012119 | NZNIC012119K |  | 12119 | 1570000 | 0 | 1571500 | 1225101.06 | 0 | -172047.53 | -78710.57 | #N/A | 0 | #N/A | 1570000 | 1226601.06 | -0.21873 | 1225101.06 | 0 | 1500 | 0 | #N/A | -0.23813 | 0 | 1.7785 | 0 | 1.5428 | 0 | 7
CBP/B | 12071 | Add Raffinate I Washer Column System in BD Plant | Completed | CTE/P | Cao Lin | Wang Yuncai | 41526 | 41939 | 0 | 0 | T_2015 | ZNIC.012071 | NZNIC012071K |  | 12071 | 8622000 | 0 | 8824040 | 7814981.88 | 198113.21 | -1043844.15 | -535306.12 | 8622000 | 0 | -75000.21 | 8622000 | 8013095.09 | -0.070622 | 7814981.88 | 198113.21 | 0 | 0 | 0.09063 | -0.10711 | 0 | 2.5159 | 0 | 1.5995 | 2 | 10
CTS/P | 12044 | Cooling Water Expansion from PP to Syngas | Completed | CTE/P | Sun Duoxun | Wu Zefei | 41764 | 42121 | 0 | 0 | T_2015 | ZNIC.012044 | NZNIC012044K |  | 12044 | 3830000 | 0 | 3834800 | 1998299.17 | 0 | -61072.5 | -40305.81 | 3830000 | 0 | 1054974.68 | 3830000 | 1998299.17 | -0.47825 | 1998299.17 | 0 | 0 | 0 | -0.4093 | -0.19639 | 0 | 1.2877 | 0 | 1.2891 | 0 | 1
CBP/M | 11229 | Revamp Dosing System of Cooling System of EB/SM | Completed | CTE/P | Zhu Jianxin | Ling Taizhong | 41709 | 42133 | 0 | 0 | H | ZNIC.011229 | NZNIC011229K |  | 11229 | 1099000 | 0 | 1101000 | 996916.14 | 0 | -191656.98 | -142193.85 | 1099000 | 0 | 224642.99 | 1099000 | 998916.14 | -0.091068 | 996916.14 | 0 | 2000 | 0 | -0.012823 | -0.38305 | 0 | 1.852 | 0 | 1.8079 | 2 | 6

## Sheet5 (hidden)
Cost Report for MOC
BU. | Job No | Job Type | Job Title | Account | PM | MC | Budget | Planned | Actual | Cost to Com | Estiamted Final Cost | COST_COMPLE% | Remarks
CBP/P | 15313 | MOC | Protection Relay of U4PM6101A Replacement for Updating | 973434426 | Ge Yong | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
COA/A | 15309 | MOC | Add Filter on Inlet of F430 | 973506548 | Meng Yousheng | 2015-12-10 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CEP/E | 15307 | MOC | Add Tie-in for Chiller U3777 | 973507320 | Wang Zhigao | 0 | 33800 | 23800 | 17020 | 6780 | 23800 | 50.36%
CEP/E | 15304 | MOC | Add a Filter at Outlet of P5311 | 973507099 | Li Jun | 0 | 23800 | 23800 | 7200 | 16600 | 23800 | 30.25%
CBP/B | 15303 | MOC | Connect the Original and New Fuel Oil Line in BD | 973519560 | Wang Can | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CEP/E | 15302 | MOC | Add a Spring Hanger to T13017-1 | 973378059 | Gu Jingfeng | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CBP/B | 15299 | MOC | Redesign& Reinstall the Fuel Oil Line from BD to EU Piperack | 973529386 | Wang Can | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CBP/S | 15294 | MOC | Adding H2 Detectors for Coldbox's Leakage | 973495739 | Gong Feibao | 0 | 121000 | 105859.22 | 65708.16 | 40151.06 | 105859.22 | 54.3%
CEP/P | 15282 | MOC | Add Liquid Waste tank | 973471450 | Gu Jingfeng | 0 | 39050 | 0 | 6600 | 0 | 6600 | 16.9%
COA/A | 15280 | MOC | Add Local Pressure Gauge on Inlet P430 | 973470849 | Meng Yousheng | 0 | 15000 | 9400 | 2750 | 6650 | 9400 | 18.33%
CBP/C | 15276 | MOC | Modify the Gas Sampler Type to Closed Loop Sampler at Prolysis Gasoline Unit(PGU) | 973482590 | Sun Aihong | 0 | 20000 | 17520 | 4400 | 13120 | 17520 | 22%
CBP/C | 15275 | MOC | Modify the EBO Product Sampler Type to Closed Loop Sampler at Quench Section | 973482589 | Sun Aihong | 0 | 20000 | 17520 | 0 | 17520 | 17520 | 0%
CTE | 15271 | MOC | Modification of Road Lamp at North Gate on the Yangba raod. | 973487007 | Bian Jiacai | 0 | 119789 | 75265.27 | 5500 | 69765.27 | 75265.27 | 4.591%
CEP/E | 15269 | MOC | EO Analyzer House Air Conditioning System Modification | 973454483 | Wang Wei | 0 | 680000 | 339750 | 4400 | 335350 | 339750 | 0.6471%
COO/A | 15261 | MOC | Add Drain Valves | 973437650 | Chen Yuxin | 2015-10-23 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
COO/A | 15249 | MOC | Add a Set of Drain Valves and Sightglass on K4800A/B and K4992A/B with EHT | 973458234 | Li Shouqing | 0 | 150720 | 122883 | 25300 | 97583 | 122883 | 16.79%
COO/C | 15244 | MOC | Modify the Cofferdam of Waste Oil IBCs | 973386824 | Xia Qun | 2015-10-20 | 27825 | 27705 | 14313.9 | 13391.1 | 27705 | 51.44%
CBP/P | 15238 | MOC | Add Grid and Lock for U456-TR-001/002/003/004/005/006 | 973344599 | Wang Shicheng | 0 | 122500 | 139962.5 | 2475 | 137487.5 | 139962.5 | 2.02%
CBP/S | 15235 | MOC | Add Temporary Piping to V1202 from P1201 Outlet | 973376659 | Wang Can | 2015-10-14 | 88170 | 90969.56 | 73325.48 | 17644.08 | 90969.56 | 83.16%
COO/C | 15234 | MOC | Add a Cofferdam around P3812 | 973378581 | Xia Qun | 2015-11-27 | 83350 | 79540 | 23550 | 55990 | 79540 | 28.25%
COO/C | 15232 | MOC | Relocate the Hose Reel Box Beside P2200 | 973379392 | Zhang Fanwen | 2015-09-30 | 47650 | 41214.87 | 26831.11 | 14383.76 | 41214.87 | 56.31%
COO/C | 15227 | MOC | Modification of PA HB/LB Loading System According Assessment | 973360623 | Xia Qun | 2015-10-20 | 180000 | 129784 | 86450.97 | 43333.03 | 129784 | 48.03%
CBP/M | 15224 | MOC | Add a Pavement between EB/SM and BD/IB | 973319084 | Yan Jun | 2015-10-21 | 47000 | 46608 | 31091.58 | 15516.42 | 46608 | 66.15%
CBP/P | 15222 | MOC | Anti-vibration for Inlet and Discharge Line of P6402C | 973488820 | Wang Can | 0 | 193000 | 140525 | 33530 | 106995 | 140525 | 17.37%
CBP/U | 15221 | MOC | CBPU Modlify HPFW System into YBS | 973517510 | Zhang Fanwen | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
COO/C | 15212 | MOC | Add a Sample Point at C2619 Off Gas Pipe | 973384528 | Li Shouqing | 0 | 198990 | 138990 | 0 | 138990 | 138990 | 0%
CBL/T | 15210 | MOC | Add Container for Maintenance & Instrument Storeroom near SCTF Control Building | 973371676 | Wang Shicheng | 2015-09-30 | 21050 | 22850 | 3557.74 | 19292.26 | 22850 | 16.9%
CBP/M | 15208 | MOC | Leakage of the Roof of MCC of EB/SM Plant | 973314814 | Wang Shicheng | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
COO/O | 15205 | MOC | Reduce C3106 Level and Modify C3 BF3 Exhaust Pipeline in C3106 | 973347817 | Sun Yan | 0 | 96550 | 90794.54 | 53466.51 | 37328.03 | 90794.54 | 55.38%
CBL/O | 15194 | MOC | Relocate the Venting Line of CMHL019B of A511 | 973525110 | Zhang Fanwen | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
CBP/P | 15190 | MOC | Add Fence and Door for Waste Chemical Laydown | 973308117 | Xia Qun | 0 | 108000 | 76450 | 0 | 76450 | 76450 | 0%
COO/O | 15189 | MOC | Add Mannual Switch for Shutdown and Startup Fresh Air System of HVAC in Control Room or DCS | 973335860 | Gao Feng | 0 | 85000 | 66405 | 20740 | 45665 | 66405 | 24.4%
CBL/O | 15187 | MOC | Add Temperature Control for 99% FA of Z3950 | 973421119 | Gong Feibao | 0 | 107750 | 98250 | 37117.56 | 61132.44 | 98250 | 34.45%
CBL/P | 15181 | MOC | Move Switch of Fresh Air System to Control Room | 973353778 | Gao Feng | 2015-11-26 | 85050 | 65050 | 20692.31 | 44357.69 | 65050 | 24.33%
COA/S | 15177 | MOC | Install New Platforms in the Production Building | 973485229 | Yu Yi | 0 | 411548 | 220075 | 5500 | 214575 | 220075 | 1.336%
CEP/E | 15175 | MOC | Add a Balance Line between the V5150&V5152 | 973458544 | Gu Jingfeng | 0 | 117500 | 96300 | 14245.14 | 82054.86 | 96300 | 12.12%
COA/A | 15173 | MOC | Modification for Heat Tracing of Melted Salt Pipeline | 973470745 | Xu Jin | 0 | 265000 | 135900 | 6200 | 129700 | 135900 | 2.34%
CTM | 15170 | MOC | YBS Warehouse Covered Work Site Zone Increase | 973371675 | Yu Yi | 0 | 439000 | 311967.9 | 42571.41 | 269396.49 | 311967.9 | 9.697%
CBP/C | 15165 | MOC | Replace the Air Condition of the Switch Room D-110 | 973327841 | Wang Shicheng | 2015-10-23 | 26000 | 23920 | 10827.36 | 13092.64 | 23920 | 41.64%
COO/O | 15162 | MOC | Move the Flammable Gas Cylinder from Laboratory to Cylinder Room and Install Introduction of Pipeline | 973364287 | Liu Xiaoli | 2015-10-20 | 28810 | 27761.27 | 17951.46 | 9809.81 | 27761.27 | 62.31%
CBP/S | 15161 | MOC | Add 2 Footpath near U1621 and Z1901 | 973379812 | Yan Jun | 2015-09-30 | 45000 | 42717 | 28611.36 | 14105.64 | 42717 | 63.58%
CEP/P | 15158 | MOC | Add HVAC for B150 Workshop | 973388920 | Gao Feng | 2015-12-03 | 106075 | 96575 | 41331.02 | 55243.98 | 96575 | 38.96%
COA/E | 15157 | MOC | Install a Piperack Layout for AE | 973334427 | Yu Yi | 2015-09-14 | 34500 | 33078 | 30389.36 | 2688.64 | 33078 | 88.09%
COA/E | 15151 | MOC | Modified the Steel Beam above V6650 | 973487180 | Yu Yi | 0 | 111379 | 73700 | 2200 | 71500 | 73700 | 1.975%
COA/L | 15150 | MOC | Add an Anti Dropping Device for A455 Loading Station | 973487181 | Yu Yi | 0 | 131145 | 79750 | 4400 | 75350 | 79750 | 3.355%
CBL/O | 15148 | MOC | Relocate the Vent Pipeline of Manhole of L309 | 973308295 | Zhang Fanwen | 2015-10-30 | 125250 | 102365 | 86989.65 | 15375.35 | 102365 | 69.45%
CBL/O | 15145 | MOC | Add HVAC Control Button in C701 | 973353779 | Gao Feng | 2015-11-26 | 81050 | 86376.03 | 54883.06 | 31492.97 | 86376.03 | 67.72%
CBP/M | 15136 | MOC | Relocation for Flowmeter F85012 of Production Waste Water | 973290387 | Zhang Fanwen | 2015-11-28 | 102100 | 34100 | 19070 | 15030 | 34100 | 18.68%
COO/A | 15135 | MOC | Decrease Viabration of Pipeline from Tower C3100 to C3300 | 973304632 | Wang Can | 0 | 40000 | 36000 | 45170 | 0 | 45170 | 112.9%
CEP/E | 15131 | MOC | Modify Storage Place for Empty Containers | 973288013 | Yan Jun | 2015-12-03 | 261000 | 235930 | 179206.68 | 56723.32 | 235930 | 68.66%
CBL/O | 15129 | MOC | Modification of Power Room of A800 | 973390465 | Hu Xiao | 0 | 125000 | 75874 | 42490.82 | 33383.18 | 75874 | 33.99%
COA/A | 15127 | MOC | Add Tie-in Point for WW Header | 973250501 | Meng Yousheng | 0 | 15000 | 11000 | 11620 | 0 | 11620 | 77.47%
COA/A | 15126 | MOC | Modification for E541 Drain Line | 973250500 | Meng Yousheng | 0 | 25000 | 20900 | 17400 | 3500 | 20900 | 69.6%
CEP/E | 15123 | MOC | Add a Production Water Pipeline to TOC Pond | 973239639 | Li Jun | 0 | 41000 | 40700 | 42330 | 0 | 42330 | 103.2%
COA/L | 15120 | MOC | Add Driver Room for A400 | 973427927 | Yu Yi | 0 | 220000 | 151335 | 17875 | 133460 | 151335 | 8.125%
CBP/C | 15119 | MOC | Add a Work Platform for the Filter F-230 | 973378580 | Wang Shicheng | 2015-12-31 | 51425 | 51425 | 31725 | 19700 | 51425 | 61.69%
CBL/P | 15118 | MOC | Modification for SLOP Piping of Safety Valve of Battery Limit | 973366108 | Zhang Fanwen | 2015-12-28 | 127720 | 117974.34 | 55735.4 | 62238.94 | 117974.34 | 43.64%
CEP/E | 15115 | MOC | Extend Local Trench at Unloading Station | 973516439 | Yan Jun | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
COA/A | 15113 | MOC | CTM/A Build Spare Parts Storage | 973371671 | Yu Yi | 2015-12-30 | 116000 | 117389 | 7150 | 110239 | 117389 | 6.164%
CBP/C | 15110 | MOC | Move the Smoking Room to Outside the Control Building | 973389727 | Wang Shicheng | 0 | 50675 | 51101 | 42089.21 | 9011.79 | 51101 | 83.06%
COO/C | 15106 | MOC | Revamp T3810 to Store DMA | 973240379 | Liu Xiaoli | 0 | 18500 | 18500 | 12385 | 6115 | 18500 | 66.95%
COA/A | 15105 | MOC | Build Garbage Station at GAA Plant | 973246059 | Xia Qun | 0 | 327500 | 332678 | 52179.49 | 280498.51 | 332678 | 15.93%
COA/E | 15101 | MOC | Re-install Deluge Valve for T9610 | 973389266 | Zhang Fanwen | 0 | 127600 | 107600 | 14300 | 93300 | 107600 | 11.21%
CBP/C | 15099 | MOC | Modify Work Platform at the Quench Section | 973377859 | Wang Shicheng | 2015-12-31 | 23825 | 23825 | 20335 | 3490 | 23825 | 85.35%
COO/C | 15098 | MOC | Improve Ventilation Condition of DCS Engineering Room | 973245543 | Yu Yi | 2015-07-30 | 28600 | 22300 | 2865.92 | 19434.08 | 22300 | 10.02%
COA/E | 15094 | MOC | Add a Sluice Valve at the Rain Trench from the DMA3 Pit to Rain Total Pit | 973330990 | Zhang Fanwen | 0 | 95060 | 88035 | 48283.19 | 39751.81 | 88035 | 50.79%
CTE | 15092 | MOC | Modification for Taffic Facilities | 973245545 | Yu Yi | 0 | 499000 | 462800 | 15950 | 446850 | 462800 | 3.196%
COA/S | 15090 | MOC | Extend and Modify the Ditch in Truck Loading Station | 973460235 | Yu Yi | 0 | 149000 | 66000 | 2750 | 63250 | 66000 | 1.846%
COA/E | 15084 | MOC | Add Jacket for T9668 Circulate Pipe | 973268793 | Wang Can | 0 | 195000 | 152580 | 80155.81 | 72424.19 | 152580 | 41.11%
CTS | 15078 | MOC | B655 C1 Lab Item of Feed Additive | 973209930 | Liu Xiaoli | 2015-06-08 | 150000 | 3283.28 | 74271.93 | 0 | 74271.93 | 49.51%
CTE | 15075 | MOC | Fire Fighting Water Pipe Modification for YBS Admin Building | 973219082 | Zhang Fanwen | 2015-08-19 | 281000 | 308864.2 | 194115.59 | 114748.61 | 308864.2 | 69.08%
CEP/P | 15073 | MOC | Add a 4" Tie-in on the VAM Pipe from CLTF to LDPE | 973302646 | Gu Jingfeng | 0 | 105850 | 90850 | 58940.19 | 31909.81 | 90850 | 55.68%
COO/A | 15070 | MOC | Optimization of Gas-Liquid Separation Facilities for Off Gas 1, Off Gas 2, Off Gas3 in ACN | 973190332 | Liu Duo | 2015-05-05 | 65570 | 63570 | 48970.31 | 14599.69 | 63570 | 74.68%
COO/O | 15069 | MOC | The Modification of P1810A/B Input Valve | 973171709 | Yu Xiya | 2015-05-07 | 42000 | 47371.09 | 24558.08 | 22813.01 | 47371.09 | 58.47%
CBL/T | 15067 | MOC | Lead the Fire Alarm Signal of STT101 to STT301 | 973275980 | Bian Jiacai | 0 | 123000 | 78710 | 34421.58 | 44288.42 | 78710 | 27.99%
COA/A | 15065 | MOC | Extending E340 Platform | 973352580 | Yu Yi | 2015-11-25 | 167000 | 105611 | 29264.2 | 76346.8 | 105611 | 17.52%
COA/L | 15059 | MOC | Extend the Rainproof Shed of D620 Loading Station | 973244161 | Yu Yi | 2015-11-28 | 278000 | 199583.2 | 68317.28 | 131265.92 | 199583.2 | 24.57%
COO/C | 15049 | MOC | Demolishing K1200 for PA Expansion Project | 972970641 | Yuan Jinhua | 0 | 2403600 | 3600 | 0 | 3600 | 3600 | 0%
COO/C | 15046 | MOC | Install Card Registration Device | 973120684 | Yan Yicheng | 2015-03-30 | 79188 | 49188 | 48355.24 | 832.76 | 49188 | 61.06%
COA/A | 15045 | MOC | Install Platforms for Salt Pump | 973227191 | Yu Yi | 0 | 460000 | 345080 | 57735 | 287345 | 345080 | 12.55%
COO/C | 15044 | MOC | Alter Arrestors' Location on PA Off Gas Lines | 973126954 | Yuan Jinhua | 2015-03-30 | 15790 | 25790 | 18545 | 7245 | 25790 | 117.4%
CEP/L | 15043 | MOC | Revamp the Gound of A915 with Epoxy Resin | 973143414 | Xia Qun | 2015-09-30 | 658000 | 584225 | 509100.8 | 75124.2 | 584225 | 77.37%
COO/C | 15018 | MOC | Revamp Valves and Pipe Connections of Utility Station in C1 Complex | 973358700 | Yuan Jinhua | 0 | 18550 | 18550 | 5205 | 13345 | 18550 | 28.06%
COO/C | 15017 | MOC | Revamp HVAC System in C1 Control Building | 973160155 | Gao Feng | 2015-09-18 | 501000 | 168100 | 156395.05 | 11704.95 | 168100 | 31.22%
CEP/P | 15013 | MOC | Add Two Steam Traps for the P11807 MP Steam | 973160145 | Gu Jingfeng | 2015-09-15 | 121000 | 129806 | 90073.94 | 39732.06 | 129806 | 74.44%
CBP/S | 15012 | MOC | Add New Water Source for Air Coolers E1741's Sprayers | 973333837 | Chen Chen | 0 | 195400 | 136400 | 2750 | 133650 | 136400 | 1.407%
COO/O | 15008 | MOC | Upgrade Open Items According to the Process Safety Review Requirements | 973049116 | Gong Feibao | 2015-09-22 | 17100 | 17100 | 20690 | 0 | 20690 | 121%
CBL/P | 15006 | MOC | Revamp HVAC System in CLTF Control Building | 973181190 | Gao Feng | 2015-11-26 | 364000 | 164601.04 | 77816.28 | 86784.76 | 164601.04 | 21.38%
COO/C | 15005 | MOC | The Revamping of Smoking Room in C1 Plant | 973203335 | Gao Feng | 2015-10-12 | 89000 | 95770 | 78586.61 | 17183.39 | 95770 | 88.3%
CBP/P | 14322 | MOC | Revamp HVAC System in PP Control Building and Adm. Building | 973189552 | Gao Feng | 2015-09-25 | 705000 | 429317.76 | 339749.3 | 89568.46 | 429317.76 | 48.19%
CBP/M | 14319 | MOC | Revamping the Ground of Concocting Room of Cooling Water Dosing System | 973035133 | Gao Feng | 2015-06-12 | 198975 | 191500 | 145282.23 | 46217.77 | 191500 | 73.02%
COO/C | 14301 | MOC | Add Some Manual Valves in DMA Plant | 973043163 | Li Shouqing | 0 | 186705 | 98105 | 154288.59 | 0 | 154288.59 | 82.64%
CBP/M | 14299 | MOC | Revamping Dry Gas Seal System | 973357432 | Chu Chao | 2015-05-31 | 91900 | 265135.35 | 91241.85 | 173893.5 | 265135.35 | 99.28%
CBL/T | 14295 | MOC | Relocate the Fire-fighting Monitor WM-L202 | 973331498 | Zhang Fanwen | 2015-12-02 | 97450 | 96528 | 60646.17 | 35881.83 | 96528 | 62.23%
CEP/L | 14289 | MOC | Add Leakage Detectors for Packing Line | 973211318 | Zhou Yanduo | 2015-12-04 | 371000 | 317850 | 327307.78 | 0 | 327307.78 | 88.22%
CEP/E | 14283 | MOC | Seperate 2-PH and DEG Safety Valve Discharge Lines | 972922028 | Wang Zhigao | 2015-05-13 | 50000 | 46200 | 48190 | 0 | 48190 | 96.38%
CBP/C | 14280 | MOC | Add Site Lighting Sysyem in Start-up Boiler Section | 973286478 | Hu Xiao | 2015-11-30 | 147000 | 103930.83 | 110907.84 | 0 | 110907.84 | 75.45%
CBP/U | 14269 | MOC | Modify the impeller of P8701 | 973343789 | Chen Yuxin | 0 | 199180 | 174278.4 | 48805 | 125473.4 | 174278.4 | 24.5%
CBP/U | 14268 | MOC | The Top Flatform of Co-incinerator Expand | 973113995 | Yu Yi | 2015-06-19 | 224000 | 217877.65 | 146325.01 | 71552.64 | 217877.65 | 65.32%
CEP/E | 14266 | MOC | Change Work Liquid of Z3770-8 from DMW to CW | 972956291 | Wang Zhigao | 2015-05-13 | 35000 | 33120 | 32962.82 | 157.18 | 33120 | 94.18%
CEP/E | 14265 | MOC | Add a Flowmeter on NG to EOEG Flare Pilot Burner | 972956292 | Wang Zhigao | 2015-05-13 | 40000 | 38770 | 42120 | 0 | 42120 | 105.3%
CBL/T | 14264 | MOC | Add a Container as a Lounge Room at Loading&Unloading Station in SCTF | 973270047 | Wang Shicheng | 2015-11-16 | 110625 | 121158.87 | 133864.13 | 0 | 133864.13 | 121%
CBP/C | 14263 | MOC | Change the Pipe Size of Second Burner of Fuel Gas from 3" to 4" | 973168953 | Chen Chen | 2015-10-30 | 262200 | 172380 | 160798.11 | 11581.89 | 172380 | 61.33%
COO/A | 14247 | MOC | Add Water Cooler and Inducer for Pumps P2400/P2500/P2600 | 972922251 | Liu Duo | 2015-05-25 | 273200 | 34375.19 | 384748.11 | 0 | 384748.11 | 140.8%
CTS/U | 14246 | MOC | Move the Tie-in to SAP HP Steam in TAR | 972924061 | Yu Xiya | 2015-05-07 | 230000 | 235720 | 329170.17 | 0 | 329170.17 | 143.1%
COA/A | 14233 | MOC | Extend the Waterproof of Stabilizer Preparation Station | 973236661 | Yu Yi | 0 | 186000 | 153570 | 57842.97 | 95727.03 | 153570 | 31.1%
CEP/P | 14228 | MOC | Modify Pellet CW Exchanger to Parallel Mode | 972895397 | Gu Jingfeng | 2015-07-29 | 219000 | 196900 | 216369.2 | 0 | 216369.2 | 98.8%
CEP/L | 14225 | MOC | Repaving the Concrete Ground in PS Warehouse | 973191611 | Gao Feng | 2015-10-29 | 1294000 | 1152068 | 79148.69 | 1072919.31 | 1152068 | 6.117%
COA/S | 14224 | MOC | Modification for Potable Water Line | 972927197 | Xu Jin | 2015-08-07 | 230000 | 204624.28 | 173912.62 | 30711.66 | 204624.28 | 75.61%
CBP/B | 14221 | MOC | Replace the FV-1503 with a More Suitable Control Valve | 973256493 | Gong Feibao | 0 | 179248 | 120171.71 | 51634.79 | 68536.92 | 120171.71 | 28.81%
CEP/S | 14220 | MOC | Replace the Push Button of Electric Motor in CEP/S | 973025628 | Xu Zheng | 0 | 366540 | 155540 | 164287.23 | 0 | 164287.23 | 44.82%
CBP/C | 14216 | MOC | Add Safe Passage between the Work Platform in PGU Section | 973152182 | Wang Shicheng | 2015-09-21 | 100000 | 78974 | 62113.21 | 16860.79 | 78974 | 62.11%
CBP/C | 14215 | MOC | Add Work Platform nearby the Flow Meters | 973152181 | Wang Shicheng | 2015-09-21 | 160000 | 132712 | 126187.26 | 6524.74 | 132712 | 78.87%
CBL/O | 14213 | MOC | Add 3 Wall-fans on the Wall of A605 PALD Drum filling Workshop | 972877642 | Yu Yi | 2015-07-21 | 261000 | 233111.34 | 257308.46 | 0 | 257308.46 | 98.59%
CBP/C | 14212 | MOC | Add N2 and Blowdown Pipe from SCTF to 274 Steel Structure Yixi Road | 972827264 | Chen Chen | 2015-05-09 | 558000 | 537820.92 | 637737.12 | 0 | 637737.12 | 114.3%
CAP/A | 14209 | MOC | Modification for F450B/F455A and Add Filters for T9514/16 | 972793548 | Zhu Jianxin | 2015-04-30 | 700000 | 360539.74 | 631156.96 | 0 | 631156.96 | 90.17%
CCP/A | 14201 | MOC | Move Mass Flowmeter F23002 from the 2nd Floor to the 1st Floor | 972887482 | Liu Duo | 2015-05-06 | 70000 | 21000 | 38518.26 | 0 | 38518.26 | 55.03%
CEP/P | 14196 | MOC | Add the Vibration Signal into DCS System for K11501&K21501 | 972760217 | Shen Liying | 2015-02-06 | 415000 | 197310.43 | 552197.25 | 0 | 552197.25 | 133.1%
CBP/S | 14195 | MOC | Add Polished Condensate Makeup Line to U1621 & U1861 | 973041189 | Wang Can | 0 | 198950 | 153902.74 | 47519.08 | 106383.66 | 153902.74 | 23.88%
CEP/E | 14189 | MOC | EOEG Cable Tray Replacement | 972743165 | Hao Yongyong | 2015-05-07 | 1550000 | 1638570 | 1588539.96 | 50030.04 | 1638570 | 102.5%
CAP/E | 14128 | MOC | Change T9668 Waste Water Tank to DMA3 Heavies Tank | 972684047 | Xu Jin | 2014-09-04 | 400000 | 414457.81 | 467881 | 0 | 467881 | 117%
CBP/S | 14120 | MOC | Add Silencer for Venting Line of External CO2 | 972586402 | Gu Jingfeng | 2015-07-24 | 82700 | 114575.68 | 98779.07 | 15796.61 | 114575.68 | 119.4%
CBP/C | 14119 | MOC | Add New Pipeline to Transport Liquid LPG from STT1120 to the Furnace | 972722696 | Sun Aihong | 2014-10-20 | 390000 | 622733.89 | 643699.29 | 0 | 643699.29 | 165.1%
CBP/A | 14109 | MOC | Add a Steam Trap for 520-E-204 | 972670911 | Wang Can | 2015-05-09 | 162000 | 122399.02 | 162803.63 | 0 | 162803.63 | 100.5%
CBP/C | 14073 | MOC | Move Control Valve FV2408 to the Inlet Nozzle of V910 | 972702734 | Wang Can | 2015-05-09 | 147725 | 107468.53 | 151650.39 | 0 | 151650.39 | 102.7%
CBP/A | 14069 | MOC | Add a Bypass Line from AEU Pit Drum to PGU Off-spec Drum | 972731699 | Chen Chen | 2014-10-17 | 191000 | 220150.19 | 268708.9 | 0 | 268708.9 | 140.7%
CBP/M | 14065 | MOC | Replace Butterfly Valves for Cooling Water Tower | 972676906 | Sun Aihong | 2015-04-30 | 487000 | 544005.2 | 404481.24 | 139523.96 | 544005.2 | 83.06%
CBP/B | 14061 | MOC | Add a Support for E1604 | 972631740 | Ding Juntao | 2015-04-25 | 155550 | 82550 | 29480.39 | 53069.61 | 82550 | 18.95%
CBP/C | 14059 | MOC | Add a Flowmeter on Continuous Blowdown Pipeline of H109 | 972651625 | Wang Can | 2015-05-09 | 190000 | 156462.42 | 192171.77 | 0 | 192171.77 | 101.1%
CTS/P | 14044 | MOC | Modify Filter ST6503 | 972785185 | Chen Yangwei | 2015-05-06 | 239925 | 141419.23 | 412800.67 | 0 | 412800.67 | 172.1%
CBP/M | 14040 | MOC | Modify Discharge Temperature Interlock System of H2301 | 972732621 | Gong Feibao | 2015-04-29 | 405000 | 218063.51 | 187376.92 | 30686.59 | 218063.51 | 46.27%
CBP/M | 14036 | MOC | Adding Two Flammable Gas Detectors in CWR Pipe | 972937929 | Gong Feibao | 2015-11-04 | 291000 | 259140.85 | 282094.63 | 0 | 282094.63 | 96.94%
CBP/C | 14028 | MOC | Modification of Flare Obstacle Lighting and Ignition System for EU | 972802859 | Tong Shaojian | 0 | 2500000 | 193191.23 | 2453339.54 | 0 | 2453339.54 | 98.13%
CBP/C | 14024 | MOC | Change Temporary Tie to Permanent Type for the Lines from Wison and E930 | 972319739 | Qiu Zhufeng | 2015-05-09 | 135000 | 68675 | 79377.44 | 0 | 79377.44 | 58.8%
CBP/C | 14022 | MOC | Add a Pipeline from Seal Oil Drainer to 330-V-310 | 972320940 | Qiu Zhufeng | 2015-05-09 | 139000 | 71475 | 67617.86 | 3857.14 | 71475 | 48.65%
CBP/B | 14020 | MOC | Add Silencer in Steam Venting Line of V514 | 972377375 | Chen Chen | 2015-04-25 | 121000 | 119277.7 | 144464.16 | 0 | 144464.16 | 119.4%
CBP/B | 14017 | MOC | Add a Basket Filter on Outlet Line of P404A/B | 972576812 | Wang Can | 2015-05-04 | 176000 | 99660.28 | 150682.12 | 0 | 150682.12 | 85.61%
CBP/C | 13246 | MOC | Add Filters for IA Header | 971989443 | Wang Can | 2015-05-04 | 271000 | 196036.96 | 297744.28 | 0 | 297744.28 | 109.9%
COA/A | 13216 | MOC | Install the Deep Pipes in CAA Tanks for Restab System | 971848268 | Li Xingming | 0 | 26400 | 26400 | 27500 | 0 | 27500 | 104.2%
CBP/B | 13052 | MOC | Add One Pipeline from C1200 to EU C220 for Recycling Offgas | 971877174 | Sun Aihong | 2014-05-30 | 437100 | 491174.08 | 528057.2 | 0 | 528057.2 | 120.8%
Formulas:
MC = VLOOKUP([Job No],[1]Eproject!$A:$P,16,FALSE)