## Overview
BU. Code | Job No. | Job Type | Lead By | Job Title | Budget (RMB) | Project Manager | Construction Manager | Engineering Manager | Approval Date | MC Planed | MC Revised | Priority | Category | Job Status | Schedule | Cost | Scope | Received Date | Estimated Final Cost(RMB) | MC Actual | MC Signed | RFSU | Punch C Killed | FC Signed | Business Closed | IFC Received | As-built Received | MD Received | Date of Registeration | Cost Effectivity | PVI | Cancel Date | Account No. | Network No. | Study WO | CTE Involved | CAPEX Plan No | CDI | MOC Form No
Note on U1: Min Chen: 超出计划MC6个月仍未有实际MC日期的为红色
Note on V1: Min Chen: 超出实际MC10天仍未签MC证书的为红色。
Note on Y1: Min Chen: 超出实际MC90天仍未签TCCC证书的为红色。
Note on Z1: Min Chen: 超出TCCC180天仍未商务关闭的为红色。
Note on AB1: Min Chen: 超出实际MC90天仍未收到AB的为红色。

## Permit_General
项目号 | 项目名称 | 项目经理 | 计划/实际 | 环评 | 节能报告 | 项目备案 | 规划许可 | 安全条件 审查 | 安全设施 设计审查 | 消防设计 审查 | 施工许可 | 施工开始 | 机械竣工 | 安全设施 竣工验收 | 消防设施 竣工验收 | 投用 | 环保设施 竣工验收

## Permit_Pressure Piping & Vesse
项目号 | 项目名称 | 项目经理 | 计划/实际 | 压力管道 | 压力容器 | SQIB | 档案验收 | 第三方监理

## Schedule_Gantt_Bar
General
Job No. | BU. Code | Job Type | Job Title | Priority | Category | Schedule
Note on A1: Wang Daan: A: Receive Date ~ Approval Date B: Approval Date ~ Const. ME (Civil) Start C: Const ME (Civil) Start ~ DE ME(Civil) End D: DE ME(Civil) Ebd ~ Const ME(Civil) End