## Overview
BU. Code | Job No. | Job Type | Lead By | Job Title | Budget (RMB) | Project Manager | Construction Manager | Approval Date | MC Planed | MC Revised | Priority | Category | Job Status | Schedule | Cost | Scope | Received Date | Estimated Final Cost(RMB) | MC Actual | MC Signed | FC Signed | Business Closed | IFC Received | As-built Received | MD Received | Cost Effectivity | PVI | Cancel Date | Network No. | CDI
Note on T1: Min Chen: 超出计划MC6个月仍未有实际MC日期的为红色
Note on U1: Min Chen: 超出实际MC10天仍未签MC证书的为红色。
Note on V1: Min Chen: 超出实际MC90天仍未签TCCC证书的为红色。
Note on W1: Min Chen: 超出TCCC180天仍未商务关闭的为红色。
Note on Y1: Min Chen: 超出实际MC90天仍未收到AB的为红色。

## Permit_General
项目号 | 项目名称 | 项目经理 | 计划/实际 | 环评 | 节能报告 | 项目备案 | 规划许可 | 安全条件 审查 | 安全设施 设计审查 | 消防设计 审查 | 施工许可 | 施工开始 | 机械竣工 | 安全设施 竣工验收 | 消防设施 竣工验收 | 投用 | 环保设施 竣工验收

## Permit_Pressure Piping & Vesse
项目号 | 项目名称 | 项目经理 | 计划/实际 | 压力管道 | 压力容器 | SQIB | 档案验收 | 第三方监理

## Schedule_Gantt_Bar
General
Job No. | BU. Code | Job Type | Job Title | Priority | Category | Schedule
Note on A1: Wang Daan: A: Receive Date ~ Approval Date B: Approval Date ~ Const. ME (Civil) Start C: Const ME (Civil) Start ~ DE ME(Civil) End D: DE ME(Civil) Ebd ~ Const ME(Civil) End

## Rolesview
General | [5 empty] | ROLES | [12 empty] | ROLES | [5 empty] | ROLES
BU. Code | Job No. | Job Type | Job Title | Job Status | Priority | M00 _Pro Mngmnt | P10 _Pro Des | P11 _Pro Che | P12 _Pro App | P20 _Mec/Equ Des | P21 _Mec/Equ Che | P22 _Mec/Equ App | P30 _Plu/FF Des | P31 _Plu/FF Che | P32 _Plu/FF App | P40 _Pip Des | P41 _Pip Che | P42 _Pip App | A10 _Ins Des | A11 _Ins Che | A12 _Ins App | A20 _Ele Des | A21 _Ele Che | A22 _Ele App | C10 _Civ Des | C11 _Civ Che | C12 _Civ App | C20 _MP Des | C21 _MP Che | C22 _MP App