## 2-TP-02-试压包封面UG-FW-001
[8 empty] | Form No. | TP-002
巴斯夫（广东）一体化项目专用化学品二区 BASF(Guangdong) Integrated Project Citral Cluster
管道试压包 PIPING TEST PACKAGE
| 试压包号 |  |  | UG-130-FW-HT-0001
PACKAGE NUMBER
| 试验压力 |  |  | 2 | Mpa
TEST PRESSURE
| 试压介质 |  | R | 水压试验 Hydro Test |  | ¨ | 气压试验 Pneumatic Test
| TEST MEDIUM |  | ¨ | 运行试验 Service Test |  | ¨ | 目测试验 Visual Test
| 系统编号 |  |  | UG-FW
SYSTEM No.
| 系统名称 |  |  | 地下消防管道
| SYSTEM DESCRIPTION |  |  | UG Fire Water
| 施工单位 |  | 中国化学工程第七建设有限公司 CC7
CONSTRUCTION COMPANY
| 监理单位 |  | 上海申峰工程建设监理有限公司 SHENFENG
JIANLI
| 项目管理公司 |  | 连云港沃利工程技术有限公司 WORLEY
PMC
| 建设单位 |  | 巴斯夫一体化基地（广东）有限公司 BASF
OWNER

## 3-TP-03-试压包目录UG-FW-001
[6 empty] | Form No： | TP-03
巴斯夫（广东）一体化项目专用化学品二区 BASF(Guangdong) Integrated Project Citral Cluster
目录 CONTENTS
| 1 | R | PIPING TEST PACKAGE ROUTING FORM(TP-01) |  | 试压包路径表
| 2 | R | TEST PACKAGE COVER(TP-02) |  | 试压包封面
| 3 | R | TEST PACKAGE CONTENTS(TP-03) |  | 试压包目录
| 4 | R | TEST DIAGRAM LEGEND(TP-04) |  | 试压标识
| 5 | R | LINE LIST |  | 管道特性表
| 6 | R | P&ID/GAD LIST(TP-05) |  | 流程图清单
| 7 | R | MARKED UP P&ID / GAD |  | 流程图/平面布置图
| 8 | R | ISO LIST(TP-06) |  | 单线图清单
| 9 | R | MARKED UP ISO |  | 单线图
| 10 | R | LIST OF DESIGN CHANGES(J110) |  | 工程设计变更一览表
| 11 | R | BLIND LIST(TP-07) |  | 盲板清单
| 12 | R | BLIND SELECTION TABLE |  | 盲板选用对照表
| 13 | x | SPRING/HANGER SUPPORT INSTALATION INSPECTION RECORD(J403) |  | 弹簧支/吊架安装检验记录
| 14 | x | SLIDING/FIXED PIPE SHOE INSTALLATION INSPECTION RECORD(J404) |  | 滑动/固定管托安装检验记录
| 15 | x | PIPE COMPENSATOR INSTALLATION INSPECTION RECORD(J405) |  | 管道补偿器安装检验记录
| 16 | x | LIST OF PIPING ELECTROSTATIC GROUNDING(TP-08) |  | 管道静电接清单
| 17 | x | PIPING WELDED JOINT HEAT TREATMENT REPORT(J411) |  | 管道焊接接头热处理报告
| 18 | x | METAL MATERIAL CHEMICAL COMPOSITION TEST REPORT(J129) |  | 金属材料化学成分检验报告
| 19 | x | HARDNESS TEST REPORT(J130) |  | 硬度检测报告
| 20 | R | LINE HISTORY SHEETS |  | 管道追溯表
| 21 | R | PIPING WELDING RECORD(J415) |  | 管道焊接工作记录
| 22 | R | RT CONFIRMATION FORM(J412-2007) |  | 射线检测比例确认表
| 23 | R | UT/PAUT/TOFD CONFIRMATION FORM(TP-09) |  | 超声/PAUT/TOFD检查比例确认表
| 24 | x | PT/MT CONFIRMATION FORM(TP-10) |  | 渗透/磁粉检查比例确认表
| 25 | R | SUMMARY OF PIPING NDT RESULTS(J412-2017) |  | 管道无损检测结果汇总表
| 26 | R | PIPING NDT QUANTITY STATISTICAL FORM(J413) |  | 管道无损检测数量统计表
| 27 | R | PUNCH LIST(TP-11) |  | 尾项清单
| 28 | R | WATER(MACHINE) CALIBREATION LIST(TP-12) |  | 试压用水（具）检查清单
| 29 | R | WATER QUALITY TESTING REPORT |  | 水质检测报告
| 30 | R | PRESSURE GAUGE INSPECTION CERTIFICATE |  | 压力表检验合格证
| 31 | x | SAFETY VALVE CALIBRATION REPORT |  | 安全阀校验报告
| 32 | R | PIPING SYSTEM PRESSURE TEST CONDITION CONFIRMATION RECORD(J406-1) |  | 管道系统压力试验条件确认记录
| 33 | R | PIPING SYSTEM PRESSURE TEST RECORD(J406-2) |  | 管道系统压力试验记录
| 34 | R | RECORD OF FLUSHING AND BLOWING REPORT(J408) |  | 吹扫/清洗记录
| 35 | R | RECORD OF REINSTATEMENT REPORT(TP-13) |  | 复位记录
| 36 | R | BOLT TORQUE/TIGHTENING REPORT(TP-14) |  | 法兰扭矩记录表

## 4-TP-04-试压标识
| Form No. | TP-04
巴斯夫（广东）一体化项目专用化学品二区 BASF(Guangdong) Integrated Project Citral Cluster
试压标识 TEST DIAGRAM LEGEND
TEST LIMIT
OPEN VALVE
CLOSE VALVE
TEMPORARY SPOOL
TEST BLIND
SPECTACLE BLIND CLOSE
VALVE TO BE REMOVED
GOLDEN JOINT (100% X-RAY)
INSTALL PLUG
REMOVE INTERNAL
REMOVE ELEMENTS
TEST CAP
WATER INJECTION POINT
PRESSURE GAUGE
HIGHEST POINT / VENT
Test Manifold With PSV, Pressure Gauge & Drain valve
C
S
TB
SB
RV
GJ
IP
RI
RE
TC
WIP
O
PG
V
TM
C
S
TB
SB
RV
GJ
IP
RI
RE
TC
WIP
O
PG
V
TM